## Schedule Instructions
I. | Instructions for Schedule of Products and Due Dates
This workbook contains the spreadsheet for the Schedule of Products and Due Dates. Items in <blue type> need to be completed. All other items should remain unchanged.
For each Administrative Task, insert the planned start and completion dates. For the Critical Project Reviews (CPRs), add as many CPRs as the project requires. If this form is being completed by an Applicant as part of a proposal to the Energy Commission, leave the CPR sections blank. These sections will be completed by the Energy Commission prior to issuing a funding award.
For each Technical Task, insert the name of each task as it is titled in the Scope of Work, the name of each product(s) associated with each task as they are titled in the Scope of Work (using Caps and Bold), and the planned completion dates. Delete or insert rows as necessary.

## Schedule of Products
Schedule of Products and Due Dates
Task Number | Task Name | Product(s) | Due Date | PIER Funds | Match Funds
1.1 | Attend Kick-off Meeting
|  | Updated Schedule of Products | <Insert Date>
|  | Updated List of Match Funds | <Insert Date>
|  | Updated List of Permits | <Insert Date>
|  | Written Statement of Match Share Activities | <Insert Date>
|  | Kick-Off Meeting Agenda (CEC) | <Insert Date>
1.2 | Critical Project Review Meetings
| 1st CPR Meeting | CPR Report | <CEC will complete>
|  | CPR Meeting Agenda (CEC) | <CEC will complete>
|  | Schedule for written determination (CEC) | <CEC will complete>
|  | Written determination (CEC) | <CEC will complete>
<CEC will complete> |  | <CEC will complete> | <CEC will complete>
|  | <CEC will complete> | <CEC will complete>
1.3 | Final Meeting
|  | Written documentation of meeting agreements | <Insert Date>
|  | Schedule for completing closeout activities | <Insert Date>
1.4 | Monthly Calls
|  | Email to CAM concurring with call summary notes | Within 5 days of receipt
1.5 | Quarterly Progress Reports
|  | Quarterly Progress Reports | 10th calendar day of each January, April, July, and October during the approved term of this Agreement
1.6 | Final Report
|  | Final Outline of the Final Report | <Insert Date>
|  | Draft Final Report | <Insert Date> | 0 | 0
|  | Final Report (no less than 60 days before the end term of the agreement) | <Insert Date>
1.7 | Identify and Obtain Match Funds
|  | A letter regarding match funds or stating that no match funds are provided | <Insert Date> | 0 | 0
|  | Copy(ies) of each match fund commitment letter(s) (if applicable) | <Insert Date>
|  | Letter(s) for new match funds (if applicable) | Within 10 days of identifying new match funds | 0 | 0
|  | Letter that match funds were reduced (if applicable) | Within 10 days of identifying reduced funds | 0 | 0
1.8 | Identify and Obtain Required Permits |  |  | 0 | 0
|  | Letter documenting the permits or stating that no permits are required | <Insert Date>
|  | A copy of each approved permit (if applicable) | Within 10 days of receiving each permit | 0 | 0
|  | Updated list of permits as they change during the term of the Agreement (if applicable) | Within 10 days of change in list of permits
|  | Updated schedule for acquiring permits as changes occur during the term of the Agreement (if applicable) | Within 10 days of change in schedule for obtaining permits
|  | A copy of each final approved permit (if applicable) | Within 10 days of receiving each permit
1.9 | Obtain and Execute Subawards
|  | Letter describing the subawards needed, or stating that no subawards are required | <Insert Date>
|  | Draft subcontracts (if requested) | 15 days prior to the scheduled execution date
|  | Final subcontracts (if requested) | Within 10 days of execution
1.10 | Handling CEC Or Third-Party Confidential Information and Personal Information
|  | Signed non-disclosure agreement from Contractor and Subcontractor employees | <Insert Date prior to Task 3 (Deployment)>
|  | Signed Information Security Program Plan Attestation Form | <Insert Date prior to Task 3 (Deployment)>
|  | Employee Security Awareness Training Certificates | <Insert Date prior to Task 3 (Deployment)>
|  | Verification of destruction of confidential information and personal information | <Insert Date prior to Task 3 (Deployment)>
2 | Phase 1 Product Development |  |  | 0 | 0
<Applicant may update task and product names as needed>
|  | Evidence of product development, product capabilities, product testing, and ultimately customer availability of the product | <Insert Date>
|  | Evidence that the product meets the minimum interoperability requirements | <Insert Date>
|  | <Add/delete rows as necessary> | <Insert Date>
3 | Phase 1 Customer Deployment
<Applicant may update task and product names as needed>
|  | Evidence of each completed customer deployment | <Enter Phase 1 deployment START date and COMPLETION date> | 0 | 0
|  | Entry of deployment information in the Customer Deployment Log | <Same as above>
|  | Indication of participation in SCE Dynamic Rates pilot for in the Customer Deployment Log each participating deployment | <Same as above>
|  | Evidence of coordination and coordination plans with project team partners | <Same as above>
|  | Datasheets for each EVSE model listed in the Customer Deployment Log indicating certification by a Nationally Recognized Test Laboratory and the Open Charge Alliance, or equivalent. | <Same as above>
|  | Completed and signed AB 841 Certification. | <Same as above> | 0 | 0
|  | Entry of EVITP Certification Numbers in the Customer Deployment Log | <Same as above> | 0 | 0
4 | Data Collection, Analysis, and Reporting
|  | Customer deployment data collection and reporting plan | <Insert Date>
|  | Ongoing collection and storage of 15-minute charging data | <Enter Phase 1+2 deployment START date and COMPLETION date>
|  | Ongoing reporting of two normalized profiles as described in Reference Section 3 at the end of the SOW document, reported monthly | <Same as above>
|  | Ongoing reporting of an average $/kWh value of electricity used for charging that month for each deployment, reported monthly | <Same as above>
|  | Ongoing reporting of an average price ($/kWh) of electricity for charging that would have been realized that month on an otherwise-applicable electricity rate for each deployment with a customer enrolled on a dynamic rate, reported monthly | <Same as above>
|  | Ongoing maintenance of an accurate and up to date Customer Deployment Log, reported monthly | <Same as above>
|  | Report containing other legislatively required data reporting as described in Assembly Bill 211 and Reference Section 3 at the end of the SOW document | <Insert Date>
|  | Evidence of compliance with all applicable regulatory requirements for recordkeeping and reporting standards, including but not limited to uptime requirements and operation and maintenance requirements. | <Enter Phase 1+2 deployment START date and COMPLETION date>
<Second to Last> | Phase 2 Customer Deployment |  | <Delete this task if no Phase 2 is proposed>
|  | Evidence of each completed customer deployment | <Enter Phase 2 deployment START date and COMPLETION date>
|  | Entry of deployment information in the Customer Deployment Log | <Same as above>
|  | Indication of participation in SCE Dynamic Rates pilot for in the Customer Deployment Log each participating deployment | <Same as above>
|  | Evidence of coordination and coordination plans with project team partners | <Same as above>
|  | Datasheets for each EVSE model listed in the Customer Deployment Log indicating certification by a Nationally Recognized Test Laboratory and the Open Charge Alliance, or equivalent. | <Same as above>
|  | Completed and signed AB 841 Certification. | <Same as above>
|  | Entry of EVITP Certification Numbers in the Customer Deployment Log | <Same as above>
<Last> | PROJECT FACT SHEET |  |  | 0 | 0
|  | Initial Project Fact Sheet | <Insert Date>
|  | Final Project Fact Sheet | <Insert Date> | 0 | 0
|  | High Quality Digital Photographs | <Insert Date>