## Schedule Instructions
I. | Instructions for Schedule of Products and Due Dates
This workbook contains the spreadsheet for the Schedule of Products and Due Dates. Items in <blue type> need to be completed. All other items should remain unchanged.
For each Administrative Task, insert the planned start and completion dates. For the Critical Project Reviews (CPRs), add as many CPRs as the project requires. If this form is being completed by an Applicant as part of a proposal to the Energy Commission, leave the CPR sections blank. These sections will be completed by the Energy Commission prior to issuing a funding award.
For each Technical Task, insert the name of each task as it is titled in the Scope of Work, the name of each product(s) associated with each task as they are titled in the Scope of Work (using Caps and Bold), and the planned completion dates. Delete or insert rows as necessary.

## Schedule of Products
Schedule of Products and Due Dates
Task Number | Task Name | Product(s) | Due Date | PIER Funds | Match Funds
1.1 | Attend Kick-off Meeting
|  | Updated Schedule of Products | <Insert Date>
|  | Updated List of Match Funds | <Insert Date>
|  | Updated List of Permits | <Insert Date>
|  | Written Statement of Match Share Activities | <Insert Date>
|  | Kick-Off Meeting Agenda (CEC) | <Insert Date>
1.2 | Critical Project Review Meetings
| 1st CPR Meeting | CPR Report | <Insert Date>
|  | CPR Meeting Agenda (CEC) | <Insert Date>
|  | Schedule for written determination (CEC) | <Insert Date>
|  | Written determination (CEC) | <Insert Date>
<Add as many CPRs as required> |  | <Utilize same products as 1st CPR Meeting> | <Insert Date>
|  | <Utilize same products as 1st CPR Meeting> | <Insert Date>
1.3 | Final Meeting
|  | Written documentation of meeting agreements | <Insert Date>
|  | Schedule for completing closeout activities | <Insert Date>
1.4 | Monthly Calls
|  | Email to CAM concurring with call summary notes | Within 5 days of receipt
1.5 | Quarterly Progress Reports
|  | Quarterly Progress Reports | 10th calendar day of each January, April, July, and October during the approved term of this Agreement
1.6 | Final Report
|  | Final Outline of the Final Report | <Insert Date>
|  | Draft Final Report | <Insert Date> | 0 | 0
|  | Final Report (no less than 60 days before the end term of the agreement) | <Insert Date>
1.7 | Identify and Obtain Match Funds
|  | A letter regarding match funds or stating that no match funds are provided | <Insert Date> | 0 | 0
|  | Copy(ies) of each match fund commitment letter(s) (if applicable) | <Insert Date>
|  | Letter(s) for new match funds (if applicable) | Within 10 days of identifying new match funds | 0 | 0
|  | Letter that match funds were reduced (if applicable) | Within 10 days of identifying reduced funds | 0 | 0
1.8 | Identify and Obtain Required Permits |  |  | 0 | 0
|  | Letter documenting the permits or stating that no permits are required | <Insert Date>
|  | A copy of each approved permit (if applicable) | Within 10 days of receiving each permit | 0 | 0
|  | Updated list of permits as they change during the term of the Agreement (if applicable) | Within 10 days of change in list of permits
|  | Updated schedule for acquiring permits as changes occur during the term of the Agreement (if applicable) | Within 10 days of change in schedule for obtaining permits
|  | A copy of each final approved permit (if applicable) | Within 10 days of receiving each permit
1.9 | Obtain and Execute Subawards
|  | Letter describing the subawards needed, or stating that no subawards are required | <Insert Date>
|  | Draft subcontracts (if requested) | 15 days prior to the scheduled execution date
|  | Final subcontracts (if requested) | Within 10 days of execution
2 | <Insert Name of Task (using Caps and Bold)> |  |  | 0 | 0
|  | <Insert 1st Product Name> | <Insert Date>
|  | <Insert 2nd Product Name> | <Insert Date>
|  | <etc. Add/delete rows as necessary> | <Insert Date>
3 | <Insert Name of Task (using Caps and Bold)>
|  | <Insert 1st Product Name> | <Insert Date> | 0 | 0
|  | <Insert 2nd Product Name> | <Insert Date> | 0 | 0
|  | <etc. Add/delete rows as necessary> | <Insert Date> | 0 | 0
4.2 | RECORDKEEPING
|  | Remote Monitoring Records | Within 10 business days of CEC request
|  | Maintenance Records | Within 10 business days of CEC request
|  | Data Dictionary | Within 10 business days of CEC request
4.3 | MAINTENANCE REQUIREMENTS
|  | Maintenance section of annual report | <Insert Date>
4.4 | REPORTING
|  | Annual Report on Charger Reliability and Maintenance | 10th day of each January
5 | DATA COLLECTION AND ANALYSIS
|  | Data on charger installations and charging events will be submitted electronically in Quarterly Progress Reports | 10th day of each January, April, July, and October
|  | Data collection information and analysis | No less than 60 days before the end term of the agreement
6 | PROJECT FACT SHEET |  |  | 0 | 0
|  | Initial Project Fact Sheet | <Insert Date>
|  | Final Project Fact Sheet | <Insert Date> | 0 | 0
|  | High Quality Digital Photographs | <Insert Date>