## Project Schedule
Carefully read the instructions in this row before completing the project schedule.
Delete instructions after completing the schedule by right clicking on the rows number and selecting "delete."
• Insert the name of the applicant/recipient where indicated above in blue.
• Insert the estimated Agreement term where indicated below in blue. If the Scope of Work is being prepared for a solicitation, please follow any
guidelines regarding start and end dates.
• Insert technical task, subtask, and product names in the “Task/Subtask Name” and “Product(s)” columns, where indicated in blue. These names
must match the names in Part IV of the Scope of Work (Technical Tasks). If a draft and final version are required, insert “Draft” and “Final”
before the product name and place the draft and final product names on separate rows in the “Products” column (see subtasks 1.6.1 and 1.6.2).
• Insert product due dates in the “Due Date” column, where indicated in blue. Dates must fall within the agreement term and may not fall on weekends
(the date will turn red if it falls on the weekend). Insert dates in the M-D-YYYY format. Example: 5-1-2015.
• Due dates for all technical tasks other than the “TBD” tasks must precede the last 5 months of the agreement unless otherwise specified by the CAM.
These months should focus on development of the Final Report and "TBD" tasks.
• The CAM will insert all information in green prior to execution of the agreement, including meeting dates and questionnaire due dates for Task TBD-1.
Agreement Term: M-D-YYYY to M-D-YYYY
Within this Scope of Work, "days" means business days.
Changes to due dates must be approved in writing by the CAM, and may require approval by the CEC's Executive Director or his/her designee.
Task/ Subtask # | Task/Subtask Name | Meeting Name | Product(s) | Due Date
1 | General Project Tasks
1.1 | Products
1.2 | Kick-off Meeting | Kick-off Meeting |  | [CAM to insert date]
|  |  | Kick-off Meeting Presentation | 5 days prior to Kick-off Meeting
|  |  | Updated Project Schedule (if applicable) | 5 days after determination of the need to update the documents
Match Funds Status Letter (subtask 1.7) (if applicable)
Permit Status Letter (subtask 1.8) (if applicable)
CAM Product
|  |  | Kick-off Meeting Agenda | 7 days prior to the kick-off meeting
1.3 | CPR Meeting | CPR Meeting #1 |  | [CAM to insert date]
|  | CPR Meeting #2 |  | [Same as above]
|  |  | CPR Report(s) | 15 days prior to the CPR meeting
CAM Products
|  |  | CPR Agenda | 5 days prior to the CPR meeting
|  |  | Progress Determination | As indicated in the Schedule for Providing a Progress Determination
1.4 | Final Meeting | Final Meeting |  | [CAM to insert date. Must be the last scheduled date, no later than 60 days prior to the agreement end date; REDUCE SIZE OF ROW after inserting date]
|  |  | Final Meeting Agreement Summary (if applicable) | 7 days after the final meeting
|  |  | Schedule for Completing Agreement Closeout Activities | 7 days after the final meeting
|  |  | All Final Products | 7 days after the final meeting
1.5 | Progress Reports and Invoices |  | Progress Reports | 10 days after the first of each month
|  |  | Invoices | 10 days after the first of each month or quarter
1.6 | Final Report
1.6.1 | Final Report Outline |  | Draft Final Report Outline | [Insert date that is at least 9 months prior to the end of the Agreement term]
|  |  | Final Report Outline | As determined by the CAM
CAM Product (s)
|  |  | Energy Commission Style Manual | At least 2 months prior to the final report outline due date
|  |  | Comments on Draft Final Report Outline | 10 days after receipt of the Draft Final Report Outline
|  |  | Approval of Final Report Outline | 10 days after receipt of the Final Report Outline
1.6.2 | Final Report |  | Summary of TAC Comments on Draft Final Report
|  |  | Draft Final Report | [Insert date that is at least 7 months prior to the end of the Agreement term]
Written Responses to Comments (if applicable)
|  |  | Final Report | [Insert date that is at least 5 months prior to the end of the Agreement term]
CAM Products
|  |  | Written Comments on Draft Final Report | 15 days after receipt of the Draft Final Report
1.7 | Match Funds |  | Match Funds Status Letter | 2 days prior to the kick-off meeting
|  |  | Supplemental Match Funds Notification Letter (if applicable) | 10 days after receipt of additional match funds
|  |  | Match Funds Reduction Notification Letter (if applicable) | 10 days after any reduction of match funds
1.8 | Permits |  | Permit Status Letter | 2 days prior to the kick-off meeting
|  |  | Updated List of Permits (if applicable) | 10 days after determination of the need for a new permit
|  |  | Updated Schedule for Acquiring Permits (if applicable) | 10 days after determination of the need for a new permit
|  |  | Copy of Each Approved Permit (if applicable) | 7 days after receipt of each permit
1.9 | Subcontracts |  | Draft Subcontracts (if required by the CAM) | As determined by the CAM
|  |  | Final Subcontracts | As determined by the CAM
1.1 | Technical Advisory Committee (TAC) |  | List of Potential TAC Members | 2 days prior to the kick-off meeting
|  |  | List of TAC Members | 7 days after finalization of the TAC
|  |  | Documentation of TAC Member Commitment | 7 days after receipt of the documentation
1.11 | TAC Meetings | TAC Meeting #1 |  | [CAM to insert date]
|  | TAC Meeting #2 |  | [Same as above]
|  |  | Draft TAC Meeting Schedule | 20 days after the kickoff meeting
|  |  | Final TAC Meeting Schedule | 10 days after the first TAC meeting
|  |  | Draft TAC Meeting Agendas | 20 days prior to each TAC meeting
|  |  | TAC Meeting Back-up Materials | 20 days prior to each TAC meeting
|  |  | Final TAC Meeting Agenda | 7 days prior to each TAC meeting
|  |  | TAC Meeting Summaries | 10 days after each TAC meeting
1.12 | Project Performance Metrics |  | TAC Performance Metrics Summary | 10 days after first TAC meeting
|  |  | Project Performance Metrics Results | Same date as the Draft Final Report due date
Technical Tasks
2 | [Insert task name] |  | [Insert product name] | [Same as above]
|  |  | [Insert product name] | [Same as above]
|  |  | [Insert product name] | [Same as above]
3 | [Insert task name] |  | [Insert product name] | [Same as above]
|  |  | [Insert product name] | [Same as above]
|  |  | [Insert product name] | [Same as above]
[TBD-1] | Evaluation of Project Benefits |  | Initial Project Benefits Questionnaire | 30 days after the kick-off meeting
|  |  | Annual Survey(s) | January 31st of each agreement year
|  |  | Final Project Benefits Questionnaire | Same date as the Draft Final Report due date
|  |  | Documentation of Project Profile on EnergizeInnovation.fund | 30 days after the Kick-off Meeting
|  |  | Documentation of Organization Profile on EnergizeInnovation.fund | 30 days after the Kick-off Meeting
[TBD-2] | Technology/Knowledge Transfer Activities |  | Draft Technology Transfer Plan | 30 days prior to TAC Meeting #1
|  |  | Final Technology Transfer Plan | 30 days after TAC Meeting #1
|  |  | Summary of TAC Comments | 30 days after TAC Meeting #1
|  |  | Draft Technology Transfer Summary Report | Same date as the Draft Final Report due date
|  |  | Final Technology Transfer Summary Report | 30 days after the Draft Technology Transfer Summary Report due date
|  |  | High Quality Digital Photographs | Same date as the Draft Final Report due date