## Schedule Instructions
I. | Instructions for Schedule of Products and Due Dates
This workbook contains the spreadsheet for the Schedule of Products and Due Dates. Items in <blue type> need to be completed. All other items should remain unchanged.
For each Administrative Task, insert the planned start and completion dates. For the Critical Project Reviews (CPRs), add as many CPRs as the project requires. If this form is being completed by an Applicant as part of a proposal to the Energy Commission, leave the CPR sections blank. These sections will be completed by the Energy Commission prior to issuing a funding award.
For each Technical Task, insert the name of each task as it is titled in the Scope of Work, the name of each product(s) associated with each task as they are titled in the Scope of Work (using Caps and Bold), and the planned completion dates. Delete or insert rows as necessary.

## Schedule of Products
Schedule of Products and Due Dates
Task Number | Task Name | Product(s) | Due Date | PIER Funds | Match Funds
1.1 | Attend Kick-off Meeting
|  | Updated Schedule of Products | <Insert Date>
|  | Updated List of Match Funds | <Insert Date>
|  | Updated List of Permits | <Insert Date>
|  | Written Statement of Match Share Activities | <Insert Date>
|  | Kick-Off Meeting Agenda (CEC) | <Insert Date>
1.2 | Critical Project Review Meetings
| 1st CPR Meeting | CPR Report | <Insert Date>
|  | CPR Meeting Agenda (CEC) | <Insert Date>
|  | Schedule for written determination (CEC) | <Insert Date>
|  | Written determination (CEC) | <Insert Date>
<Add as many CPRs as required> |  | <Utilize same products as 1st CPR Meeting> | <Insert Date>
|  | <Utilize same products as 1st CPR Meeting> | <Insert Date>
1.3 | Final Meeting
|  | Written documentation of meeting agreements | <Insert Date>
|  | Schedule for completing closeout activities | <Insert Date>
1.4 | Monthly Calls
|  | Email to CAM concurring with call summary notes | Within 5 days of receipt
1.5 | Quarterly Progress Reports
|  | Quarterly Progress Reports | 10th calendar day of each January, April, July, and October during the approved term of this Agreement
1.6 | Final Report
|  | Final Outline of the Final Report | <Insert Date>
|  | Draft Final Report | <Insert Date> | 0 | 0
|  | Final Report (no less than 60 days before the end term of the agreement) | <Insert Date>
1.7 | Identify and Obtain Match Funds
|  | A letter regarding match funds or stating that no match funds are provided | <Insert Date> | 0 | 0
|  | Copy(ies) of each match fund commitment letter(s) (if applicable) | <Insert Date>
|  | Letter(s) for new match funds (if applicable) | Within 10 days of identifying new match funds | 0 | 0
|  | Letter that match funds were reduced (if applicable) | Within 10 days of identifying reduced funds | 0 | 0
1.8 | Identify and Obtain Required Permits |  |  | 0 | 0
|  | Letter documenting the permits or stating that no permits are required | <Insert Date>
|  | A copy of each approved permit (if applicable) | Within 10 days of receiving each permit | 0 | 0
|  | Updated list of permits as they change during the term of the Agreement (if applicable) | Within 10 days of change in list of permits
|  | Updated schedule for acquiring permits as changes occur during the term of the Agreement (if applicable) | Within 10 days of change in schedule for obtaining permits
|  | A copy of each final approved permit (if applicable) | Within 10 days of receiving each permit
1.9 | Obtain and Execute Subawards
|  | Letter describing the subawards needed, or stating that no subawards are required | <Insert Date>
|  | Draft subcontracts (if requested) | 15 days prior to the scheduled execution date
|  | Final subcontracts (if requested) | Within 10 days of execution
2 | Block Grant Internal Controls, Processes and Procedures |  |  | 0 | 0
|  | Written internal controls, processes, and procedures | <Insert Date>
|  | Updated internal controls, processes, and procedures | <Insert Date>
3 | Website Design, Development, Maintenance, and Implementation
|  | Website design and content | <Insert Date> | 0 | 0
4 | Overall Project Plan Development
|  | Overall Project Plan | <Insert Date>
|  | Updated Overall Project Plan | <Insert Date>
5 | Incentive Project Development |  |  | 0 | 0
|  | Incentive Project Recommendations(s) | <Insert Date>
|  | Incentive Project Designs | <Insert Date> | 0 | 0
Incentive Project Plan
|  | Updated Incentive Project Plan | <Insert Date>
6 | Incentive Project Implementation
|  | Application documents for individual incentive project(s) | <Insert Date>
|  | Implementation Manual for individual incentive project(s) | <Insert Date>
|  | Outreach matrerials for individual incentive project(s) | <Insert Date>
|  | Incentive project records, including, but not limited to financial records, incentive payment documentation (e.g., completed incentive request forms, photographs of installed chargers, and other appropriate documentation to confirm compliance with project requirements), problems/issues experienced, and how identified problems/issues were resolved. | Upon CAM Request
|  | Submit an AB 841 Certification that certifies the project has complied with all AB 841 (2020) requirements specified in Exhibit C or describes why the AB 841 requirements do not apply to the project. The certification shall be signed by Recipient’s authorized representative. | <Insert Date>
|  | Submit EVITP Certification Numbers of each Electric Vehicle Infrastructure Training Program certified electrician that installed electric vehicle charging infrastructure or equipment. EVITP Certification Numbers are not required to be submitted if AB 841 requirements do not apply to the project. | <Insert Date>
7 | Operations and Reliability
7.2 | Recordkeeping
|  | Remote Monitoring Records | <Insert Date>
|  | Maintenance Records | <Insert Date>
|  | Data Dictionary | <Insert Date>
7.3 | Maintenance Requirements
|  | Maintenance section | Included in Quarterly Progress Report, Task 1.5
7.4 | Reporting
|  | Quarterly Report on Charger Reliability and Maintenance | Included in Quarterly Progress Report, Task 1.5
8 | Semi-Annual Electric Vehicle Charger Inventory Reports
|  | Electric Vehicle Charger Inventory Report | Within 30 calendar days of execution and then the end of each July and end of each January thereafter during the term of the agreement.
9 | Data Collection & Analysis
|  | Data Collection Plan | <Insert Date>
|  | Data Collection and Information Analysis Report | <Insert Date>
|  | User Survey Report | <Insert Date>
|  | Process Improvement Recommendation(s) | <Insert Date>
10 | Project Fact Sheet
|  | Initial Project Fact Sheet | <Insert Date>
|  | Final Project Fact Sheet | <Insert Date>
|  | High Quality Digital Photographs | <Insert Date>
<Etc.> | <Insert Task Name>
|  | <Insert 1st Product Name> | <Insert Date>
|  | <Insert 2nd Product Name> | <Insert Date>
|  | <etc. Add/delete rows as necessary> | <Insert Date>