|  |
| --- |
| **2022 STANDARDS UPDATE SCHEDULE** (9-1-2020) |
| **Current Schedule** | **ACTIVITY OR MILESTONE** |
| November 2018 –November 2019 | Updated Weather Data Files |
| November 2018 –December 2019 | Metric Development |
| November 2018 - July 2019 | Measures Identified and Approved |
| April 24, 2019 | Present the Efficiency Measure Proposal Template for public to submit measures |
| October 17, 2019 | Compliance Metrics and Climate Data workshop |
| August 2019 - November 2019 | First Round of Utility-Sponsored Stakeholder Workshops |
| January 2020 | Research Version of CBECC Available with new weather data files and updated Metric |
| February 2020 -April 2020 | Second Round of Utility-Sponsored Stakeholder Workshops |
| March 10, 2020 | Staff Workshop on the proposed changes for the ATTCP program  |
| March 26, 2020 | Staff Workshop on the EDR1  |
| March 2020 -April 2020 | All Initial CASE/PUBLIC Reports Submitted to Commission |
| July 2020 – August 2020 | All Final CASE/PUBLIC Reports Submitted to the Commission |
| September 2020 -October 2020 | Commission Staff Workshops |
| September 2020– November 2020  | Express Terms Developed (including ADA and New MF Section) |
| November 2020 – December 2020 | Commission Staff Reports |
| January 2021 | Internal Review of Express Terms Package by ED, EO, Com (1 month) |
| February 2021 | OAL Publishes Notice, Initial Study and Negative Declaration review/comment period starts |
| February 2021 | OAL Published Notice, 45-day Language posted and set to list serve, Start of 45-day review/comment period |
| March 2021 | Lead Commissioner Hearing |
| April 2021 | End of 45-day review/comment period |
| May 2021 | Staff reviews comments and drafts 15-day Language |
| June 2021 | Notice 15-day language published, Start of 15-day review/comment period |
| July 2021 | Adoption of 2022 Standards at Business Meeting |
| September 2021 | Final Statement of Reasons Drafted and Approved |
| July 2021 | Adoption CALGreen (energy provisions) - Business Meeting |
| December 2021 | Approval of the Manuals |
| October 2021 | Final Rulemaking Package delivered to CBSC |
| December 2021 | CBSC Approval Hearing  |
| January 2022 | Software, Compliance Manuals, Electronic Documents Available to Industry |
| January 1, 2023 | **Effective Date** |