## Grant Approval Chart
|  | Division/Program |  |  |  | Admin/CGL
Line # | Type of Change | CAM | CAM's Supervisor | Manager | Director Or Designee | CAO | CGL Office Manager | Attorney | Executive Director | Business Meeting | Documentation of Change | Authority
1 | Address: Changes of Recipient (as opposed to project site) (in state to in state) | X |  |  |  | X |  |  |  |  | Email Notification | Authority: None needed
2 | Address: Changes of Recipient (as opposed to project site) (out of state to in state) | X |  |  |  | X |  |  |  |  | Email Notification | Authority: None needed
3 | Address: Changes of Recipient (as opposed to project site) (out of state to out of state) | X |  |  |  | X |  |  |  |  | Email Notification | Authority: None needed
4 | Address: Changes of Recipient (as opposed to project site) (in state to out of state) | X | X | X | X | X |  | add attorney if out of country |  |  | Email Approval | Authority: Order and Resolution*
5 | Budget: Increase in Match share | X |  |  |  | Copy to CGL for grant file*** |  |  |  |  | Email Notification | Authority: None needed
6 | Budget: Decrease in Match share | X | X | X | X | X | X |  |  |  | Grant Amendment (CEC-140) and revised budget | Authority: Order and Resolution*
7 | Budget: Match Reallocation (any amount)† | X | X |  |  | Copy to CGL for grant file*** |  |  |  |  | Email Approval | Authority: Order and Resolution*
8 | Budget: CEC fund Reallocations within a category† | X |  |  |  | Copy to CGL for grant file*** |  |  |  |  | Email Notification | Authority: Order and Resolution*
9 | Budget: CEC fund Cumulative Budget Reallocation under $150K† | X | X |  |  | Copy to CGL for grant file*** |  |  |  |  | Email Approval | Authority: Order and Resolution*
10 | Budget: CEC fund Cumulative Budget Reallocation $150K - $300K† | X | X | X |  | Copy to CGL for grant file*** |  |  |  |  | Email Approval | Authority: Order and Resolution*
11 | Budget: CEC fund Cumulative Budget Reallocation over $300K† (After $300k+ review, cumulative resets to $0) | X | X | X | X | Copy to CGL for grant file*** |  |  |  |  | Email Approval | Authority: Order and Resolution*
12 | Budget: Decrease in funding before final invoice (no scope change) | X | X | X | X | X | X |  |  |  | Grant Amendment (CEC-140) and revised budget | Authority: Order and Resolution*
13 | Budget: Agreement Funding Augmentation (ARFVTP total agreement under $75,000) | X | X | X | X | X | X | X | X |  | Grant Amendment (CEC-140) and revised budget | Authority: Energy Commission Order No. 12-0711-6
14 | Budget: Agreement Funding Augmentation (all other) | X | X | X | X | X | X | X | X | X | Grant Amendment (CEC-140) and revised budget | Authority: Business Meeting
15 | Confidential: designate product/deliverable as Confidential | X | X | X | X | X | X | X | X |  | Grant Amendment (CEC-140) and revised confidential products list (Exhibit C - Attachment 1) | Authority: Order and Resolution*. Regulation**
16 | Contact List: Changes to any contact information | X |  |  |  | X |  |  |  |  | Email Approval | Authority: Order and Resolution*
17 | Equipment: Disposition of Equipment | X | X | X | X | Copy to CGL for grant file*** |  |  |  |  | Letter from Division | Authority: Order and Resolution*
18 | Fixing Clerical Mistakes: Both parties agreed to one thing but accidentally included something else. | X | X |  |  | X |  | X |  |  | Email Approval | Authority: Order and Resolution*
19 | Intellectual Property (IP): Add pre-existing IP | X | X |  |  | Copy to CGL for grant file*** |  | X |  |  | Email Approval | Authority: Order and Resolution*
20 | New Agreement | X | X | X | X | X | X | X | X | X | Grant Agreement (CEC-146) and documents listed on the CEC-146 | Authority: Business Meeting
21 | New Agreement (ARFVTP $75,000 and under) | X | X | X | X | X | X | X | X |  | Grant Agreement (CEC-146) and documents listed on the CEC-146 | Authority: Energy Commission Order No. 12-0711-6
22 | Permits: Additional Permits | X |  |  |  | Copy to CGL for grant file*** |  |  |  |  | Email Notification | Authority: None needed
23 | Prime: Recipient Change (New Recipient. This is a Novation.) | X | X | X | X | X | X | X | X | X | Grant Amendment (CEC-140) and all revised documents originally listed on the CEC-146 | Authority: Business Meeting
24 | Prime: Corporate Structure Change that does not create a new legal entity | X | X | X | X | X | X | X |  |  | Grant Amendment (CEC-140) and documents affected by the change (e.g. SOW, etc.) | Authority: Order and Resolution*
25 | Prime: Name Change Only (no new legal entity) | X | X | X | X | X | X | X |  |  | Grant Amendment (CEC-140) and all revised documents originally listed on the CEC-146 | Authority: Order and Resolution*
26 | Schedule: Schedule changes within term | X |  |  |  | Copy to CGL for grant file*** |  |  |  |  | Email Approval | Authority: Order and Resolution*
27 | Site: Change to site location (When CEQA exempt or not a project under CEQA. No Amendment required to update site location in NOE or SOW.) | X | X |  |  | X |  | X |  |  | Email Approval | Authority: None needed
28 | Site: Change to site location (When CEQA requires more than a notice of exemption) | X | X | X | X | X | X | X | X | X | Grant Amendment (CEC-140) and CEQA related documents | Authority: Business Meeting
29 | SOW: Change to purpose of SOW | X | X | X | X | X | X | X | X | X | Grant Amendment (CEC-140), revised SOW, and project schedule if revised | Authority: Business Meeting
30 | SOW: SOW changes (not to purpose) | X | X | X | X | X | X | X |  |  | Grant Amendment (CEC-140), revised SOW, and project schedule if revised | Authority: Order and Resolution*
31 | Issuing or Lifting a Stop Work Order (SWO) | X | X | X | X | Copy to CGL for grant file*** |  |  | Copy of Letter to EO (Electronic notification 24hrs before issuing or lifting a SWO) |  | Stop Work Order Letter or Lifting Stop Work Order Letter | Authority: Terms and Conditions
32 | Subs/Vendors: Add subrecipient or vendor† | See appropriate budget reallocation category for approval authority (i.e. line # 5 to 14). If sub or vendor is out of country, add Attorney approval. | [9 empty] | Authority: Terms and Conditions, and Order and Resolution*
33 | Subs/Vendors: Removing subrecipient or vendor† | See appropriate budget reallocation category for approval authority (i.e. line # 5 to 14). | [9 empty] | Authority: Order and Resolution*
34 | Subs/Vendors: Subrecipient or vendor name change. (Same entity, not a replacement.)† | X |  |  |  | X |  |  |  |  | Email Approval | Authority: Order and Resolution*
35 | Vendors: Replacing vendor (in state to in state; out of state to in state; out of state to out of state)† | X |  |  |  | Copy to CGL for grant file*** |  | add attorney if out of country |  |  | Email Approval | Authority: Order and Resolution*
36 | Subs: Replacing subrecipient (in state to in state; out of state to in state; out of state to out of state)† | X | X |  |  | Copy to CGL for grant file*** |  | add attorney if out of country |  |  | Email Approval | Authority: Order and Resolution*
37 | Subs/Vendors: Replacing subrecipient or vendor (in state to out of state)† | X | X | X | X | Copy to CGL for grant file*** |  | add attorney if out of country |  |  | Email Approval | Authority: Order and Resolution*
38 | Sub Redesignated as Vendor† | X | X |  |  | Copy to CGL for grant file*** |  |  |  |  | Sub-to-Vendor Form | Authority: Order and Resolution*
39 | Term Extension: Not beyond liquidation date | X | X | X | X | X | X |  |  |  | Grant Amendment (CEC-140) and revised project schedule | Authority: Order and Resolution*
40 | Term Extension: Beyond liquidation date | X | X | X | X | X | X |  | X |  | Grant Amendment (CEC-140) and revised project schedule | Authority: Order and Resolution*
41 | Termination with funds spent | X | X | X | X | X | X | X | X | X | Termination Letter (from CEC) | Authority: Business Meeting.
42 | Termination without funds spent (after the agreement is executed) | X | X | X | X | X | X |  |  |  | Termination Letter (from CEC) | Authority: Order and Resolution*
43 | Cancellation prior to the agreement being executed | X | X | X | X | X |  |  |  |  | Cancellation Letter (from CEC) | Authority: Order and Resolution*
44 | Terms and Conditions change that affects CEC rights/liability and is NOT made to improve the administrative efficiency and flexibility of the agreement (e.g., changes made by ECAMS effort.) | X | X | X | X | X | X | X | X | X | Grant Amendment (CEC-140) and revised Terms and Conditions | Authority: Business Meeting
45 | Terms and Conditions change that doesn't affect CEC rights/liability, or that does affect the CEC rights/liability but is made to improve the administrative efficiency and flexibility of the agreement (e.g., changes made by ECAMS effort.) | X | X | X | X | X | X | X |  |  | Grant Amendment (CEC-140) and revised Terms and Conditions | Authority: Order and Resolution*
46 | Travel: New Travel not on the Budget Worksheet (in-state)† | X | [8 empty] | Travel Form | Authority: Order and Resolution*
47 | Travel: New Travel not on the Budget Worksheet (out-of-state)† | X | X | [7 empty] | Travel Form | Authority: Order and Resolution*
48 | Travel: New Travel not on the Budget Worksheet (out-of-country)† | X | X | X | [6 empty] | Travel Form | Authority: Order and Resolution*
49 | Travel: New Travel not on the pre-approved travel list (out-of-state to a banned state)† | X | X | X | [6 empty] | Travel Form | Authority: Order and Resolution*
AGREEMENT DEVELOPMENT/AMENDMENT CHANGES MADE POST-BUSINESS MEETING APPROVAL, PRE-AGREEMENT/AMENDMENT EXECUTION
A.1 | Non-substantive Changes to Agreement Documents and Backup Materials: Non-substantive changes include, but are not limited to, minor "not to purpose" changes to the SOW, or pushing out the agreement end date.‡ | X | X |  |  | X |  | X |  |  | CEC internal approval process (Agreement end date changes will require Budget Office verification) | Authority: Order and Resolution*
A.2 | Substantive Changes to Agreement Documents and Backup Materials: See definition below.‡ | See appropriate line item for documentation of change and approval authority
*Authority: Energy Commission Order No. 12-0711-6 (ARFVTP agreements only) and Resolution No. 20-0812-1a (all agreements) authority to Executive Director or designee.
**Authority: Title 20 California Code of Regulations (CCR) Section 2505(c)(2)(B) (all agreements) authority to Executive Director or designee.
***Instructions for sending copies to CGL for grant file: Please email approvals to CGLfiles@energy.ca.gov
† Applies to Recipients and Major Subrecipients
‡ Substantive changes are signification and important changes that require the buy-in of all approvers for the line item within this chart that is applicable to the change in question. Substantive changes may include, but are not limited to, the following: [1] decrease in match share, [2] budget reallocation between budget categories at $150K or more, [3] decrease in total funding amount (no scope change), [4] increase in total funding amount, [5] designating a deliverable as confidential, [6] recipient change, [7] recipient corporate structure change, [8] change to site location (when CEQA requires more than a notice of exemption), [9] change to purpose of Scope of Work (SOW), [10] replacing subrecipient or vendor (in state to out of state), [11] pushing out the agreement end date past the funding liquidation date, [12] cancelling the agreement, [13] revising the agreement's terms and conditions, and [14] new travel (out-of-country or out-of-state to a banned state).