GRANT FUNDING OPPORTUNITY

California’s National Electric Vehicle Infrastructure Formula Program – Solicitation 3

GFO-25-602

Solicitation Information

https://www.energy.ca.gov/funding-opportunities/solicitations

State of California

California Energy Commission

December 2025

##### Table of Contents

I.	Introduction	5

A.	Purpose of Solicitation	5

B.	Background	5

C.	Key Activities and Dates	6

D.	How Award Is Determined	6

E.	Availability of Funds	7

F.	Applicant Award Cap	8

G.	Maximum Number of Applications	8

H.	Multiple EV Charging Stations Per Application	8

I.	Agreements Contingent on Funding Availability	9

J.	Pre-Application Workshop	10

K.	Participation Through Zoom	10

L.	Questions	11

M.	Contact Information	11

N.	Reference Documents	12

II.	Eligibility Requirements	14

A.	Applicant Requirements	14

B.	Project Requirements	16

C.	Match Funding Requirements	38

D.	Unallowable Costs (Reimbursable or Match Share)	40

III.	Application Format, Required Documents, and Delivery	42

A.	Required Format for an Application	42

B.	Method for Delivery	42

C.	Solicitation Informational Documents	43

D.	Application Content	43

IV.	Evaluation Process and Criteria	59

A.	Application Evaluation	59

B.	Notice of Proposed Awards	62

C.	Debriefings	62

D.	Scoring Scale	62

E.	Technical Evaluation Criteria	64

F.	Cost Evaluation	67

G.	Tie Breakers	69

V.	Administration	70

A.	Definition of Key Words	70

B.	Cost of Developing Application	75

C.	Confidential Information	75

D.	Solicitation Cancellation and Amendments	75

E.	Errors	75

F.	Modifying or Recalling an Application	76

G.	Immaterial Defect	76

H.	Opportunity to Cure Administrative Errors	76

I.	Disposition of Applicant’s Documents	77

J.	Applicants’ Admonishment	78

K.	Agreement Requirements	78

L.	No Agreement Until Signed and Approved	79

M.	Executive Order N-6-22 – Russia Sanctions	79

##### Attachments

1 – Project Narrative

1B – Station Information

2 – Schedule of Products and Due Dates

3 – Proposal Budget

4 – Letters of Commitment

5 – Preliminary Site Plan

6 – California Environmental Quality Act (CEQA) Worksheet

7 – National Environmental Policy Act (NEPA) Preliminary Environmental Study (PES) Form

8 – Utility Verification Form

9 – Resumes

10 – Contact List

11 – Past Performance Reference Form

12 – Applicant Declaration

13 – Letters of Support (optional)

14 – Scope of Work (informational only)

15 – Right of Way Certification Form 13B (NEVI) (informational only)

# I.	Introduction

## Purpose of Solicitation

This is a competitive grant solicitation. The California Energy Commission (CEC) announces the availability of up to $79,000,000 in grant funds for projects that will strategically deploy electric vehicle (EV) charging stations with publicly accessible, high-powered, direct current fast chargers (DCFCs) to support light-duty EV travel along major corridors as required under the National Electric Vehicle Infrastructure (NEVI) formula program.

Submitted projects should be for installation and operation of DCFCs, using commercially available technology, within a previously disturbed or developed area such that the projects will qualify for the National Environmental Policy Act (NEPA) categorical exclusion for electric vehicle charging stations codified in the Code of Federal Regulations, Title 10, Chapter X, Part 1021, Appendix B, Categorical Exclusion B5.23, as explained in the Federal Register notice of the U.S. Department of Transportation’s adoption of the electric vehicle charging stations categorical exclusion (see https://www.federalregister.gov/documents/2023/09/20/2023-20238/notice-of-adoption-of-electric-vehicle-charging-stations-categorical-exclusion-under-the-national).

## Background

The Infrastructure Investment and Jobs Act (IIJA) (Public Law 117-58) authorizes hundreds of billions of dollars in new investments in a wide array of infrastructure categories, including roads and bridges, water infrastructure, passenger rail, energy, and broadband internet. The IIJA includes $5 billion to accelerate EV infrastructure deployment nationally under the NEVI formula program. California’s share is expected to be $384 million, allocated over 5 years.

NEVI is an initiative to create a coast-to-coast network of EV chargers focused on major highways that support the majority of long-distance trips. This national network will give drivers confidence that they can always find a place to charge, and jump start private investment in charging infrastructure.

The CEC is collaborating with the California Department of Transportation (Caltrans) on charging infrastructure deployment under an interagency agreement in which the CEC is charged with implementing and administering California’s NEVI formula program.

The CEC and Caltrans prepare NEVI deployment plans as required by the NEVI formula program. The most recent California NEVI Plan is found at https://dot.ca.gov/-/media/dot-media/programs/sustainability/documents/transportation-electrification/nevi/2025-ca-nevi-plan-update-a11y.pdf. Information about the state’s implementation of the NEVI program is found at https://www.energy.ca.gov/programs-and-topics/programs/federal-ev-infrastructure-programs.

## Key Activities and Dates

Key activities including dates and times for this solicitation are presented below.  An addendum will be released if the dates change for the asterisked (*) activities. Times listed are Pacific Standard Time or Pacific Daylight Time, whichever is being observed.

| ACTIVITY | ACTION DATE |
| --- | --- |
| Solicitation Release | December 29, 2025 |
| Pre-Application Workshop* | January 14, 2026 |
| Deadline for Written Questions* | January 22, 2026 |
| Anticipated Distribution of Questions/Answers | Week of February 9, 2026 |
| Support for Application Submission in the Energy Commission Agreement Management System (ECAMS) until 5:00 p.m. | Ongoing until March 25, 2026 |
| Deadline to Submit Applications by 11:59 p.m.* | March 25, 2026 |
| Anticipated Notice of Proposed Awards Posting | Week of June 1, 2026 |
| Anticipated CEC Business Meeting | August 2026 |

## How Award Is Determined

Awards will be determined according to the following steps:

- Applications must pass screening

Applications must first pass the administrative screening and technical screening discussed in Section IV.A.1-4. Applicants that pass these screenings will proceed to Technical Evaluation, discussed in Section IV.A.6.

- EV charging stations must achieve at least the minimum scores required in Technical Evaluation

The technical evaluation will evaluate each charging station separately.

Each proposed EV charging station in an application that passes screening will be evaluated separately using the scoring scale shown in Section IV.D. to score each EV charging station based on the Technical Evaluation Criteria listed in Section IV.E. A minimum score of 70 percent overall is required for the charging station to be eligible for funding. Each station must additionally receive a minimum score of 70 percent on both Technical Evaluation Criterion 2, Project Readiness, and Technical Evaluation Criterion 4, Project Budget and Finances, to be eligible for funding.

- EV charging stations will be ranked based on Cost Evaluation

EV charging stations that pass screening and receive a score of 70 percent or higher for IV.E Technical Evaluation (overall and for Technical Evaluation Criterion 2 and 4) will advance to Cost Evaluation, discussed in Section IV.A.7. and Section IV.F., wherein the cost efficiency metric of Cost-per-CCS-Port will be calculated for each charging station. Unless the CEC exercises any of its other rights regarding this solicitation (e.g., to cancel the solicitation or reduce funding), each application’s proposed charging station(s) will be ranked according to their Cost-per-CCS-Port against the other proposed stations in the same “Needed Location” of a “Corridor Segment” (terms defined in Section II.B. and listed in Section V.A.). The station obtaining the lowest Cost-per-CCS-Port score for each Needed Location will be recommended for funding.

- Additional awards if funding is still available

The CEC reserves the right to recommend funding additional stations for a Needed Location after all Needed Locations with eligible EV charging stations have one station proposed for funding. The stations within the second-lowest Cost-per-CCS-Port in their respective Needed Location will be awarded in order of lowest Cost-per-CCS-Port to highest. For example, if the second-lowest Cost-per-CCS-Port for one Needed Location is $70,000 and the second-lowest for another Needed Location is $80,000, the station with the $70,000 Cost-per-CCS-Port will be proposed for award first. Awarding of second-ranked stations will continue according to this process until the CEC determines, at its sole discretion, that there is sufficient station coverage or funding is exhausted, whichever comes first. If funding remains after all second-ranked stations for the Needed Locations have been awarded, the same process may continue for third-ranked stations, and so on.

If the funds available under this solicitation are insufficient to fully fund an EV charging station proposed for award, CEC reserves the right to recommend partially funding that charging station. In this event, the proposed Applicant/Awardee and Commission Agreement Manager (CAM) shall meet and attempt to reach agreement on a reduced scope of work commensurate with the level of available funding.

## Availability of Funds

A total of $79,000,000 is available for awards under this solicitation. The CEC, at its sole discretion, reserves the right to increase or decrease the amount of funds available under this solicitation.

## Applicant Award Cap

Any one Applicant may receive no greater than 20 percent of the total funds available under this solicitation. If an Applicant requests more than 20 percent of the funds available, the CEC intends to propose awards to the Applicant using the Cost Evaluation score (the Cost-per-CCS-Port) for each station in the application. In determining which stations to fund, if some of the Applicant’s stations received the same score, the tie breaker criteria listed in Section IV.G. will be used to determine which stations are proposed for award.

If the lowest Cost-per-CCS-Port station for a Needed Location is not eligible because the Applicant has exceeded the applicant award cap, the CEC intends to award the next-lowest cost station for that Needed Location.

The CEC reserves the right, at its sole discretion, to modify or eliminate the applicant award cap.

## Maximum Number of Applications

Applicants are only eligible to submit one (1) application under this solicitation. Each application must contain a minimum of one (1) and a maximum of twenty (20) EV charging stations. Additional information is provided in Section I.H. Multiple EV Charging Stations Per Application, of this manual.

Applicants may also be subrecipients, vendors, or suppliers for other Applicants’ projects, but must ensure they are prepared to complete their designated work if all applications in which they have a role are awarded.

Each EV charging station within the application will be evaluated, scored, and ranked individually. An Applicant may be awarded funding for some but not all of the EV charging stations proposed in their application. A single grant agreement may provide funding for multiple charging stations.

## Multiple EV Charging Stations Per Application

An application may include proposals for multiple EV charging stations, as described in Section I.G. Maximum Number of Applications, and subject to the applicant award cap (Section I.F). However, each EV charging station within the application will be evaluated, scored, and ranked individually. Proposing multiple stations does not guarantee that all proposed stations will be recommended for funding. Applicants must ensure that the proposed budgets and requested funding amounts are appropriate and separate for each station proposed in the event that one or more stations are not awarded funding.

Applications containing multiple EV charging stations must do the following:

- Clearly delineate between the proposed individual EV charging stations throughout the application by numbering the stations (1, 2, 3, etc.) and identify them as Station 1, Station 2, Station 3, etc.

- Submit one of each of the following attachments per application, while using the station numbering to clearly identify the relevant station number for the information being provided in the Project Narrative and Letters of Support.

  - Project Narrative (Attachment 1)

  - Station Information (Attachment 1B)

  - Resumes (Attachment 9)

  - Contact List (Attachment 10)

  - Past Performance Reference Form (Attachment 11)

  - Applicant Declaration (Attachment 12)

  - Letters of Support (Attachment 13) (optional)

- For each EV charging station proposed in the application, submit a separate and distinct:

- Schedule of Products and Due Dates (Attachment 2)

- Proposal Budget (Attachment 3)

- Letters of Commitment (Attachment 4)

- Preliminary Site Plan (Attachment 5)

- California Environmental Quality Act (CEQA) Worksheet (Attachment 6)

- National Environmental Policy Act (NEPA) Preliminary Environmental Study (PES) Form (Attachment 7)

- Utility Verification Form (Attachment 8)

For example, an application for five (5) EV charging stations shall include five (5) separate Schedules of Products and Due Dates, Proposal Budgets, Letters of Commitment, Preliminary Site Plans, CEQA Worksheets, NEPA PES Forms, and Utility Verification Forms, clearly numbered for each station. The application shall include one (1) attachment for each of the following elements: Project Narrative, Resumes, Contact List, Past Performance Reference Form, Applicant Declaration, and Letters of Support (optional).

## Agreements Contingent on Funding Availability

Without limitation to any other of the CEC’s rights and remedies, if any of the Clean Transportation Program funds used for agreements resulting from this solicitation, or any of the federal funds for the NEVI program, become unavailable; are reduced; or are deleted, for any reason including but not limited to FHWA’s failure to obligate funds, de-obligation of previously obligated funds, or failure to provide sufficient funds to reimburse the State of California for the work identified in agreements’ scopes of work, or for CEC administrative costs to oversee and implement resulting agreements, as the CEC may in its sole discretion determine, without limitation to all other rights and remedies available to it, the CEC shall have the option to either: (1) cancel agreements resulting from this solicitation with no liability occurring to the CEC; or (2) offer agreement amendments to the Recipients to reflect a reduced amount of funds. Should the CEC choose to cancel any resulting agreements, the CEC shall have no liability to pay any funds whatsoever to the agreement Recipients, any subrecipients, and any vendors; nor to furnish any other consideration under the agreements; and the Recipients shall not be obligated to perform any provisions of the agreements.

## Pre-Application Workshop

There will be one Pre-Application Workshop; participation in this meeting is optional but encouraged. The Pre-Application Workshop will be held remotely through Zoom at the date, time and location listed below. Please call the Commission Agreement Officer (CAO) listed below or refer to CEC's solicitation information website at https://www.energy.ca.gov/funding-opportunities/solicitations to confirm the date and time.

January 14, 2026

9:30 a.m. Pacific Standard Time

Via Zoom

## Participation Through Zoom

Zoom is the CEC's online meeting service. When attending remotely, presentations will appear on your computer/laptop/mobile device screen, and audio may be heard via the device or telephone. Please be aware that the Zoom meeting will be recorded.

Zoom Instructions:

To join this workshop, go to Zoom at: https://energy.zoom.us/j/83006497206?pwd=i10YGT272OhvuX17agU1Lyd1PdZpdK.1. You may also access the workshop by going to the Zoom webpage at https://join.zoom.us and enter the unique meeting ID and password below:

Meeting ID: 830 0649 7206

Meeting Password: 521021

Topic: Pre-Application Workshop for California’s NEVI Formula Program Solicitation 3

Telephone Access Only:

Call (888) 853-5257 or (888) 475-4499 (toll-free). When prompted, enter the unique meeting ID number above. To comment over the telephone, dial *9 to “raise your hand” and *6 to mute/unmute your phone line.

Access by Mobile Device:

Download the application from the Zoom Download Center at https://energy.zoom.us/download.

Technical Support:

For assistance with problems or questions about joining or attending the meeting, please call Zoom technical support at (888) 799-9666 ext. 2, or you may contact the CEC’s Public Advisor’s Office at publicadvisor@energy.ca.gov, or (916) 957-7910.

To determine whether your computer is compatible with Zoom, visit

the Zoom support website at https://support.zoom.us/hc/en-us/articles/201362023-System-requirements-for-Windows-macOS-and-Linux.

## Questions

During the solicitation process, for questions only related to submission of applications in ECAMS, please contact ECAMS.SalesforceSupport@energy.ca.gov. By contacting this email address, Applicants will be able to access a team of technical assistants who can answer questions about application submission. Please also see Section III for additional information about ECAMS.

Applicants may ask questions at the Pre-Application Workshop and may submit written questions via e-mail to the CAO listed in the following section. However, all technical questions must be received by the deadline listed in the “Key Activities and Dates” table above. Questions received after the deadline may be answered at the CEC's discretion. Non-technical questions (e.g., questions concerning application format requirements or attachment instructions) may be submitted to the CAO at any time prior to 5:00 p.m. of the application deadline date. Similarly, questions related to submission of applications in ECAMS may be submitted to ECAMS.SalesforceSupport@energy.ca.gov at any time prior to 5:00 p.m. of the application deadline date.

The question-and-answer set will be posted on the CEC’s solicitation information website at www.energy.ca.gov/funding-opportunities/solicitations.

Any verbal communication with a CEC employee concerning this solicitation is not binding on the State and shall in no way alter a specification, term, or condition of the solicitation. All communication must be directed in writing to the CAO assigned to the solicitation.

## Contact Information

Eunice Lemos-Adair, Commission Agreement Officer

California Energy Commission

715 P Street, MS-1

Sacramento, California 95814

Telephone: 1-279-226-1065

E-mail: Eunice.lemos-adair@energy.ca.gov

## Reference Documents

Applicants responding to this solicitation may want to familiarize themselves with the following documents:

- Energy Commission Agreement Management System (ECAMS) https://www.energy.ca.gov/funding-opportunities/funding-resources/ecams-resources.

- California Energy Commission. Federal Electric Vehicle Infrastructure Programs. https://www.energy.ca.gov/programs-and-topics/programs/federal-ev-infrastructure-programs.

- California Energy Commission. California’s National Electric Vehicle Infrastructure Funding Program Map.

https://experience.arcgis.com/experience/135c0da4b70f4717b4664ad2e427d2bc.

- Caltrans. Local Assistance Procedures Manual. https://dot.ca.gov/programs/local-assistance/guidelines-and-procedures/local-assistance-procedures-manual-lapm.

- Caltrans. Local Assistance Guidelines and Procedures.

https://dot.ca.gov/programs/local-assistance/guidelines-and-procedures.

- Caltrans. Right of Way Manual. https://dot.ca.gov/programs/right-of-way/right-of-way-manual.

- National Electric Vehicle Infrastructure Standards and Requirements (23 CFR Part 680)

https://www.federalregister.gov/documents/2023/02/28/2023-03500/national-electric-vehicle-infrastructure-standards-and-requirements.

- U.S. Department of Transportation, Federal Highway Administration. National Electric Vehicle Infrastructure (NEVI) Program. https://www.fhwa.dot.gov/environment/nevi/.

- U.S. Department of Transportation, Federal Highway Administration. National Electric Vehicle Infrastructure (NEVI) Formula Program Guidance. https://www.fhwa.dot.gov/environment/nevi/resources/NEVI-Interim-Final-Program-Guidance-8-11-2025.pdf.

- Caltrans and the California Energy Commission. California's Deployment Plan for the National Electric Vehicle Infrastructure Program - 2025 Annual Update.

https://dot.ca.gov/-/media/dot-media/programs/sustainability/documents/transportation-electrification/nevi/2025-ca-nevi-plan-update-a11y.pdf.

- Joint Office of Energy and Transportation. Technical Assistance

https://driveelectric.gov/technical-assistance/.

- National Archives – Federal Register. Waiver of Buy America Requirements for Electric Vehicle Chargers

https://www.federalregister.gov/documents/2023/02/21/2023-03498/waiver-of-buy-america-requirements-for-electric-vehicle-chargers.

- California Energy Commission. National Electric Vehicle Infrastructure (NEVI) Funding Program, Docket Log 22-EVI-05. https://efiling.energy.ca.gov/Lists/DocketLog.aspx?docketnumber=22-EVI-05.

- Electric Vehicle Infrastructure Training Program

https://evitp.org/.

- California Energy Commission. Electric Vehicle Infrastructure Deployment Assessment – SB 1000.

https://www.energy.ca.gov/programs-and-topics/programs/clean-transportation-program/electric-vehicle-infrastructure

- California Energy Commission. Electric Vehicles Charging Infrastructure Assessment – AB 2127.

https://www.energy.ca.gov/programs-and-topics/programs/electric-vehicle-charging-infrastructure-assessment-ab-2127

- California Air Resources Board. Electric Vehicle Supply Equipment (EVSE) Standards.

https://ww2.arb.ca.gov/our-work/programs/electric-vehicle-supply-equipment-evse-standards.

- California Department of Food and Agriculture, Division of Measurement Standards. Zero-Emission Vehicle Projects. https://www.cdfa.ca.gov/dms/programs/zevfuels/.

- Clean Transportation Program Investment Plans. https://www.energy.ca.gov/programs-and-topics/programs/clean-transportation-program/clean-transportation-program-investment.

# II.	Eligibility Requirements

## Applicant Requirements

- Eligibility

This solicitation is open to all private entities, excluding investor-owned utilities, and is also open to California Tribal Organizations serving California Native American Tribes.

Eligible Applicants must have less than or equal to fifty (50) active projects across all CEC-funded ZEV infrastructure grant agreements, including block grants, at the time of agreement execution. A project is considered “active” if it has been awarded under one of CEC’s grants or block grant programs and construction has not finished on the project; a request for final reimbursement has not been submitted; final reimbursement is pending; or the agreement term has not expired. The CEC reserves the right to modify this requirement.

- Terms and Conditions

Each grant agreement resulting from this solicitation will include terms and conditions that set forth the grant recipient’s rights and responsibilities. By providing the authorizations and certifications required under this solicitation, each Applicant agrees to enter into an agreement, if awarded, with the CEC to conduct the proposed project according to the terms and conditions for this solicitation, the NEVI Standard terms and conditions, found at https://www.energy.ca.gov/sites/default/files/2025-09/NEVI_Standard_Terms_ADA.pdf, the NEVI Special Federal terms and conditions, found at https://www.energy.ca.gov/sites/default/files/2025-09/NEVI_Special_Federal_Terms_ADA.pdf, and, if applicable, the Special Terms and Conditions for California Tribal Organizations with Sovereign Immunity serving California Native American Tribes with Sovereign Immunity, found at https://www.energy.ca.gov/media/12259, without negotiation.

Failure to agree to the terms and conditions by taking actions such as failing to provide the required authorizations and certifications or indicating that acceptance is based on modification of the terms may result in rejection of the application. Applicants must read the terms and conditions carefully. The CEC reserves the right to modify the terms and conditions prior to executing grant agreements.

If a California Tribal Organization (Tribal Organization) with sovereign immunity serving a California Native American Tribe (Tribe) with sovereign immunity is listed as a proposed awardee in the Notice of Proposed Awards (NOPA), before bringing the proposed award to a Business Meeting, CEC staff must receive (a) resolution(s) or other authorizing document(s) by the governing body of the Tribe and/or Tribal Organization (as applicable) which:

    - Authorizes the Tribal Organization to enter into the proposed agreement, including accepting the Special Terms and Conditions for California Tribal Organizations with Sovereign Immunity Serving California Native American Tribes with Sovereign Immunity, including the Limited Waiver of Sovereign Immunity and Consent to Jurisdiction; and

    - Approves a limited waiver of the Tribal Organization’s sovereign immunity, to the extent that any such sovereign immunity exists, for any and all claims by the CEC that may arise relating to this Agreement and any remedies therefore under the laws of the state of California and the laws of the United States of America; and

    - Consents to personal jurisdiction over the Tribal Organization, and consents to venue in any court of the State of California and any federal court sitting in the State of California; and waives any and all claim that the Tribal Organization may have, including without limitation that such court is an inconvenient forum, for the purposes of any proceeding related to this Agreement; and, with respect to a proceeding in a court of the State of California or a federal court sitting in the State of California, any requirement that tribal remedies must be exhausted; and

    - Delegates authority to execute the proposed agreement to an appropriate individual.

The above requirements may be provided in one or more documents. The document(s) will be included as an exhibit to the resulting grant agreement.

Delay in award. Any delay in the Tribe or Tribal Organization’s ability to provide the documentation specified in sections (i)-(iv) above may result in a delayed award of the grant agreement.

Reservation of right to cancel proposed award. Funds available under this solicitation have encumbrance deadlines which the CEC must meet in order to avoid expiration of the funds. In addition to any other rights reserved to it under this solicitation or that it otherwise has, the CEC reserves the right to cancel a proposed award for an EV charging station at any time if it determines, in its sole and absolute discretion, that the documentation described in sections (i)-(iv) above would likely not be provided prior to an encumbrance deadline, and that the CEC’s ability to meet its encumbrance deadline may thereby be jeopardized. In this instance, the CEC may cancel the proposed award for the EV charging station and award funds to the next ranked EV charging station for that Needed Location according to the evaluation process discussed in Section I.D. How Award is Determined.

- California Secretary of State Registration

All corporations, limited liability companies (LLCs), limited partnerships (LPs) and limited liability partnerships (LLPs) that conduct intrastate business in California are required to be registered and in good standing with the California Secretary of State prior to its project being recommended for approval at a CEC Business Meeting. If not currently registered with the California Secretary of State, Applicants and project team members (e.g., subrecipients and even match fund partners) are encouraged to contact the Secretary of State’s Office as soon as possible to avoid potential delays in beginning the proposed project(s) (should the application be proposed for funding).

For more information, contact the Secretary of State’s Office via the Secretary of State Office’s website at www.sos.ca.gov. Sole proprietors using a fictitious business name must be registered with the appropriate county and provide evidence of registration to the CEC prior to their project being recommended for approval at a CEC Business Meeting.

## Project Requirements

Each application must propose to design, install, operate and maintain between one (1) and twenty (20) public EV charging stations, each in a unique Needed Location along a Corridor Segment listed in Table 1. Each Needed Location is a section of a Corridor Segment with two (2) endpoints that are offramps or intersections where a vehicle can exit the corridor. To qualify as a Needed Location, the EV charging station site must be located within one (1) mile as a car drives by the shortest route of the endpoints, or within one (1) mile as a car drives by the shortest route from any offramp or intersection between the specified endpoints.

The proposed stations in an application can be for Needed Locations in one or more Corridor Segments. It is not necessary to propose stations in all Needed Locations for one Corridor Segment – the CEC expects to combine stations proposed in different applications to achieve build-out of each Corridor Segment. An Applicant may submit only one (1) application as explained in Section I.G.

The California’s National Electric Vehicle Infrastructure Funding Program Map at https://experience.arcgis.com/experience/135c0da4b70f4717b4664ad2e427d2bc is available to view the state’s Corridor Segments and Corridor Groups. The CEC has divided the federally-designated Alternative Fuel Corridors (AFCs) into twenty-three (23) Corridor Groups for the purpose of making NEVI formula funding available via grant funding opportunities (GFOs) like this one. The Corridor Groups are further divided into Corridor Segments, which are labeled A, B, C, etc. The Needed Locations are shorter sections within each Corridor Segment that are labeled i, ii, iii, etc.

EV charging equipment that receives incentive funding from another CEC grant funding opportunity (GFO) or block grant incentive project is not eligible for funding under this GFO.

Table 1: Project Corridor Segments

| Corridor Group | Corridor Segment | Description | Needed Locations |
| --- | --- | --- | --- |
| 1 | A | I-5: Sacramento to Oregon | - Exit 522 (I-80, Sacramento) to Exit 540 (West Street, Woodland) - Exit 556 (Rd 6, Dunnigan) to Exit 578 (SR 20, Williams) - Exit 586 (Maxwell Colusa Rd, Maxwell) to Exit 603 (Biggs-Willows Rd, Willows) - Exit 619 (Newville Rd, Orland) to Exit 633 (Finnell Ave, Corning) - Exit 642 (Flores Ave, Red Bluff) to Exit 653 (Jellys Ferry Rd, Red Bluff) - Exit 662 (Bowman Rd, Cottonwood) to Exit 668 (North St, Anderson) - Exit 680 (SR 299, Redding) to Exit 690 (Bridge Bay Rd, Redding) - Exit 728 (Railroad Park Dr, Dunsmuir) to Exit 740 (N Mt. Shasta Blvd, Mt. Shasta) - Exit 770 (Killgore Hills Rd, Yreka) to Exit 776 (Montague Rd, Yreka) |
| 1 | C | SR 99: Red Bluff (I-5) to Sacramento (I-5) SR 32: Orland (I-5) to Chico (SR 99) | - SR 99: Bogue Rd (Yuba City) to Eager Rd (Yuba City) - SR 99: Exit 383 (Park Ave/Skyway, Chico) to Garner Ln (Chico) or SR 32: Canal St (Hamilton City) to SR 99 (Chico) |
| 1 | D | SR 65: Roseville (I-80) to Olivehurst (SR 70) SR 70/149: SR 70/SR 99 junction south of Plumas Lake (SR 99) to SR 149/SR 99 near Durham | - SR 65: I-80 (Roseville) to SR 70 (Olivehurst) - SR 70: Exit 9 (Feather River Blvd, Plumas Lake) to E 24th St (Marysville) - SR 70: Georgia Pacific Way (Oroville) to Exit 49 (Garden Dr, Oroville) |
| 1 | E | SR 44: Redding (I-5) to Susanville (SR 36) | - I-5 (Redding) to Old 44 Dr/Millville Plains Rd (Millville) - Wilson Hill Rd (Shingletown) to SR 89 (Old Station) |
| 2 | A | US 101: North of Leggett to Oregon | - SR 271/Valley Rd (Cooks Valley) to Exit 656 (SR 254, Myers Flat) - Exit 679 (Scotia) to Exit 689 (Main St, Fortuna) - Exit 702 (Herrick Ave, Eureka) to Exit 722 (Airport Rd, McKinleyville/Arcata Airport) - Lundblade St (Orick) to Wilson Creek Rd/DeMartin Beach Picnic Area (Klamath) - Humboldt Rd (Crescent City) to Oregon border |
| 2 | C | SR 299: Arcata (US 101) to Redding | - Exit 1 (Giuntoli Ln, Arcata) to Exit 5 (Blue Lake Blvd, Blue Lake) - Trinity River Hwy/SR 96 (Willow Creek) to Denny Rd (Trinity Village) - Rose Rd (Big Bar) to Steel Bridge Rd (Douglas City) - Iron Mountain Rd (Redding) to S Market St (Redding) |
| 3 | A | SR 1: North of San Francisco (US 101) to Leggett (US 101) | - US 101 (Mill Valley) to Calle del Arroyo (Stinson Beach) - Sir Francis Drake Blvd (Olema) to 2nd St (Tomales) - Bodega Hwy (Bodega) to Burke Ave (Jenner) - Skaggs Springs Rd (Stewarts Point) to Fish Rock Rd (Gualala) - Iverson Ave (Point Arena) to Crispin Rd (Manchester) - Albion Ridge Rd (Albion) to Caspar Frontage Rd W/Fern Creek Rd (Caspar) - Simpson Ln (Fort Bragg) to Mill Creek Dr (Fort Bragg) - Pacific Ave (Westport) to US 101 (Leggett) |
| 3 | B | US 101: San Francisco to Leggett (SR 1) | - Exit 442 (Alexander Ave, Sausalito) to Exit 463 (Atherton Ave/San Marin Dr, Novato) - Exit 472B (SR 116, Petaluma) to Exit 498 (Old Redwood Hwy/Windsor River Rd, Santa Rosa) - Exit 503 (Central Healdsburg) to Exit 522 (SR 128, Cloverdale) - SR 175 (Hopland) to Exit 557 (West Rd, Redwood Valley) - Exit 568 (SR 20, Willits) to Exit 573 (N Main St, Willits) - Harwood Rd (Laytonville) to SR 1 (Leggett) |
| 4 | A | US 395: Nevada near Cold Springs to Oregon near New Pine Creek | - Nevada border to Laver Crossing (Doyle) - Standish Buntingville Rd (A3, Janesville) to Blue Ln (Litchfield) - School House Rd (Ravendale) to Pencil Rd (Alturas) - Rd 133B (Davis Creek) to Oregon border |
| 5 | A | US 395: Hesperia (I-15) to SR 14 (Inyokern) | - I-15 (Hesperia) to Colusa Rd (Adelanto) - Hoffman Rd (Atolia) to SR 14 (Inyokern) |
| 5 | B | US 395: Inyokern (SR 14) to Nevada near Topaz Lake | - Sykes Rd (Coso Junction) to Lake St (Cartago) - SR 136 (Lone Pine) to Fort Rd (Independence) - Steward Ln (Big Pine) to Keough Hot Springs Rd (Bishop) - Bishop Golf Course Rd (Bishop) to Pine Creek Rd/Mill Creek Rd (Bishop) - S Landing Rd (Crowley Lake) to SR 203 (Mammoth Lakes) - SR 120 (Mono Lake Basin Rd, Lee Vining) to SR 167 (Pole Line Rd, Lee Vining) - SR 270 (Dog Town) to Emigrant St (Bridgeport) - East Side Ln (Walker/Coleville) to Nevada border |
| 5 | C | SR 14: Santa Clarita (I-5) to Inyokern (US 395) | - Exit 2 (Newhall Ave, Newhall) to Exit 24 (Crown Valley Rd, Acton) - Exit 30 (Pearblossom Hwy, Palmdale) to W Ave G (Lancaster) - Exit 64 (Silver Queen Rd, Mojave) to Phillips Rd (Mojave) - Jawbone Canyon Rd (Cantil) to US 395 (Inyokern) |
| 5 | D | US 6: Bishop (US 395) to Nevada Border | - Hunter Ave (Chalfant) to Nevada border |
| 6 | A | I-5: South of Sacramento to Kettleman City | - Exit 391 (SR 165, Los Banos) to Exit 349 (SR 33, Cantua Creek) |
| 8 | A | SR 20: Calpella (US 101) to Upper Lake (SR 29) and Clearlake Oaks (SR 53) to Yuba Pass (I-80) SR 29: Upper Lake (SR 20) to Lower Lake (SR 53) | - SR 20: E St (Williams) to Acacia Ave (Sutter) - SR 20: Smartville Rd (Smartville) to Penn Valley Dr/Rough and Ready Hwy (Penn Valley) - SR 29: SR 20 (Upper Lake) to SR 53 (Lower Lake) |
| 8 | C | US 50: Placerville (SR 49) to South Lake Tahoe | - SR 49 (Placerville) to Exit 60 (Sly Park Rd, Pollock Pines) - Whitehall Bluffs Rd (Pollock Pines/White Hall) to Nevada border |
| 8 | D | I-80: Sacramento to Nevada Border | - Exit 86 (I-5, Sacramento) to Exit 116 (SR 193, Newcastle) - Exit 133 (Canyon Way/Placer Hills Rd, Colfax) to Exit 161 (SR 20, Camp Spaulding) - Exit 174 (Donner Pass Rd, Soda Springs) to Nevada border |
| 9 | C | SR 120: Manteca (I-5) to Lee Vining (US 395) | - Exit 2 (McKinley Ave, Manteca) to Steinegul Rd (Escalon) - Valley Home Rd (Oakdale) to La Grange Rd (Keystone) - SR 108 (Yosemite Junction) to Whites Gulch Rd (Groveland) - Smith Station Rd (Groveland) to western boundary of Yosemite National Park - Eastern boundary of Yosemite National Park to US 395 (Lee Vining) |
| 10 | A | SR 1: San Francisco (US 101) to Lompoc (SR 246) | - US 101 (The Presidio, San Francisco) to Miramontes Point Rd (Half Moon Bay) - SR 84 (San Gregorio) to Bonny Doon Rd (Davenport) - Western Dr (Santa Cruz) to SR 129 (Watsonville) - Dolan Rd (Moss Landing) to Carmel Valley Rd (Carmel-By-The-Sea) - Corona Rd (Carmel Highlands) to Big Creek Cove Vista Point (Big Sur) - Willow Creek View Point (Big Sur) to SR 46 (Green Valley Rd, south of Cambria) - N Ocean Ave (north end of Cayucos) to Olive Street (San Luis Obispo) - W Grand Ave (Grover Beach) to SR 246 (Lompoc) |
| 11 | A | SR 12: Sebastopol (SR 116) to Lodi (SR 99) | - SR 116 (Sebastopol) to Warm Springs Rd (Kenwood) - Arnold Dr (Glen Ellen) to SR 221 (Napa) - Exit 56 (Chadbourne Rd, Fairfield) to SR 84 (Rio Vista) - SR 160 (Isleton) to SR 99 (Lodi) |
| 12 | A | I-80: San Francisco (US 101) to Sacramento (I-5) I-505: Vacaville (I-80) to Dunnigan (I-5) | - I-80: US 101 (San Francisco) to Exit 33 (SR-37, Vallejo) - I-80: Exit 39/39A (Red Top Rd, Fairfield) to Exit 75 (Mace Blvd, Davis) - I-505: I-80 (Vacaville) to I-5 (Dunnigan) |
| 13 | A | SR 41: Cholame (SR 46) to Fish Camp SR 46: Paso Robles (US 101) to Famoso (SR 99) | - SR 41: SR 33 (Reef Station/Avenal) to Hanford Armona Rd (Lemoore) - SR 41: Grangeville Blvd (Lemoore) to Exit 135 (N Friant Rd/Blackstone Ave, Fresno) - SR 41: N Fork Rd (O’Neals) to Fish Camp - SR 46: US 101 (Paso Robles) to SR 41 (Cholame) - SR 46: Lost Hills Rd (Lost Hills) to SR 99 (Famoso) |
| 13 | B | SR 140: Gustine (I-5) to El Portal (Yosemite) SR 180: Fresno (SR 99) to Miramonte (SR 245) | - SR 140: I-5 (Gustine) to Campus Pkwy (Merced) - SR 140: Plainsburg Rd (Planada) to SR 49/Jones Street (Mariposa) - SR 140: Chamberlain Rd (Midpines) to Yosemite National Park entrance - SR 180: Academy Ave (Sanger) to SR 245 (Miramonte) |
| 13 | C | SR 198: Coalinga (I-5) to Three Rivers (Sequoia National Park) | - I-5 (Coalinga) to Exit 81 (Houston Ave, Lemoore) - Exit 83 (14th Ave, Armona) to Exit 108 (SR 216, Lovers Lane, Visalia) - SR 65 (Exeter) to Sequoia National Park entrance |
| 13 | D | SR 152: Watsonville (SR 1) to Chowchilla (SR 99) SR 156: San Juan Bautista (US 101) to Hollister (SR 152) | - SR 152: SR 1 (Watsonville) to San Felipe Rd (San Felipe/Gilroy) - SR 152: SR 33 (Santa Nella Blvd, Santa Nella) to SR 99 (Chowchilla) - SR 156: US 101 (San Juan Bautista) to SR 152 (north of Hollister) |
| 13 | E | SR 99: South of Turlock to Wheeler Ridge (I-5) | - Exit 211 (Lander Ave, Turlock) to Exit 185 (E Mission Ave, Merced) - Exit 170 (SR 233, Chowchilla) to Exit 131 (SR 41, Fresno) - Exit 124 (S Clovis Ave, Fowler) to Exit 106/106B (Merritt Dr, Traver) - Exit 96/97 (SR 198, Visalia) to Exit 76 (SR 190, Tipton) - Exit 73 (Ave 120, Pixley) to Exit 39 (Merced Ave, north of Bakersfield) - Exit 28 (Olive Dr, Bakersfield) to I-5 (Wheeler Ridge). |
| 14 | A | I-8: El Centro to Arizona Border | - Exit 114 (Imperial Ave/SR 86, El Centro) to Exit 118A/B (SR 111, El Centro) - Exit 151 (Gordon Wells Rd, Winterhaven) to Arizona border |
| 14 | D | SR 111: Whitewater (I-10) to Mecca (SR 86) SR 86/SR 78: Coachella (I-10) to Brawley (SR 111) SR 111: Brawley (SR 78) to Calexico | - SR 111: I-10 (Whitewater) to Country Club Dr (Rancho Mirage) - SR 111: Bob Hope Dr (Rancho Mirage) to Airport Blvd (Thermal) - SR 86: I-10 (Coachella) to Desert Shores Dr (Desert Shores/Thermal) - SR 86: N Marina Dr (Salton City) to SR 78, and SR 78 to SR 111 (Brawley) - SR 111: SR 78 (Brawley) to SR 98 (Calexico) |
| 15 | A | SR 78: Oceanside (I-5) to Escondido (I-15) I-5: San Clemente (SR 1) to Mexico Border | - SR 78: Exit 1/1B (I-5, Oceanside) to Exit 17/17A (I-15, Escondido) - I-5: Exit 79 (SR 1, Dana Point/ San Clemente) to Exit 54C (Harbor Dr, Oceanside) - I-5: Exit 47 (Palomar Airport Rd, Carlsbad) to Exit 34 (Del Mar Heights Rd, Del Mar) - I-5: Exit 29 (Genesee Ave, La Jolla) to Mexico border |
| 17 | B | SR 1: Oxnard (US 101) to Dana Point (I-5) | - US 101 (Oxnard) to SR 23 (western Malibu) - Heathercliff Rd (Malibu) to W Century Blvd/LAX (Los Angeles) - I-105 (Los Angeles) To Warner Ave (Sunset Beach) - Seapoint Street (Huntington Beach) to I-5 (Dana Point) |
| 18 | B | SR 60: Los Angeles (I-10/I-5) to Beaumont (I-10) | - I-10/I-5 (downtown Los Angeles) to Exit 28 (Phillips Ranch Rd, Pomona) - Exit 32 (Ramona Ave, Chino) to Exit 59 (Day St, Moreno Valley) - Exit 62 (Perris Blvd, Moreno Valley) to I-10 (Beaumont) |
| 21 | A | SR 16: Sacramento (South Watt Ave) to Plymouth (SR 49) SR 49: Plymouth (SR 16) to Jackson (SR 88) SR 88: Jackson (SR 49) to Stockton (SR 99) | - SR 16: South Watt Ave (Sacramento) to SR 49 (Plymouth) - SR 49: SR 16 (Plymouth) to SR 88 (Jackson) - SR 88: SR 49 (Jackson) to SR 99 (Stockton). |

- Compliance with Requirements Applicable to NEVI Projects

Project selection and grant administration shall be consistent with the Bipartisan Infrastructure Law, enacted as the Infrastructure Investment and Jobs Act (IIJA), (Pub. L. 117-58). The NEVI formula program is authorized under Paragraph (2) under the Highway Infrastructure Program heading in title VIII of division J of the Bipartisan Infrastructure Law.

Applicants should take note that there are special requirements associated with the federal NEVI formula program, which will apply to projects awarded under this grant. The CEC will use state funds, likely from the Clean Transportation Program, to fund NEVI projects and will receive federal funds as reimbursement. Therefore, both Clean Transportation Program and federal NEVI formula program requirements will apply to grants resulting from this solicitation. The federal requirements are described in detail in the terms and conditions that will be required for grants awarded under this solicitation, which are referenced in Section II.A.2.

Without limitation to those terms or any other provision of this solicitation or resultant grant agreements, Applicants should in particular note that all work must comply with the Build America Buy America Act enacted as part of the IIJA, Davis Bacon Act, National Environmental Policy Act, Americans with Disabilities Act of 1990, Title VI of the Civil Rights Act of 1964, all applicable requirements of Title VIII of the Civil Rights Act of 1968, the Uniform Relocation Assistance and Real Property Acquisition Act [49 Code of Federal Regulations (CFR) 24 et seq.], and the requirements of the federal NEVI Program, including the requirements of United States Code (USC) Title 23, Chapter 1; and 2 CFR part 200; and 23 CFR parts 35 and 36; any promulgated regulations for the federal NEVI Program; and California’s NEVI Deployment Plan, as amended from time to time.

The Federal Uniform Act must be followed on all federal-aid, local assistance projects, which is how all projects resulting from this solicitation will be categorized. This Act applies if federal funds are used in any phase of a project.

- Project Location

- Each proposed EV charging station must be in a Needed Location of one (1) Corridor Segment.

- The EV charging stations must be sited within one (1) mile, as a car drives by the shortest route, of the corridor segment’s nearest off-ramp or intersection where a vehicle can exit the corridor. The EV charging stations must be easily accessible via a route that can safely and conveniently accommodate all light-duty EVs traveling to the facility, entering and leaving the facility, returning to the highway, and continuing in the original direction of travel.

- Proposed EV charging stations must be sited on previously disturbed or developed areas. “Previously disturbed or developed” refers to land that has been changed such that its functioning ecological processes have been and remain altered by human activity. The phrase encompasses areas that have been transformed from natural cover to non-native species or a managed state, including, but not limited to, utility and electric power transmission corridors and rights-of-way, and other areas where active utilities and currently used roads are readily available (10 CFR 1021.102(g)(1), found at https://www.ecfr.gov/current/title-10/chapter-X/part-1021/section-1021.102#p-1021.102(g)(1)).

- Access and parking must be in accordance with applicable requirements (such as local land use and zoning requirements) in the proposed project area and incorporate appropriate control technologies and best management practices as further described in the Federal Register notice of the Department of Transportation’s adoption of the EV charging stations categorical exclusion under NEPA (see https://www.federalregister.gov/documents/2023/09/20/2023-20238/notice-of-adoption-of-electric-vehicle-charging-stations-categorical-exclusion-under-the-national).

- Proposed EV charging stations must not be sited on property owned by Caltrans.

- Number of EV Charging Stations

For purposes of this solicitation, an EV charging station refers to the area in the immediate vicinity of a group of chargers and includes the chargers, supporting equipment, parking areas adjacent to the chargers, and lanes for vehicle ingress and egress. An EV charging station could comprise only part of the property on which it is located. Multiple chargers may be associated with one EV charging station.

Applicants must propose to install between one (1) and twenty (20) EV charging stations, each one in a unique Needed Location listed in Table 1: Project Corridor Segments, above.

- Number of Charging Ports

Each EV charging station must have a minimum of four (4) and a maximum of twenty (20) network-connected DCFC ports with a CCS Type 1 connector permanently attached. As long as a DCFC has a CCS connector, it may optionally have an SAE J3400 connector.

- Charging Equipment and Networking Requirements

All the following requirements must be met:

- Power Requirements

  - Each charging port must support output voltages between 250 volts DC and 920 volts DC.

  - Each port must have a continuous power delivery rating of at least 150 kW and supply power of at least 150 kW (or up to an EV’s power delivery request), simultaneously from each charging port at a charging station. Charging stations may conduct power sharing so long as each charging port continues to meet an EV’s request for power of at least 150 kW (or up to an EV’s power delivery request).

  - EV charging stations should be supported by a grid connection of at least 150 kW per installed port. For EV charging stations not connecting to the grid, Applicants will need to justify in the Project Narrative how the station will still comply with the simultaneous supply of 150 kW per charging port requirement using renewable distributed energy resources (DER).

- Connectors

  - Each DCFC must have at least one (1) permanently attached CCS Type 1 connector. Additional connector types such as SAE J3400 are allowed to be installed if the CCS connector requirement is still met. CHAdeMO is not an eligible connector. Connectors should be rated with a current carrying capacity of greater than or equal to 375 Amps.

- Interoperability: Charger-to-EV Communication

  - The chargers must conform to ISO 15118-3, and hardware must be capable of implementing both ISO 15118-2 and ISO 15118-20.

  - The chargers must include all necessary software and hardware to perform Plug-and-Charge using ISO 15118-2.

  - Conformance testing for charger software and hardware should follow ISO 15118-4 and 15118-5, respectively.

- Interoperability: Charger-to-Charger Network Communication

  - The chargers must conform to Open Charge Point Protocol (OCPP) 2.0.1 or later. Manufacturers must attest that the charger conforms to OCPP 2.0.1 or later by detailing it on a publicly available charger specification sheet.

- Interoperability: Charging-Network-to-Charging Network Communication

  - The charger’s networking software must connect to a central management system using OCPP 2.0.1 for the purposes of charger management and data reporting.

  - The charging network must be capable of communicating with other charging networks in accordance with the Open Charge Point Interface (OCPI) 2.2.1.

- Interoperability: Network Switching Capability

- The chargers must be designed to securely switch network providers without any changes in hardware.

- Cybersecurity

  - The chargers and charging software must meet all the NEVI cybersecurity requirements listed in the federal NEVI standards. Funding recipients will be required to develop a cybersecurity plan as required in Section II.B.18 after agreement execution and prior to the time of station commissioning.

- Charger Network Connectivity Requirements

- The chargers must be networked and must include the following three abilities:

      - Have network connectivity with one of the following:

        - IEEE 802.11n for high-bandwidth wireless networking, or

        - IEEE 802.3 for Ethernet for local- or wide-area network applications.

      - Be able to receive remote software updates, real-time protocol translation, encryption, and decryption, including:

        - Internet Protocol (IP)-based processor which must support multiple protocols, and

        - Compliance with Transmission Control Protocol (TCP)/IP and IPv6.

      - Be able to connect to a network’s back-end software.

  - Each charging port must be covered by and included in a networking agreement for at least five (5) years.

- Safety and Weather Resistance

- The charging equipment must be certified by an Occupational Safety and Health Administration Nationally Recognized Testing Laboratory.

- The charging equipment must be able to withstand extreme weather conditions, including temperature extremes, flooding, heavy rains, and high winds.

- Display screens must be protected from malfunctions due to condensation and any local area weather conditions.

- Compliance with State Requirements

- All chargers must meet applicable requirements, including those of Senate Bill 454 (Corbett, Chapter 418, Statutes of 2013), the California Air Resources Board Electric Vehicle Supply Equipment (EVSE) Standards, and the California Department of Food and Agriculture Division of Measurement Standards, for public chargers.

- Compliance with Applicable Laws, Ordinances, Regulations, and Standards

All Applicants proposed for award must comply with all applicable laws, ordinances, regulations, and standards; federal, state, and local electrical and building codes for construction; and at all EV charging stations, equipment must be publicly accessible.

- EV Charging Station Accessibility and Availability

EV charging stations funded under this solicitation must be publicly accessible 24 hours per day, 7 days per week, year-round. Equipment must be available to the public without restriction. A station that is not maintained or restricts access only to customers, tenants, employees, or other customers is not publicly accessible. This does not prohibit isolated or temporary interruptions in service or access because of maintenance or repairs.

Signage that limits who can use the chargers is strictly prohibited. Signs and other actions cannot be used to limit access to guests, patrons, or otherwise that would cause a driver to believe they would be prohibited from, towed, or fined for using the charger.

Site hosts must include signage indicating that the parking stall is for active EV charging only with a time limit for usage of the stall. A minimum of at least one (1) sign per six (6) charging stalls is recommended so that a driver can reasonably see the rules.

Sites where chargers are proposed to be located behind gates or barriers are generally not considered to have public access. An Applicant proposing sites that are located behind a gate or barrier has the burden of proof to describe why said chargers are public. The Applicant must submit documentation describing why the gate or barrier is necessary, and must disclose how someone charging their vehicle would access the charger. The disclosure shall include the available hours and access fees, the full process to access the charger, pay, and exit the site including if the driver must enter a building or otherwise navigate the facility. Such sites will be considered on a case-by-case basis and, if approved, will be required to add signage (1) directing the driver to the specific locations of the chargers on the property, (2) explicitly state that the chargers are available for all members of the public to use, and (3) include the cost to access the site. Signage shall be readable from the public roadway and at the gate entrance.

Optimal sites will have no fee associated with gaining access to the chargers. However, it is expected that some sites will have a fee associated simply by the nature of parking in certain environments. This could be a parking fee for the stall such as when someone parks in a downtown location and pays a paybox for using the stall for a given number of hours, a parking ramp that has a fee for access, or gated parking when done for safety or to limit loitering. In circumstances where a fee is required, the Applicant must disclose to the CEC the cost and details of the fee. The CEC will have the discretion to determine on a case-by-case basis if the fees are prohibitive, and in such cases, the CEC may require the Applicant to provide two (2) hours of free parking at the charging stall.

The CEC will not fund fast chargers located in hotel or motel parking lots unless a hotel or motel is the only type of property with an available paved lot area within the respective Needed Location. The hotel or motel parking lot must allow full public access to the facility parking lot. All other conditions required for publicly accessible installations must still be met.

Chargers that are located in a valet parking area or in circumstances where the driver must valet their vehicle to gain access to the charger are not eligible as public chargers.

The EV charging stations must have paved parking spaces available to render EV charging services. EV charging stations and parking areas must be well lit. The charger user must be able to easily read any instructions on the charger and the area around the vehicle must have adequate lighting to allow the driver to safely walk from the charger to the charging port on the vehicle.

Since the EV charging stations funded under this solicitation are intended to offer a service to the public, accessibility to all EV drivers is required. Applicants should familiarize themselves with the Division of the State Architect’s requirements on complying with the Americans with Disabilities Act, coordinate with their local permitting agency, and comply with the customer service requirements in Section II.B.13 to ensure accessibility for all drivers.

- Project Team

The Applicant, or the Subrecipient installing chargers, must be an Experienced Contractor, which is defined as a company or organization with a proven record of accomplishment in overseeing the procurement, permitting, and installation of at least twenty (20) DCFCs. The company or organization must have completed installations at three (3) or more different property locations for three (3) or more different customers since January 1, 2018.

Not every subcontractor or vendor must meet this definition to participate in the project. At minimum, the project team must include one (1) Experienced Contractor to serve as a subject matter expert to all other contractors, if necessary.

The project team must include a charging network provider that has demonstrated experience or has the capability to provide networking services for the charging stations for at least the entire 5-year in-service requirement (see Section II.B.11).

- Build America, Buy America

Without limitation to all other requirements in the terms and conditions that will be required for grants awarded under this solicitation, which are referenced in Section II.A.2 above, or any other provision of this solicitation or resultant grant agreements, Applicants should in particular note that Recipients must comply with federal Buy America requirements consistent with the final Federal NEVI standards (23 U.S.C. 313 at https://www.govinfo.gov/content/pkg/USCODE-2021-title23/pdf/USCODE-2021-title23-chap3-sec313.pdf) and Build America, Buy America Act (Pub. L. No 117-58, div. G sections 70901-70927). This includes, but is not limited to, requirements that all iron and steel; all manufactured products; and all construction materials that are used in the project are produced in the United States. Applicants are encouraged to review the Federal requirements and to verify with their equipment supplier(s) that their equipment meets and can document compliance with this requirement.

- Data Submittals

Applications that result in proposed awards and executed agreements will be required to perform recordkeeping and reporting on charger operations and reliability as specified in the solicitation Scope of Work (Attachment 14). These requirements include quarterly, annual, and one-time data submittals, as well as real-time reporting of charger status and charging session information through application programming interface (API). Applicants should familiarize themselves with the National Electric Vehicle Infrastructure Standards and Requirements found at https://www.federalregister.gov/documents/2023/02/28/2023-03500/national-electric-vehicle-infrastructure-standards-and-requirements and the solicitation Scope of Work requirements and ensure they have systems in place to comply.

- Operation, Maintenance, and Uptime

Each charging port, charger, and EV charging station funded through the solicitation must operate for public use for at least five (5) years after its commissioning date.

Each charging port must have an average annual uptime of greater than 97 percent per the requirements of the NEVI program specified in 23 CFR 680.116(b). A charging port is considered to be “up” when its hardware and software are both online and available for use, or in use, and the charging port successfully dispenses electricity in accordance with requirements for the minimum power level (see 23 CFR 680.106(d)). Charging port uptime must be calculated on a monthly basis for the previous twelve (12) months. Charging port uptime percentage must be calculated using the following equation:

µ = ((525,600−(T_outage−T_excluded))/525,600) × 100

where:

µ = port uptime percentage

T_outage = total minutes of outage in previous year

T_excluded = total minutes of outage in previous year caused by the following reasons outside the charging station operator's control, provided that the charging station operator can demonstrate that the charging port would otherwise be operational: electric utility service interruptions, failure to charge or meet the EV charging customer's expectation for power delivery due to the fault of the vehicle, scheduled maintenance, vandalism, or natural disasters. Also excluded are hours outside of the identified hours of operation of the charging station.

It will be the Recipient’s responsibility to demonstrate that this uptime requirement is met.

Each charging port, charger, and EV charging station funded through this solicitation shall meet the specific recordkeeping, maintenance, and reporting requirements related to uptime and other metrics that are detailed in the Scope of Work (Attachment 14).

- Payment Options

All of the following requirements must be met:

- The public charging stations must provide secure payment methods, be accessible to persons with disabilities, and must at minimum include:

  - Near Field Communication (NFC) and Radio Frequency Identification (RFID) contactless payment methods that accept major debit and credit cards.

  - Either an automated toll-free phone number or short message/messaging system (SMS) that provides the EV charging customer with the option to initiate a charging session and submit payment.

- Additional payment mechanisms may be offered, such as Plug-and-Charge or payment through mobile apps.

- Any customer or vehicle with the appropriate charging port connection must be allowed to utilize the charging station. Charging cannot be restricted to a specific customer base or vehicle manufacturer.

- The charging stations must not require a membership for use.

- The charging stations must not delay, limit, or curtail power flow to vehicles on the basis of payment method or memberships.

- The charging stations must provide access for users that are limited English proficient and accessibility for people with disabilities. Automated toll-free phone numbers and SMS payment options must clearly identify payment access for these populations.

- The point-of-sale and supporting network must use an open protocol to allow subscribers of other EV charging system networks to access the charging station.

- The point-of-sale and supporting network must be secure and meet the final NEVI cybersecurity requirements.

- Customer Service

The project must provide customer support service and ensure that EV charging customers have mechanisms to report outages, malfunctions, and other issues with the charging infrastructure. Mechanisms may include, but are not limited to, a toll-free telephone number, an email, instant messaging chat, or an online portal. The customer support service must be capable of providing or dispatching services to address customer concerns at the charging station. Customer support must be available in at least English and Spanish. Projects must comply with the Americans with Disabilities Act of 1990 requirements and multilingual access when creating reporting mechanisms.

- Highway and On-Site Signage

The project must coordinate with appropriate local agencies and Caltrans for directional signage on and along the highway and local roads, if it is not already installed. The signs must meet the California Manual on Uniform Traffic Control Devices (CA MUTCD) standards, and all other applicable laws, ordinances, regulations, and standards. The Recipient shall coordinate with cities and counties on trailblazer signage on local roads leading to the charging location. This award may cover funding for trailblazer and on-site signage as required to comply with the federal NEVI standards.

Recipients may contact Caltrans sign coordinators and ask for sign installation on the State Highway System at https://dot.ca.gov/programs/safety-programs/sign-specs/district-sign-coordinators.

- Eligible Project Costs

Costs incurred for the following are eligible for CEC reimbursement or as the Applicant’s match share, after the corresponding project phase has been authorized by the FHWA and the grant agreement has been formally executed:

  - DCFC electric vehicle supply equipment (EVSE, or chargers) with between 4 and 20 CCS ports per station

  - Transformers

  - Electric panels

  - Conduit

  - Wiring

  - Meters

  - Costs for planning and permitting of on-site, renewable DER equipment such as solar arrays or stationary battery energy storage systems (BESS) that are directly related to the charging of EVs. These costs should only be considered if they will lead to lower costs to consumers, greater EV charging station reliability, and if they do not substantially increase the timeline for completing an EV charging station project. Any of these systems must be interconnected to the charging system and must be separately metered from the site host's regular business meter.

  - Installation costs

  - Planning and engineering design costs

  - Stub-outs

  - Lighting, canopies, and other amenities designed to serve EV charging station customers

  - Demand management equipment

  - Networking licenses for up to five (5) years of operations and which are purchased during the agreement term

  - Equipment warranties for up to five (5) years of operations and which are purchased during the agreement term

  - Maintenance provided during the agreement term for up to five (5) years of operations, or a maintenance agreement or a service level agreement for up to five (5) years of operations and which is purchased during the agreement term

  - Local engagement and outreach related to EV charging, not to exceed three percent of the total reimbursable project cost.

  - Signage

  - EV charging infrastructure workforce development directly related to the charging of EVs in the proposed project, not to exceed three percent of the total reimbursable project cost.

The following project costs and/or types ARE NOT eligible as CEC reimbursement or match share. This includes but is not limited to:

  - Vehicle purchases

  - Manufacturing costs

  - A standard outlet (110/120 volt or 220/240 volt)

  - Level 1 and/or Level 2 chargers

  - DCFC EVSE (chargers) without CCS connectors

  - DCFC EVSE (chargers) above the 20 CCS port maximum at one charging station

  - Mobile charging equipment

  - Land acquisition or lease costs

  - Costs to obtain match funding commitments

  - Lighting, canopies, and other amenities on the charging station site that are not designed to serve station customers

  - Nonrenewable distributed energy resources

  - Distribution grid or other equipment costs that are otherwise covered by programs or tariff rules of the electric utilities are excluded

  - Projects that are mandated by any local, regional, state, or federal law, rule, or regulation

  - Projects that help the Applicant meet a performance requirement mandated by local, regional, state, or federal law, rule, or regulation

  - Paper studies or research projects (e.g., a study which assess the cost and feasibility of EV charging station installations along certain regions/corridors)

  - Projects that are primarily surveys to determine interest in the installation of EV charging stations in a particular region/corridor

  - Proposals for vehicle demonstrations or demonstrations of existing technologies

  - Software development

A project that receives incentive funding from another CEC grant funding opportunity (GFO) or block grant incentive project is not eligible for this GFO.

- Electric Vehicle Infrastructure Training Program (EVITP)

EV charging infrastructure and equipment located on the customer side of the electrical meter shall be installed by a contractor with the appropriate license classification, as determined by the Contractors’ State License Board, and at least one (1) electrician on each crew, at any given time, who holds an EVITP certification. Projects that include installation of a charging port supplying 25 kilowatts or more to a vehicle must have at least 25 percent of the total electricians working on the crew for the project, at any given time, who hold EVITP certification. One member of each crew may be both the contractor and an EVITP certified electrician. The requirements stated in this paragraph do not apply to any of the following:

- EV charging infrastructure installed by employees of an electrical corporation or local publicly owned electric utility.

- EV charging infrastructure funded by moneys derived from credits generated from the Low Carbon Fuel Standard Program (Subarticle 7 (commencing with Section 95480) of Article 4 of Subchapter 10 of Chapter 1 of Division 3 of Title 17 of the California Code of Regulations).

- Single-family home residential EV chargers that can use an existing 208/240-volt outlet.

- Compliance with California EVSE Commercial Device Requirements All electric vehicle supply equipment (EVSE) installed for commercial use shall have a type approval certificate issued through the California Type Evaluation Program (CTEP) administered by the California Department of Food and Agriculture (CDFA) Division of Measurement Standards (DMS) or Certificate of Conformance issued by the National Type Evaluation Program (NTEP) administered through the National Conference on Weights and Measures (NCWM). California accepts NTEP certificates so long as the device also meets CCR Title 4, Section 4002.11.

Unless otherwise updated by the CDFA DMS, any installation, repair, or maintenance on commercial EVSE must be performed by a Registered Service Agency (RSA) and after the device is placed in service, the RSA must report this information to the county within 24 hours. Device owners are responsible for registering their device with the county.

- Data Privacy and Cybersecurity

Recipients shall be responsible for cybersecurity as it relates to owning, operating, maintaining, and data sharing for the EVSE. The Recipient must develop and submit to the CEC a Data Management and Cybersecurity Plan after agreement execution and prior to the time of station commissioning. The Data Management and Cybersecurity Plan, as required in the Scope of Work (Attachment 14), must include the Recipient’s data security policies, procedures, and remediation plan. The plan should include, at minimum, the following:

- Strong authentication and access control

- Network segmentation to isolate critical components to limit attack

- Intrusion detection and monitoring

- Integrating cybersecurity measures at the hardware level

- Firmware integrity of chargers

- User data privacy and protection

- Secure data transfer and protection at rest

- Secure communications protocols

- Payment systems

- Cloud protections

- System and data access management to ensure only authorized individuals have access

- Employee cybersecurity training

- Patching and updates

- Incident response reporting and recovery, including a communications plan

- Audits and assessments

- Continuity of operations

- Risk acceptance and mitigation

- Disaster recovery

The CEC strongly encourages Recipients use the U.S. DOT’s guidance on developing a data management plan for assistance with their drafting their plans, found at https://ntl.bts.gov/ntl/public-access/creating-data-management-plans. The US Joint Office of Energy and Transportation also has available Sample Cybersecurity Clauses for EV Charging Infrastructure Procurements, which can be found at https://driveelectric.gov/cybersecurity-clauses. Recipients are strongly encouraged to reference the Joint Office’s Sample Cybersecurity Clauses for EV Charging Infrastructure Procurements when developing their Application and agreements with subcontractors.

- Project Revenue and Pricing for EV Charging

Recipients must comply with the restrictions on use of program income specified in 23 CFR Part 680.106(m). Recipients may use revenue generated from the operation of charging stations for debt service, a reasonable return on investment, and/or costs for operation, maintenance, and site improvement. Recipients must include sufficient information in their Project Narrative (Attachment 1) for the CEC to evaluate how revenue from the proposed charging stations will be used in accordance with 23 CFR 680.106(m).

Communication of price. The price for charging must be displayed prior to initiating a charging transaction and be based on the price for electricity to charge in $/kWh. The price for charging displayed and communicated via the charging network must be the real-time price (i.e., price at that moment in time). The price at the start of the session cannot change during the session. Price structure including any other fees in addition to the price for electricity to charge must be clearly displayed and explained.

- Right of Way

Recipients must prepare to have their projects follow the procedures of federally-funded local transportation projects as explained in the Caltrans Local Assistance Procedures Manual (LAPM), found at https://dot.ca.gov/programs/local-assistance/guidelines-and-procedures/local-assistance-procedures-manual-lapm. In particular, Recipients should prepare for the Right of Way project phase by reviewing Attachment 15, the Right of Way Certification Form 13B (NEVI). This attachment is included as an informational item because, if awarded, Applicants will be responsible for completing the Right of Way Certification Form 13B as part of the Scope of Work (Attachment 14). All Applicants are encouraged to familiarize themselves with this attachment in the application phase.

As background, Right of Way Certification is to document that real property interests have been or are being secured, and physical obstructions, including buildings, utilities, and railroads, have been or will be removed, relocated, or protected as required for the construction, operation, and maintenance of the proposed federally funded project. The Right of Way Certification also documents that right of way activities were conducted in accordance with applicable policies and procedures outlined in the LAPM.

## Match Funding Requirements

- Total Match Share Requirement

For this solicitation, applications must include exactly 20 percent total match share of allowable project cost. (Example: A project for with a total allowable project cost of $5 million must have a budget with exactly $4 million in reimbursable share and $1 million in match share.)

“Match funding” or “match share” means cash or in-kind (non-cash) contributions provided by the Applicant/Recipient, subrecipients, or other parties that will be used in performance of the proposed project. Match share percentage is calculated by dividing the total match share contributions by the total allowable project cost. “Total allowable project cost” is the sum of the CEC’s reimbursable share and Recipient’s match share of the project costs. Match share expenditures have the following requirements:

- Total match share must conform to the “Cash Match Share Requirement” contained in this solicitation.

- All match share expenditures must conform to the terms and conditions of this solicitation and the resulting grant agreement.

- Applicants must disclose the source and provide verification and documentation for the match share funding committed to the project. For any match share committed by a third party (i.e., other than match share committed by the Applicant), Applicants must submit a letter of commitment from each match share partner identifying the source(s) and availability of match funding.

- During the term of the grant agreement, Recipients will be required to document and verify all match share expenditures through invoices submitted to the CEC.

- Match share funding may be in the form of cash or in-kind contributions such as donated labor hours and equipment.

- Equipment may count as match funds as long as the value of the contribution is based on documented market values or book values, prorated for its use in the project, and depreciated or amortized over the term of the project using generally accepted accounting principles (GAAP).

- Match share expenditures (cash and/or in-kind) must be documented, reasonable, allowable, and allocable to the project as determined by the CEC. Applicants proposed for award and that included in-kind match share in their budget will need to prepare a written description of in-kind match as explained in Section 3.9 Flexible Match in the Local Assistance Procedures Manual (found at https://dot.ca.gov/programs/local-assistance/guidelines-and-procedures/local-assistance-procedures-manual-lapm) for FHWA approval of the in-kind match share sources.

- Match share expenditures are allowable under an agreement only if they are incurred after an agreement is fully executed with the CEC and after E-76 approval (FHWA authorization) for the relevant project phase. Match expenditures incurred prior to the execution of an agreement and before E-76 approval (FHWA authorization) will not be eligible costs. The CEC is not liable for Applicant’s match share costs if the grant is not executed, if execution is delayed, or if the match share expenditure is not allowable by FHWA or under the terms and conditions of the grant. Please note that non-match expenditures incurred prior to agreement execution and E-76 approval (FHWA authorization) are not reimbursable.

- Cash Match Share Requirement

Applications must include a minimum 50 percent cash match share. (Example: If a project proposes $1 million in match share, $500,000 or more must be cash match and the remaining $500,000 can be in-kind match.)

Cash match means the net of any funds actually expended by the Applicant for the project. Net means after any sort of discount or rebate is applied. Expenditures for Applicant’s compensated labor hours, including allowable fringe benefit and overhead rates, travel, materials, supplies, equipment, subrecipient costs, and other miscellaneous expenditures may be claimed as cash match if the expenditures are included in the approved agreement budget, paid in full with funding sources other than CEC funds, including block grants funded by the CEC, and supported with appropriate documentation, including proof of payment. For indirect overhead, backup documentation, such as a cost allocation plan based on actual expenditures incurred and paid, is required. Cost allocations must be reasonable and allocable to the proposed project.

- In-Kind Match Share

The balance of the total match share requirement beyond the cash match share requirement (if any) may be met through in-kind match share contributions.

Applications that move to an executed agreement will require FHWA approval (separate from E-76 approval) for any in-kind match funding sources. Applicants may propose in-kind match funding in their proposal’s budget. If FHWA does not approve the in-kind match source(s), then the Applicant must replace the ineligible match sources and will still be liable for the total match funding in the grant agreement. Please reference Section 3.9 Flexible Match in the Local Assistance Procedures Manual at https://dot.ca.gov/programs/local-assistance/guidelines-and-procedures/local-assistance-procedures-manual-lapm for more information.

In-kind match share contributions are: 1) non-cash contributions provided by the Applicant; 2) cash or non-cash contributions provided by subrecipients; and 3) cash or non-cash contributions provided by other third parties. Applicant in-kind match share can be in the form of volunteer labor, existing equipment, existing supplies, and services provided by a third-party or subcontract. The value of in-kind match is based on the fair market value of the goods and services provided at the time it is claimed as match. In-kind match share must be included in the agreement budget and supported with appropriate documentation. Cost allocations must be reasonable and allocable to the proposed project.

- Match Share Restrictions

- Other Sources of CEC Funding – Other sources of CEC funding may not be claimed as match share. This includes block grants funded by the CEC.

- Other Sources of Federal Funding - Other sources of Federal funding may not be claimed as match share, unless specifically allowed by law to be used as non-Federal match.

- Funds Already Expended or Otherwise Encumbered – Applicants cannot claim funds that have already been expended or otherwise encumbered as match share. Match share expenditures are only allowable if they are incurred after an agreement is fully executed with the CEC and after E-76 approval (FHWA’s authorization of the project).

- Investor-Owned Utility Program Funding – Funding provided through utility tariff programs may not be used as match share.

- Documentation – If selected for an award, all claimed match share expenditures must be adequately documented to the CEC during the agreement invoicing process.

## D.	Unallowable Costs (Reimbursable or Match Share)

For an item of cost to be allowable for reimbursement with CEC funds or as match share expenditure, it must be included in the executed agreement budget and allowable per the terms and conditions of the resulting agreement. The following are examples of unallowable costs under an agreement resulting from this solicitation. This list is not comprehensive and additional items of cost may be unallowable in accordance with the agreement terms and conditions.

- Forgone Profit – For example, if a company usually charges 10% profit but only charges 4% to CEC the unclaimed difference is not an allowable item of cost.

- Forgone Rent – For example, rent that is not paid is not an allowable item of cost.

- Discounted or Refunded Equipment Costs – For example, a claim that equipment costs $10,000 but the grant recipient only pays $6,000 due to some “special” discount. The difference of $4,000 is not an allowable match share expense. Another example is if the grant recipient actually pays $10,000 but the vendor refunds $4,000 – only the net $6,000 is an allowable item of cost.

- Forgone Salary, Fringe, Indirect or Other Types of Cost – For example, a person normally charges or is paid $100 per hour, but will only charge $50 per hour towards the CEC award. Only actual costs incurred and paid to the employee are allowable. Therefore, if an employee is actually paid $100 per hour and CEC only reimburses at $40 per hour, then the unreimbursed $60 per hour is an allowable match share cost because this is an actual payment as opposed to a forgone salary amount. Volunteer labor (i.e., labor from a person who does not receive any compensation for their labor) may be an allowable in-kind match share expense if the value of the labor is reasonable and justified.

- Utility Provided Electrical Upgrades and Funding-– For example, expenses that are already paid or to be paid for through a utility program, tariff, or other ratepayer funding is not an allowable item of cost. This includes ratepayer funded enrollment incentives.

- Compliance with Local, Regional, State, or Federal Law, Rule or Regulation - For example, expenses associated with ensuring compliance with state or federal building codes, including provisions of the California Green Building Standards Code requiring the installation of a minimum amount of electric vehicle supply equipment, Electric Vehicle Capable, or Electric Vehicle Ready parking spaces, is not an allowable item of cost.

# III.	Application Format, Required Documents, and Delivery

## Required Format for an Application

This section contains the format requirements and instructions on how to submit an application. The format is prescribed to assist the Applicant in meeting State requirements and to enable the CEC to evaluate each application uniformly and fairly. Applicants must follow all application format instructions, answer all questions, and supply all requested information.

All applications submitted under this solicitation must be typed or printed using a standard 11-point font, single-spaced and a blank line between paragraphs.  Pages must be numbered, and sections titled.

## Method for Delivery

The method of delivery for this solicitation is the Energy Commission Agreement Management System (ECAMS), available at https://ecams.energy.ca.gov/.

Information about ECAMS will be provided at the Pre-Application Workshop. Information about how to register for an ECAMS account and guidance on how to apply through the system is available at https://www.energy.ca.gov/funding-opportunities/funding-resources under General Funding Information.

The CEC is providing a team of technical assistants to support Applicants with this process. Please email ECAMS.SalesforceSupport@energy.ca.gov for support.

ECAMS allows Applicants to complete and submit their application to the CEC prior to the date and time specified in this solicitation. Files uploaded to the system must be in Microsoft Word (doc format) and Excel Office Suite formats unless originally provided in the solicitation in another format. PDF format is acceptable. The completed Proposal Budget Template, Attachment 3, must be in Excel format.

The deadline to submit grant applications through ECAMS is 11:59 p.m. ECAMS automatically closes at 11:59 p.m. If the full submittal process has not been completed before 11:59 p.m., your application will not be considered. NO EXCEPTIONS will be entertained.

The CEC strongly encourages Applicants to upload and submit all applications by 5:00 p.m. because CEC staff will not be available after 5:00 p.m. or on weekends to assist with the upload process. And please note that while we endeavor to assist all would-be Applicants, we cannot guarantee staff will be available for consultation on the due date, so please plan accordingly.

Please give yourself ample time to complete all steps of the submission process: do not wait until right before the deadline to begin the process. Due to factors outside the CEC’s control and unrelated to ECAMS, upload times may be much longer than expected. For example, some past Applicants experienced unexpected issues on their end, causing long delays that prevented timely submission. They spent significant time and resources on applications the CEC will not consider.

Please plan accordingly. First time users must register as a new user to access the system. There will be two types of user accounts to establish: 1) An organizational account, for the entity applying to the solicitation; and 2) user accounts for individuals who will be submitting the application on behalf of the organization.

Applicants will be required to upload all attachments marked “required” in the system in order for the application to be submitted.

## Solicitation Informational Documents

In addition to this solicitation manual, the following attachments are available on the solicitation webpage as informational documents to consider in preparing applications:

  - Scope of Work (Attachment 14)

If awarded, this document will be included as part of the recipient agreement. The Scope of Work outlines tasks to be completed under this solicitation as well as project and recipient-specific information to be filled in during agreement development

  - Right of Way Certification Form 13B (NEVI) (Attachment 15)

If awarded, recipients will complete this form to document the Right of Way (R/W) or rights in real property that may be required for each EV charging station. It has been customized for the NEVI formula program.

## Application Content

Items listed below are required as part of the application package. Failure to provide any items may result in disqualification of the application. Attachment requirements are expanded and explained below in this section and in the attachments themselves. Note that Letters of Support (Attachment 13) are optional.

| Item | Attachment Number | How Many Attachments to Submit |
| --- | --- | --- |
| Project Narrative | Attachment 1 | One |
| Station Information | Attachment 1B | One |
| Schedule of Products and Due Dates | Attachment 2 | One per Station |
| Proposal Budget | Attachment 3 | One per Station |
| Letters of Commitment | Attachment 4 | One per Station |
| Preliminary Site Plan | Attachment 5 | One per Station |
| CEQA Worksheet | Attachment 6 | One per Station |
| National Environmental Policy Act (NEPA) Preliminary Environmental Study (PES) Form | Attachment 7 | One per Station |
| Utility Verification Form | Attachment 8 | One per Station |
| Resumes | Attachment 9 | One |
| Contact List | Attachment 10 | One |
| Past Performance Reference Form(s) | Attachment 11 | One |
| Applicant Declaration | Attachment 12 | One |
| Letters of Support (Optional) | Attachment 13 | One |

- Applicant Certifications

ECAMS will require Applicants to provide the required authorizations and certifications listed below prior to final submission of their application:

All Applicants must certify under penalty of perjury under the laws of the State of California that:

- I am authorized to submit this application on behalf of the Applicant.

- I authorize the CEC to make any inquiries necessary to verify the information presented in this application.

- I authorize the CEC to obtain business credit reports and make any inquiries necessary to verify and evaluate the financial condition of the Applicant.

- I have read and understand the terms and conditions contained in this solicitation. I accept the terms and conditions contained in this solicitation on behalf of the Applicant and the Applicant is willing to enter into an agreement with the CEC to conduct the proposed project according to the terms and conditions without negotiation.

- I certify that (1) this application does not contain any confidential or proprietary information, or (2) if confidential information is allowed under the solicitation, it has been properly identified.

- I certify under penalty of perjury under the laws of the State of California that, to the best of my knowledge, the information contained in this application is correct and complete.

- I am authorized to agree to the above certifications on behalf of the Applicant.

- Project Narrative (Attachment 1)

The Project Narrative must include a table of contents (which will not count towards the page limitation) and a summary of the proposed project and its operational goals and objectives.

The total number of pages for the Project Narrative is limited to 20 pages or 3 times the number of EV charging stations proposed in the project, whichever is more. For example, if 20 stations (the maximum allowed) are included in the proposed project, the Project Narrative is limited to 60 pages. The Operations and Maintenance Plan portion of the Project Narrative is limited to five (5) pages regardless of the overall Project Narrative page limit.

Applicants should submit one Project Narrative that includes information for all EV charging stations proposed in the application. Clearly delineate between the proposed individual EV charging stations throughout the application by numbering the stations (1, 2, 3, etc.) and identify them as Station 1, Station 2, Station 3, etc., throughout the Project Narrative and other application attachments.

Applicants must address each of the scoring criteria described in this section by providing sufficient, unambiguous detail so that the evaluation team will be able to evaluate the application against each scoring criterion.

The Project Narrative must respond directly to each criterion with the headings as titled below, and must include the following information:

- EV Charging Station Siting and Equipment

  - List the proposed EV charging station location(s), including addresses and the current use of the site, including if the site is an existing charging station. Provide a compelling justification for the specific proposed EV charging station location(s) and explain how each site will effectively serve customers traveling in a Needed Location identified in Table 1.

  - Calculate the maximum distance between each proposed station location and the end of the off-ramp, or highway intersection exit if there is no off-ramp, of the respective Corridor Segment. Show that the proposed project will satisfy the one-mile distance requirement by attaching a screen shot showing the distance calculation from a commercially available distance measuring tool. Explain how each proposed EV charging station location will be easily accessible from the Alternative Fuel Corridor.

  - Explain how the Preliminary Site Plan (Attachment 5) for each proposed EV charging station was designed with the customer experience in mind. Include discussion of any unique stall configurations, including any potential accommodation of cars pulling trailers, or of larger vehicles. Also discuss where lighting and shelter will be provided.

  - Discuss each proposed EV charging station’s amenities including restrooms and proximity to retail shops, restaurants, parks, pet relief areas, or other positive attributes.

  - Identify the make, model, and power level(s) of the chargers being deployed, how many ports each charger has, and why the chargers and types of connectors were chosen for the project with clear reasoning based on expected customer needs.

  - Provide the number of CCS ports proposed at each EV charging station and if the minimum requirement is exceeded.

  - Describe how the charging ports at each charging station will be guaranteed to supply vehicles with at least 150 kW simultaneously.

  - Identify the grid connection supply and its capacity, and any proposed renewable DER equipment such as solar arrays or BESS that will be used to help supply and manage power at each charging station. If the proposal includes renewable DER equipment, explain how these features will lead to lower costs to consumers and greater EV charging station reliability, and how they will not substantially increase the timeline for completing the proposed project.

- Project Readiness

  - Explain the status of site control or access rights for each proposed charging station property. Provide backup documentation, including, but not limited to: leases, ownership, site host agreements, or letters of intent, in the Letters of Commitment attachment (Attachment 4). If control or access rights for a site are not secured at the time of application, explain how control or access rights will be obtained and the anticipated timeline to do so.

  - Identify the entity(ies) that will own and operate the proposed EV charging stations and the associated equipment, and explain their readiness to assume those responsibilities.

  - Explain the due diligence conducted for each proposed charging station site, including research into the site’s zoning and progress made in obtaining necessary planning approvals and permits.

  - Explain progress made in obtaining a CEQA determination for each EV charging station, from outreach to the local authority having jurisdiction up to actual receipt of a notice of exemption or a determination that no CEQA review is required. Supporting information should be provided in the CEQA Worksheet (Attachment 6).

  - Explain if any of the following environmental issues were identified when completing the NEPA PES Form (Attachment 7): The proposed EV charging station site(s) are in Special Flood Hazard Areas (SFHA) or have open cleanup cases within a 1,000-foot radius. How to find this information is explained in Section III.D.9 of this manual. Supporting documentation should be provided in the NEPA PES Form (Attachment 7).

  - Complete a Utility Verification Form (Attachment 8) for each charging station and discuss the likely available electrical capacity for each charging station site. Discuss the plan and timeline for reaching full electrical capacity to deliver the nameplate capacity at each station site.

  - Document any communications with the manufacturer(s) that identify the estimated timeline to deliver equipment including chargers, switchgear, BESS, and any other equipment proposed for installation.

- Expected Project Benefits

  - Discuss methods that will be deployed to reduce or minimize the charging cost to drivers. Document your assumptions.

  - Describe how the EV charger deployment will benefit EV drivers and accelerate EV adoption, in terms of expanding public charger availability, increasing EV charging capacity, and serving local EV charging needs.

  - Discuss any plans for hiring, apprenticeships, or other workforce development components to the proposed project that will bring economic benefits to the local communities surrounding the proposed station site(s).

  - Describe how the project will meet or exceed the solicitation’s goal of 25 percent small business participation. Please refer to Section V.A. below for the definition of small business.

- Project Budget and Finances

  - Describe how the proposed project’s budget is cost effective and reasonable relative to the Scope of Work (Attachment 14) and expected benefits to California. If proposing more than one EV charging station, explain any budget differences between stations.

  - Calculate the Cost-per-CCS-Port for each proposed EV charging station in the application. For instance, if the project proposes five stations, there should be five values of $grant/CCS-port calculated, one per station. The Cost-per-CCS-Port includes all CEC reimbursable costs associated with the capital expenditure required for the CCS charging port. This includes, but is not limited to, administrative, design, installation, operations and maintenance, and equipment costs.

  - Calculate the total allowable project cost per kilowatt of charging capacity for each proposed EV charging station. This should be calculated by summarizing the total allowable project cost of the station (defined as the sum of the CEC’s reimbursable share and Recipient’s match share of the project costs) by the amount of charging capacity the Applicant is proposing for the station. Example: An Applicant is proposing to install a station with ten (10) 200-kW charging ports for a total station capacity of 2,000 kW and  for a total allowable project cost of $1,400,000. The total allowable project cost per kW = $700/kW. If the project proposes five stations, there should be five values of $/kW calculated, one per station.

  - Describe how the proposed project will use income or revenue earned from the operation of the EV charging stations in compliance with the 23 CFR 680.106(m), and describe how the Applicant will supply the CEC with documentation to verify compliance during the first five years of operations.

  - Provide the amount of Match Funds (cash and/or in-kind) and provide verification and documentation of the source and availability. Applicants must provide a Letter of Commitment (Attachment 4) documenting their funding support. Provide details (name and business location, type of entity, amount, etc.) for each match share funding partner.

- Operations and Maintenance Plan (Limit: 5 pages)

  - Applicants must submit an Operations and Maintenance Plan that details their strategy to operate and maintain the charging equipment funded through this solicitation for at least five years after its commissioning date. The plan must demonstrate:

      - The ability to achieve an average annual uptime of greater than 97 percent per port.

      - Strategies to physically secure the site and limit or prevent tampering with or damage to the chargers.

      - Strategies and timelines to provide prompt attention to chargers that are not operational and carry out repairs to maximize uptime.

      - The availability of site host training and outline the responsibilities of the site host in conducting operations and maintenance.

      - Who will be responsible for maintaining the charging stations, charging equipment, and all ancillary equipment, including but not limited to any awnings, canopies, shelters, restrooms, and information display kiosks or signage associated with the charging station. “Maintain,” as used in this solicitation means “to provide all needed repairs or desired and approved alteration, as well as to clean the equipment and keep it safe and presentable.”

      - The Applicant’s plan to continue station operation beyond the agreement term and minimum five-year operation, maintenance, and data reporting period.

- Team Experience and Qualifications

  - Identify, by name, all key personnel assigned to complete each EV charging station project, including the project manager, and clearly describe their individual areas of responsibility. The project manager is the one individual responsible for interacting with the CAM on all issues relating to the overall project and coordinating all aspects of work under the project.

  - Explain how the Applicant or lead installation Subrecipient(s) from the proposed project team meet(s) or exceed(s) the Experienced Contractor definition in Section II.B.8 Project Team.

  - Explain how the Applicant’s selected charging station network provider has demonstrated experience keeping chargers in service for at least five years.

  - Detail the Applicant’s experience with federally funded projects and compliance with federal requirements like the Davis Bacon Act.

  - Explain how the Applicant demonstrates experience meeting deadlines and completing milestones associated with large, complex public projects, including examples of previously successful EV charging projects. Past Performance forms (Attachment 11) will be evaluated in this criterion, if the Applicant has relevant past performance.

- Station Information (Attachment 1B)

Applicants must include a completed Station Information spreadsheet. One spreadsheet should include information for all EV charging stations proposed in the application. The information requested for each station includes the Corridor Group, Corridor Segment, and Needed Location of the station; requested grant funding and match share funding amounts; the station address; number of chargers (EVSE) proposed to be part of the funded project; number of CCS ports to be part of the funded project; if SAE J3400 connectors will be provided optionally; and if there will be onsite DER.

- Schedule of Products and Due Dates (Attachment 2)

Applicants must include a completed Schedule of Products and Due Dates for each EV charging station in the application. All EV charging stations, chargers, and supporting equipment should be operational and open for public use within three (3) years from the agreement execution date. Instructions for the Schedule of Products and Due Dates are included in Attachment 2. The Schedule of Products and Due Dates must be in MS Excel.

- Proposal Budget (Attachment 3)

Applicants must include a completed Proposal Budget for each EV charging station in the application, as well as Major Subrecipient Proposal Budgets for every station where a subaward will be $100,000 or more (explained in more detail below). Applicants must upload all budgets (Prime and Major Subrecipients) as MS Excel attachments and leave the ECAMS budget sections blank in ECAMS.

The Applicant must submit information on all tabs of the budget forms. The salaries, rates, and other costs entered must reflect the salaries, rates, and other costs the Applicant would include if selected as a grant recipient. A separate set of complete budget forms is required for the Applicant and for each subaward containing $100,000 or more of CEC funds.

    - Detailed instructions for completing these forms are included at the beginning of Attachment 3.

      - Rates and job descriptions shown must reflect rates and job descriptions charged under an agreement resulting from this solicitation. The salaries, rates, and other costs entered on these forms become a part of the final agreement. The entire term of the agreement and projected rate increases must be considered when preparing the budget. Unless a federally approved indirect rate is used, indirect rates proposed are considered capped and shall not change during the term of the agreement. The grant recipient shall only be reimbursed for their actual rates up to the indirect rate cap. A description of available indirect rate options is available on the ECAMS Resources webpage under Budget Category Guidance for indirect rates. Unlike indirect rates, the rates for Direct Labor and Fringe Benefits are treated as estimates; a grant recipient can invoice at higher rates as long as it is only invoicing for actual expenditures it has made. The hourly or monthly rates provided shall be unloaded (before fringe benefits or indirect costs).

      - The information provided in these forms will not be kept confidential.

      - All reimbursable expenditures must be expended within the approved term of the grant agreement. Expenditures may be counted as reimbursable or match share only after an agreement is executed and the FHWA authorizes the relevant project phase (E-76 approval).

      - Applicants must budget for the expenses of a Kick-off Meeting, at least one (1) Critical Project Review meeting, and a Final meeting. Meetings may be conducted at the CEC or remotely, as determined by the CAM.

      - Applicants must budget for the preparation and submission of quarterly progress reports during the term of the agreement.

      - The purchase of equipment (defined as items with a unit cost greater than $5,000 and a useful life of greater than one year) with CEC funds will require disposition of purchased equipment at the end of the project. Typically, grant recipients may continue to utilize equipment purchased with CEC funds as long as the use is consistent with the intent of the original agreement. There is no disposition requirements for equipment purchased with match share funding.

    - The Budget must reflect estimates for actual costs to be incurred during the approved term of the agreement. The CEC can only approve and reimburse for actual costs that are properly documented in accordance with the grant agreement terms and conditions.

    - Current policy dictates that Applicants shall NOT budget for, and CANNOT be reimbursed for, more than their actual allowable expenses (i.e., the budget cannot include profit, fees, or markups) under the agreement. Subrecipients (all tiers) are allowed to include up to a maximum total of 10% profit, fees or mark-ups on their own actual allowable expenses less any expenses budgeted to sub-subrecipients (i.e., profit, fees and markups are not allowed on lower tier subrecipient expenses). For example, if a subrecipient has $100,000 in actual allowable costs but has budgeted $20,000 to a sub-subrecipient, then the subrecipient can only include up to 10% profit on $80,000 ($100,000 minus $20,000). See terms and conditions for additional restrictions and requirements.

IMPORTANT – Payment of Prevailing Wage: Applicants must read and pay particular attention to the terms and conditions section related to Public Works and payment of Prevailing Wages. Prevailing wage rates can be significantly higher than non-prevailing wage rates. Failure to pay legally required prevailing wage rates can result in substantial damages and financial penalties, termination of the grant agreement, disruption of projects, and other complications.

- Letters of Commitment (Attachment 4)

Applicants must submit the following letters of commitment. One or more sets of commitment letters from key project partners and match share contributors can be submitted per application, depending on if there are different partners and match share contributors for different charging stations. Site Control Documentation must be submitted for each EV charging station in the application. Applicants may elect to combine letters into one PDF or upload multiple files. Please ensure letters are labeled according to the respective station numbers in the Project Narrative.

  - Key Project Partners: Key project partners identified in the application must provide letters demonstrating their ability to fulfill their identified roles. Letters are limited to two (2) pages each.

  - Match Share Contributors Letters of Commitment: Any match share contributors (including the Applicant and/or a third-party) must identify the intended amount of match that will be committed to the project, the funding source(s), and state that the match share contributor will provide the identified match funding. Letters of commitment from match share contributors must contain a telephone number and email address to allow the CEC to contact the match share partner or representative to confirm their authority to commit matching funds to the proposed project. Letters are limited to two (2) pages each.

  - Site Control Documentation: Documentation explaining lease arrangements, ownership or access rights for each proposed site. Documentation may include but not be limited to: a lease, site host agreement, memorandum of understanding, letter of intent, or property deed. No page limit per document.

- Preliminary Site Plan (Attachment 5)

Applicants must submit a preliminary site plan for each EV charging station in the application.

The preliminary site plan must include the following at a minimum:

- Address of the EV charging station

- Map of the charging station showing the following:

  - Location of all existing charging ports at the charging station (if applicable). Specify the power delivery rate for each existing port (if applicable).

  - Location of all ports proposed to be installed. Specify the power delivery rating planned for each charging port.

  - Location of ADA accessible ports.

  - Location of lighting and shelter (if applicable).

  - Travel path (ingress/egress) from the charging station.

Applicants may elect to combine site plans into one PDF or upload multiple files.

- CEQA Worksheet (Attachment 6)

Applicants must complete one CEQA Worksheet (Attachment 6) for each EV charging station and submit these with their application. Please consolidate the CEQA Worksheets into one PDF if possible. CEC requires this information to assist it in making its own determination under the California Environmental Quality Act (Public Resources Code Section §§ 21000 et seq).

The worksheet(s) will help Applicants and CEC to determine CEQA compliance obligations by identifying which projects may require more extensive CEQA review, and it will be used to help evaluate the Project Readiness evaluation criterion in this solicitation (see Section IV.E.2). Failure to complete the worksheet(s) may lead to disqualification of the application.

Applicants are encouraged to provide documentation of communication with the local lead agency, if one exists (e.g., a county or city). Documentation may include a completed notice of exemption, a letter from the local agency acknowledging its role in the CEQA process, or a permit application to the lead agency that is stamped as received. If no CEQA review would be required by the local lead agency, provide documentation (e.g. a letter or e-mail) from the local agency explaining why CEQA review is not required.

- Additional Requirements

- Time is of the essence. Prior to approval of the agreement at a CEC business meeting, the CEC must comply with CEQA. To comply with CEQA, the CEC must have CEQA-related information from Applicants and sometimes other entities, such as local governments, in a timely manner. For example, if a project requires an Environmental Impact Report, the process to complete it can take many months. It is critical that Applicants organize project proposals in a manner that minimizes the time required for the CEC to comply with CEQA and provide all CEQA-related information to the CEC in a timely manner. Projects recommended for funding must complete the CEQA process within 6 months of the release date of the NOPA. The CEC reserves the right to cancel proposed awards that do not meet this CEQA deadline and recommend funding for the next ranked EV charging station for that Needed Location according to the evaluation process discussed in Section I.D. How Award is Determined.

- Reservation of right to cancel proposed award. In addition to any other right reserved to it under this solicitation or that it otherwise has, if the CEC determines, in its sole and absolute discretion, that the CEQA review associated with a proposed project would not likely be completed in a timely manner, or that the CEC’s ability to meet its encumbrance deadline may be jeopardized, the CEC may cancel a proposed award and award funds to the next-ranked EV charging station for that Needed Location according to the evaluation process discussed in Section I.D. How Award is Determined, regardless of the originally proposed Applicant’s diligence in submitting information and materials for CEQA review. Examples of situations that may arise related to CEQA review include but are not limited to:

    - Example 1: If another state agency or local jurisdiction, such as a city or county, must take the role of lead agency under CEQA, the CEC’s review may be delayed while waiting for a determination from the lead agency.

    - Example 2: If the proposed work is part of a larger project for which a detailed environmental analysis has been or will be prepared by another state agency or local jurisdiction, the CEC’s review may be delayed as a result of waiting for a supplemental or initial analysis, respectively, from the other agency.

    - Example 3: If the nature of the proposed work is such that a project is not categorically or otherwise exempt from the requirements of CEQA, and an initial study or other detailed environmental analysis appears to be necessary, the CEC’s review, or the lead agency’s review, may take longer than the time available to encumber the funds. If an initial study or environmental impact report has already been completed by another state agency or a local jurisdiction, serving as the lead agency, the Applicant must ensure that such an analysis covers the work in the proposed project, or must obtain a revised analysis and determination from the lead agency reviewing the proposed project.

    - Example 4: If the proposed project clearly falls under a statutory or categorical exemption or is a project for which another state agency or local jurisdiction has already adopted a CEQA finding that the project will cause no significant effect on the environment, the project will likely have greater success in attaining rapid completion of CEQA requirements.

- The above examples are not exhaustive of instances in which the CEC may or may not be able to comply with CEQA in a timely manner and are only provided as further clarification for potential applicants. Please plan project proposals accordingly.

- National Environmental Policy Act (NEPA) Preliminary Environmental Study (PES) Form (Attachment 7)

Applicants must complete to the best of their ability one NEPA PES form for each EV charging station in the application. Please consolidate them into one PDF if possible. This form will help Applicants, the CEC, and Caltrans determine NEPA compliance obligations.

If awarded under this solicitation, Applicants will have the opportunity to review and update this form before official submission to Caltrans for NEPA review.

Applicants should review Exhibit 6-B: Instructions for Completing the Preliminary Environmental Study (PES) Form found at https://dot.ca.gov/-/media/dot-media/programs/local-assistance/documents/lapm/c06/06b.pdf to complete the designated sections.

Applicants can ignore and leave blank the top of the first page that asks for the federal project number, “to” and “from” information, and FSTIP information. Begin completing the form at the “Detailed Project Description” section a little over halfway down the first page.

Applicants should prepare the required attachments listed on page 2 of the NEPA PES form. In particular, two attachments will be used to help evaluate the Project Readiness evaluation criteria in this solicitation (see Section IV.E.2):

- GeoTracker Printout for Hazardous Materials. For this attachment, use the State Water Resources Control Board Geo Tracker found at https://geotracker.waterboards.ca.gov/ to determine if any of the proposed EV charging station addresses are located within a 1,000-foot radius of any of the following:

  - Leaking Underground Storage Tank (LUST) Cleanup Site

  - Cleanup Program Site

  - Military Cleanup Site

  - Military Privatized Site

  - Military Underground Storage Tank (UST) site

Include two screenshots of the map search results with the NEPA PES Form (Attachment 7) for each proposed EV charging station:

- The first screenshot showing the address of the site with the 1,000-foot radius. After searching for the site address, the site will load with a box showing the address of the site and an option to create a radius. Enter 1,000 feet to create a radius around the address. Take a screenshot showing the address box with the number of feet and the radius around the site.

- For the second screenshot click the ‘X’ to close the address box to only show the radius around the site. Take a screenshot showing the full radius with any potential hazardous waste sites within.

- FEMA map. For this attachment, use the FEMA Flood Map Service Center at https://msc.fema.gov/portal/search to determine if any of the proposed EV charging station addresses are located in a Special Flood Hazard Area (SFHA). SFHAs are labeled as:

Zone A, Zone AO, Zone AH, Zones A1-A30, Zone AE, Zone A99, Zone AR, Zone AR/AE, Zone AR/AO, Zone AR/A1-A30, Zone AR/A, Zone V, Zone VE, and Zones V1-V30.

Include the address of the site and a screenshot of the map search results with the NEPA PES Form (Attachment 7) for each proposed EV charging station.

No signatures are needed on this form at the time of application.

Reservation of right to cancel proposed award. In addition to any other right reserved to it under this solicitation or that it otherwise has, if the CEC determines, in its sole and absolute discretion, that the NEPA review associated with a proposed project would not likely be completed in a timely manner, or that the CEC’s ability to meet its encumbrance deadline or any other NEVI-related deadline may thereby be jeopardized, the CEC may cancel a proposed award and award funds to the next-ranked EV charging station for that Needed Location according to the evaluation process discussed in Section I.D. How Award is Determined, regardless of the originally proposed Applicant’s diligence in submitting information and materials for NEPA review.

- Utility Verification Form (Attachment 8)

Applicants must complete a Utility Verification Form for each EV charging station in the application. Please consolidate them into one PDF if possible. These forms will be used to evaluate the level of readiness for each proposed charging station. Instructions for completing the Utility Verification Form are included in Attachment 8. Applicants may need assistance from the utility company serving the area where the proposed charging station is located to complete the form. If this is required, Applicants should contact the utility company as soon as possible to understand their timelines to complete the verification form.

- Resumes (Attachment 9)

Applicants must include resumes for key personnel identified in the proposal. “Key personnel” are individuals that are critical to the project due to their experience, knowledge, and/or capabilities. Resumes are limited to a maximum of 2 pages each, consolidated into one attachment.

- Contact List (Attachment 10)

Applicants must include a completed Contact List by including the appropriate points of contact for the Applicant. CEC will complete the CEC points of contact during agreement development.

- Past Performance Reference Form(s) (Attachment 11)

Applicants must complete and submit a separate Past Performance Reference Form for each CEC agreement (e.g., contract, grant, or loan) received by the Applicant in the last 10 years, including ongoing agreements, and the 5 most recent agreements with other public agencies within the past 10 years.

- Applicant Declaration (Attachment 12)

This form requests the Applicant declare that they: are not delinquent on taxes nor suspended by the California Franchise Tax Board; are not being sued by any public agency or entity; are in compliance with the terms of all settlement agreements, if any, entered into with the CEC or another public agency or entity; are in compliance with all judgments, if any, issued against the Applicant in any matter to which the CEC or another public agency or entity is a party; are complying with any demand letter made on the Applicant by the CEC or another public agency or entity; and are not in active litigation with the CEC regarding the Applicant’s actions under a current or past contract, grant, or loan with the CEC. The declaration must be signed under penalty of perjury by an authorized representative of the Applicant’s organization.

- Letters of Support (Attachment 13 - optional)

Applicants are encouraged to submit letter(s) of support that substantiate the estimated demand and/or the potential benefits of the proposed project. Third-party letters of support can be provided by, but are not limited to: air districts, state or federal agencies, local safety officials, potential users of the proposed project, community-based organizations, and any other relevant organizations. Letters are limited to two-pages each, consolidated into one attachment.

# IV.	Evaluation Process and Criteria

## Application Evaluation

Applications will be evaluated and scored based on the responses to the information requested in this solicitation and on any other information available such as past performance of CEC agreements. As discussed in Section I.G. of this Solicitation Manual, each EV charging station within an application will be evaluated, scored, and ranked individually. The entire evaluation process from receipt of applications to posting of the Notice of Proposed Award is confidential.

To evaluate applications, the CEC will organize an Evaluation Committee. The Evaluation Committee may consist of CEC staff or staff of other California state entities.

  - Screening Criteria

The CEC’s Contracts, Grants and Loans Office will screen applications for compliance with the Administrative Screening Criteria. The Evaluation Committee will screen applications for compliance with the Technical Screening criteria. Applications that fail any of the Administrative or Technical Screening Criteria shall be disqualified and eliminated from further evaluation.

  - Administrative Screening Criteria

| ADMINISTRATIVE Screening Criteria | Pass/Fail |
| --- | --- |
| - The application is received by the CEC by the due date and time specified in the “Key Activities Schedule” in Section I of this solicitation. | Pass Fail |
| - The Applicant has not included a statement that is contrary to the required authorizations and certifications when submitting in ECAMS. | Pass Fail |

  - Technical Screening Criteria

| Technical Screening Criteria | Pass/Fail |
| --- | --- |
| - The Applicant is an eligible Applicant. | Pass Fail |
| - The application proposes between one (1) and twenty (20) EV charging stations. | Pass Fail |
| - Each proposed EV charging station has between four (4) and twenty (20) CCS Type 1 ports, each supplying at least 150 kW. | Pass Fail |
| - The project meets the match share requirement of 20%. | Pass Fail |
| - The Applicant passes the past performance screening. | Pass Fail |

  - Applicant’s Past Performance Screening Criteria (Pass/Fail)

An Applicant may be disqualified under this solicitation due to severe performance issues under one or more prior or active CEC agreement(s) within the last 10 years. For the purposes of this screening criterion an Applicant is defined as either (a) an entity, principal investigator, or lead individual acting on behalf of themselves, that received funds from the CEC (e.g. a contract, grant, or loan) and entered into an agreement(s) with the CEC; or (b) an entity, principal investigator, or lead individual that received a CEC-funded incentive. Any Applicant that does not have an active or prior agreement and has not received a CEC-funded incentive equates to no severe performance issues and therefore would pass this screening criterion.

Severe performance issues are characterized by significant negative outcomes under an agreement and may include:

  - Agreement was terminated with cause.

  - CEC filed litigation against the Applicant.

  - Severe audit findings are not resolved to CEC’s satisfaction. Severe audit findings may include but are not limited to: incomplete or unsatisfactory deliverables; grant funds used inappropriately (i.e., other than as represented); or questioned costs.

  - Project objectives were not met.

  - Significant delays in project completion resulting in delayed benefits for California. Project completion delays of one year or more from the originally proposed project schedule and caused by factors within the Applicant’s control may be considered significant.

  - Deliverables were not submitted to the CEC or were of poor quality. For example, Applicant delivered poorly written reports that required significant rework by staff prior to acceptance or publication.

  - Demonstrated poor or delayed communication when significant issues or setbacks were experienced that materially and negatively impacted the project. For example, delays in informing the CEC when the Applicant experiences loss of a key project partner or site control may be considered significant.

  - Grounds to Reject an Application or Cancel an Award

In addition to the Screening Criteria identified within this solicitation, CEC reserves the right to reject an application and/or cancel an award for reasons including, but not limited to the following:

- The application contains false or intentionally misleading statements or references which do not support an attribute or condition contended by the Applicant.

- The application is intended to erroneously and fallaciously mislead the State in its evaluation of the application and the attribute, condition, or capability is a requirement of this solicitation.

- The application does not comply or contains caveats that conflict with the solicitation and the variation or deviation is material, or it is otherwise non-responsive.

- The CEC, in its sole discretion, determines the Applicant’s, a subrecipient’s, or a vendor’s financial condition may materially impact its ability to complete the proposed project.

  - Technical Evaluation

Applications passing all screening criteria will be submitted to the Evaluation Committee to review and score based on the Evaluation Criteria using the Scoring Scale described below. The Evaluation Committee will use the Evaluation Criteria to individually score each EV charging station proposed within each application.

The Evaluation Committee reserves the right to schedule a clarification interview with an Applicant to clarify and/or verify information submitted in the application. However, these interviews may not be used to change or add to the contents of the original application. Applicants will not be reimbursed for time spent answering and clarifying questions.

The total score for each EV charging station will be the average of the combined scores of all Evaluation Committee members. A minimum score of 70 percent is required for the EV charging station to be eligible to advance to Cost Evaluation. In addition, a minimum score of 70 percent is required on both Technical Evaluation Criterion 2, Project Readiness, and Technical Evaluation Criterion 4, Project Budget and Finances, to advance to Cost Evaluation.

  - Cost Evaluation

All EV charging stations in an application that have passed screening and receive the minimum passing score of 70 percent or higher in the Technical Evaluation portion of scoring (both overall and for Technical Evaluation Criterion 2 and 4 individually) as described in the previous sections will advance to Cost Evaluation. Advancement to Cost Evaluation signifies that the EV charging station meets the minimum threshold for funding eligibility. The Evaluation Committee will then perform a cost-efficiency calculation to rank charging stations for award by Needed Location.

The Cost Evaluation and ranking process are discussed in Section IV.F. Tiebreakers are discussed in Section IV.G.

## Notice of Proposed Awards

The results of the evaluation will be posted in a Notice of Proposed Awards (NOPA) and will include (1) the total proposed funding amount; (2) the rank order of Applicants; and (3) the amount of each proposed award. CEC will publish the NOPA on the CEC’s website.

## Debriefings

Applicants that are not proposed for funding may request a debriefing after the release of the NOPA by e-mailing the CAO listed in Part I. A request for debriefing should be received no later than 15 calendar days after the NOPA is released.

## Scoring Scale

Using this Scoring Scale, the Evaluation Committee will give a score for each criterion described in the Evaluation Criteria.

| % of Possible Points | Interpretation | Explanation for Percentage Points |
| --- | --- | --- |
| 0% | Not Responsive | Response does not include or fails to address the requirements being scored. The omission(s), flaw(s), or defect(s) are significant and unacceptable. |
| 10-30% | Minimally Responsive | Response minimally addresses the requirements being scored. The omission(s), flaw(s), or defect(s) are significant and unacceptable. |
| 40-60% | Inadequate | Response addresses the requirements being scored, but there are one or more omissions, flaws, or defects or the requirements are addressed in such a limited way that it results in a low degree of confidence in the proposed solution. |
| 70% | Adequate | Response adequately addresses the requirements being scored. Any omission(s), flaw(s), or defect(s) are inconsequential and acceptable. |
| 75% | Between Adequate and Good | Response better than adequately addresses the requirements being scored. Any omission(s), flaw(s), or defect(s) are inconsequential and acceptable. |
| 80% | Good | Response fully addresses the requirements being scored with a good degree of confidence in the Applicant’s response or proposed solution. No identified omission(s), flaw(s), or defect(s). Any identified weaknesses are minimal, inconsequential, and acceptable. |
| 85% | Between Good and Excellent | Response fully addresses the requirements being scored with a better than good degree of confidence in the Applicant’s response or proposed solution. No identified omission(s), flaw(s), or defect(s). Any identified weaknesses are minimal, inconsequential, and acceptable. |
| 90% | Excellent | Response fully addresses the requirements being scored with a high degree of confidence in the Applicant’s response or proposed solution. Applicants offer one or more enhancing features, methods or approaches exceeding basic expectations. |
| 95% | Between Excellent and Exceptional | Response fully addresses the requirements being scored with a better than excellent degree of confidence in the Applicant’s response or proposed solution. Applicants offer one or more enhancing features, methods or approaches exceeding basic expectations. |
| 100% | Exceptional | All requirements are addressed with the highest degree of confidence in the Applicant’s response or proposed solution. The response exceeds the requirements in providing multiple enhancing features, a creative approach, or an exceptional solution. |

## Technical Evaluation Criteria

| Criterion | Possible Points |
| --- | --- |
| - EV Charging Station Siting and Equipment Each EV charging station within an application will be evaluated separately on the degree to which: - The justification for the proposed EV charging station location is compelling and will effectively serve customers traveling within a Needed Location identified in Table 1. - The proposed EV charging station location will be easily accessible from the Alternative Fuel Corridor and within one mile or closer of an exit (either an off-ramp or corridor exit point) and is verified using a distance measuring tool. - The proposed EV charging station site design has the customer experience in mind, including appropriate lighting, shelter, and stall configurations to support a variety of customer needs. Narrative is supported by and consistent with Preliminary Site Plan(s) (Attachment 5). - The proposed EV charging station has nearby amenities including restrooms, retail shops, restaurants, parks, pet relief areas, or other positive attributes. - The type of charging equipment, number of charging ports, and types of connectors chosen are justified with clear reasoning based on expected customer needs. - The proposed EV charging station will provide more than the minimum four (4) CCS ports. - The charging ports at the proposed EV charging station will be guaranteed to supply vehicles with at least 150 kW simultaneously. - The grid connection and its capacity, and other renewable DER equipment, such as solar arrays and BESS, will provide reliable power supply to the proposed EV charging station. Any renewable DER equipment will deliver benefits such as reduced costs to customers and improved station reliability and will not substantially increase the project timeline. | 10 |
| - Project Readiness Each EV charging station within an application will be evaluated separately on the degree to which: - Documentation (included in Attachment 4, Letters of Commitment) demonstrates site control or access rights for the proposed EV charging station property. If control or access rights are not secured for the station site at the time of application, there is a credible and expedited plan for securing control or access rights. - The owner and operator of the proposed EV charging station and its equipment are clearly identified and ready to assume those responsibilities. - Due diligence has been conducted for the proposed EV charging station site, including research into the site’s zoning and progress made in obtaining needed planning approvals and permits. - Progress has been made in obtaining a CEQA determination for the proposed EV charging station, from outreach to the local authority having jurisdiction up to actual receipt of a notice of exemption or a determination that no CEQA review is required. Supporting information to be provided in the CEQA Worksheet (Attachment 6). - The proposed EV charging station site is not in Special Flood Hazard Areas (SFHA) and does not have open cleanup cases within a 1,000-foot radius. Supporting documentation to be provided in the NEPA PES Form (Attachment 7). - There is available electrical capacity enabling timely station electrification, supported by a completed Utility Verification Form (Attachment 8). - The timeline for obtaining chargers and other proposed equipment is minimized and supported by verifiable documentation from the manufacturer(s). NOTE: Project Readiness must obtain a minimum passing score of 21 points (70 percent) within this evaluation criterion to be eligible for funding. | 30 |
| - Expected Project Benefits Each EV charging station within an application will be evaluated separately on the degree to which: - The cost to charge for drivers will be minimized, with methods and assumptions explained. - The EV charger deployment will benefit EV drivers and accelerate EV adoption, in terms of expanding public charger availability, increasing EV charging capacity, and serving local EV charging needs. - The project will bring economic benefits to the local communities surrounding the proposed station site. - There is a credible plan to meet or exceed the solicitation’s goal of 25 percent small business participation. | 10 |
| - Project Budget and Finances Each EV charging station within an application will be evaluated separately on the degree to which: - The proposed project’s budget is cost effective and reasonable relative to the Scope of Work and expected benefits to California. Explain budget differences between stations, if applicable. - The Cost-per-CCS-Port for the station is minimized and justified for the proposed power level. - The total allowable project cost per kW of EV charging capacity proposed for the station is minimized. - Income or revenue earned from the operation of the proposed EV charging station will be used in compliance with the federal NEVI standards under 23 CFR 680.106(m), (which require use for debt service, a reasonable return on investment, and/or costs for operation, maintenance, and site improvement) and there is a method in place for documenting compliance during the project. - Match funding commitments are supported by verifiable documentation. NOTE: Project Budget and Finance must obtain a minimum passing score of 21 points (70 percent) within this evaluation criterion to be eligible for funding. | 30 |
| - Operations and Maintenance Plan Each EV charging station within an application will be evaluated separately on the degree to which: - The operations and maintenance (O&M) plan demonstrate an overall ability to achieve an average annual uptime of greater than 97 percent per port. - The O&M plan demonstrates strategies to physically secure the station site effectively and limit or prevent tampering with or damage to the chargers. - The O&M plan outlines strategies and timelines to provide prompt attention to chargers that are not operational and demonstrates an ability to carry out repairs to maximize uptime. - The O&M plan outlines the availability of site host training and describes the responsibilities of the site host in conducting O&M. - The O&M plan clearly outlines who is responsible for maintaining the charging station, including all the charging equipment, auxiliary equipment, and applicable supporting elements, such as lighting and restrooms. - The Applicant commits to continuing the EV charging station’s operation beyond the agreement term and minimum five-year operation, maintenance, and data reporting period. | 10 |
| - Team Experience and Qualifications Each EV charging station within an application will be evaluated separately on the degree to which: - The key personnel assigned to complete the EV charging station project, including the project manager, and their areas of responsibility are clearly identified. - The Applicant or lead installation Subrecipient(s) from the proposed project team meet(s) or exceed(s) the Experienced Contractor definition. - The Applicant’s selected charging station network provider has demonstrated experience keeping chargers in service for at least five years. - The Applicant demonstrates experience with federally funded projects and compliance with federal requirements like the Davis Bacon Act. - The Applicant demonstrates experience meeting deadlines and completing milestones associated with large, complex public projects, including previously successful EV charging projects. Use past performance forms (Attachment 11) to document experience. | 10 |
| Total Possible Points | 100 |
| Minimum Passing Score (70%) | 70 |

## Cost Evaluation

All proposed EV charging stations scoring 70% or higher on the Technical Evaluation Criteria from Section IV.E. (both overall and for Technical Evaluation Criterion 2, Project Readiness, and Technical Evaluation Criterion 4, Project Budget and Finances) will move on to the Cost Evaluation phase. During the Cost Evaluation, EV charging stations will be ranked in ascending order within their respective Needed Location based on the Cost-per-CCS-Port of the station. Stations with the lowest Cost-per-CCS-Port within their respective Needed Location will be recommended for funding first, as described in full in Section I.D. How Award is Determined.

The Cost-per-CCS-Port is calculated by dividing the total CEC grant dollars requested for the station by the number of ports with a CCS connector proposed to be installed at the station. For example, if the total grant funding request for the station is $2,000,000, and the number of ports to be installed is 20, the Cost-per-CCS-Port would be $100,000 for that station. The total grant funding request includes all CEC reimbursable costs associated with the capital expenditure required for the CCS charging port. This includes, but is not limited to, administrative, design, installation, operations and maintenance, and equipment costs.

As explained in Section II.B. Project Requirements, each proposed EV charging station must have a minimum of four (4) CCS charging ports and a maximum of twenty (20) CCS charging ports for reimbursable funding under this solicitation, each supplying at least 150 kilowatts (kW). (An applicant may choose to install additional charging ports at that station, separate from any agreement with the CEC.)

Applicants may propose stations with DCFC chargers that include both CCS and SAE J3400 connectors, either on the same port, or on separate ports of a dual port charger. The costs associated with planning for, purchasing, installing, and operating chargers that include both CCS and SAE J3400 connectors are eligible project costs for both reimbursable and match share expenses. However, only the number of CCS ports will be counted in Cost Evaluation.

If a proposed EV charging station includes chargers with only SAE J3400 connectors, and no CCS connectors, those chargers will be considered to be outside the grant-funded project and are not eligible project costs for either reimbursement or match share expenses and are not included in Cost Evaluation.

The following are some examples to explain eligible and ineligible project costs for chargers with different port and connector configurations, and how the Cost-per-CCS-Port will be calculated.

  - The proposed project has eight single-port chargers, and each port on each charger has both CCS and SAE J3400 connectors. All eight chargers are eligible project costs for which grant funding may be requested. The number of CCS ports used in Cost Evaluation is eight.

  - The proposed project has four dual-port chargers, and each charger has one port with a CCS connector and one port with an SAE J3400 connector. All four chargers are eligible project costs for which grant funding may be requested. The number of CCS charging ports used in Cost Evaluation is four.

  - The proposed project has four single-port chargers with a CCS connector on each port and four single-port chargers with an SAE J3400 connector on each port. Only the four chargers with CCS connectors are eligible project costs for which grant funding may be requested. No grant funding may be requested for the chargers with only SAE J3400 connectors. The number of CCS charging ports used in Cost Evaluation is four.

## Tie Breakers

If the Cost-per-CCS-Port is the same for two or more EV charging stations for the same Needed Location, the application with the EV charging station with the higher score in Technical Evaluation will be ranked higher. If still tied, the charging station with a higher score in the Project Readiness criterion will be ranked higher. If still tied, an objective tiebreaker (such as a random drawing) will be utilized. Similarly, if one Applicant has proposed awards exceeding the applicant award cap, this same process will be used to determine which stations are proposed for award.

# V.	Administration

## Definition of Key Words

Important definitions for this solicitation are presented below:

| Word/Term | Definition |
| --- | --- |
| ADA | Americans with Disabilities Act |
| Alternative Fuel Corridor | AFC. In accordance with 23 U.S.C. 151, FHWA has designated alternative fuel corridors to support installation of EV charging, hydrogen, propane, and natural gas fueling infrastructure at strategic locations along major national highways. For the purposes of this solicitation, AFCs refer to those designated for the installation of EV charging infrastructure. |
| API | Application Programming Interface. A type of software interface that offers service to other pieces of software. An API allows two or more computer programs to communicate with each other. |
| Applicant | Respondent to this solicitation |
| Application | Formal written response to this document from applicant |
| BESS | Battery Energy Storage System |
| California Native American Tribe | A Native American tribe located in California that is on the contact list maintained by the Native American Heritage Commission for the purposes of Chapter 905 of the Statutes of 2004. |
| California Tribal Organization serving a California Native American Tribe | A corporation, association, or group controlled, sanctioned, or chartered by a California Native American Tribe that is subject to its laws, the laws of the State of California, or the laws of the United States. |
| Caltrans | California Department of Transportation |
| CAM | Commission Agreement Manager |
| CAO | Commission Agreement Officer |
| CCS | Combined Charging System. A charging port standard for fast charging of EVs that can provide up to 350 kilowatts of power. |
| CEC | California Energy Commission |
| CEQA | California Environmental Quality Act |
| CHAdeMO | A charging port standard for fast charging of EVs. |
| Charger | A device with one or more charging ports and connectors for charging EVs. Also referred to as electric vehicle supply equipment (EVSE). |
| Charging Network | A collection of chargers located on one or more property(ies) that are connected via digital communications to manage the facilitation of payment, the facilitation of electrical charging, and any related data requests. |
| Charging Network Provider | The entity that operates the digital communication network that remotely manages the chargers. Charging network providers may also serve as charging station operators and/or manufacture chargers. |
| Charging Port | The system within a charger that charges one EV. A charging port may have multiple connectors, but it can provide power to charge only one EV through one connector at a time. May also be referred to as “port.” |
| Charging Session | The period after a charge attempt during which the EV is allowed to request energy. Charging sessions can be terminated by the customer, the EV, the charger, the charging station operator, or the charging network provider. |
| Charging Station Operator | The entity that owns the chargers and supporting equipment and facilities at one or more charging stations. Although this entity may delegate responsibility for certain aspects of charging station operation and maintenance to subrecipients or vendors, this entity retains responsibility for operation and maintenance of chargers and supporting equipment and facilities. In some cases, the charging station operator and the charging network provider are the same entity. |
| Connector | The device that attaches an EV to a charging port to transfer electricity. |
| Corridor Group | A group of one or more corridor segments. Under the NEVI formula program, 23 Corridor Groups are defined from the designated Alternative Fuel Corridors. |
| Corridor Segment | A portion of a highway corridor that is part of a Corridor Group. Under the NEVI formula program, defined by a letter, A through E. |
| DCFC | Direct Current Fast Charger. Equipment that provides charging through a direct-current plug, typically at a rate of 50 kilowatts or higher. |
| DER | Distributed Energy Resource. Small, modular, energy generation and storage technologies that provide electric capacity or energy where it is needed. |
| E-76 | E-76 is the federal-aid authorization to proceed process. A Project Authorization/Adjustment Request Form (DOT LAPM 3-A, found at https://forms.dot.ca.gov/v2Forms/servlet/FormRenderer?frmid=DOTLAPM3A) is used to request FHWA authorization to begin reimbursable work for a specific project phase, such as construction. FHWA authorization or “E-76 approval” means the request to begin work is approved and establishes the date from which reimbursable work may begin. |
| EV | Electric Vehicle. A motor vehicle that is either partially or fully powered on electric power received from an external power source. In the NEVI regulation, EVs do not include golf carts, electric bicycles, or other micromobility devices. |
| EV Charging Station | The area in the immediate vicinity of one or more chargers and includes the chargers, supporting equipment, parking areas adjacent to the chargers, and lanes for vehicle ingress and egress. An EV charging station could comprise only part of the property on which it is located. Multiple chargers may be associated with one EV charging station. EV charging stations may also be referred to as “charging stations” or “stations.” |
| EVITP | The Electric Vehicle Infrastructure Training Program. EVITP provides training and certification for electricians installing EVSE. |
| EVSE | Electric Vehicle Supply Equipment. A “charger” as defined. |
| Experienced Contractor | A company or organization with a proven record of accomplishment in overseeing the procurement, permitting, and installation of at least 20 DCFCs. The company or organization must have completed installations at three or more different property locations for three or more different customers since January 1, 2018. |
| FHWA | U.S. Department of Transportation, Federal Highway Administration |
| GAAP | Generally Accepted Accounting Principles |
| Hardware | The machines, wiring, and other physical components of an electronic system including onboard computers and controllers. |
| Installed | Attached or placed at a location and available for use for a charging session. The date the charger is installed is the date it is first available for use for a charging session. |
| kW | Kilowatt |
| LAPM | Caltrans Local Assistance Procedures Manual |
| Level 1 Charger | A charger that operates on a circuit from 110 volts to 120 volts and transfers alternating current (AC) electricity to a device in an EV that converts AC to direct current (DC) to charge an EV battery. |
| Level 2 Charger | A charger that operates on a circuit from 208 volts to 240 volts and transfers AC electricity to a device in an EV that converts AC to DC to charge an EV battery. |
| Maintenance | Any instance in which preventive or corrective maintenance is carried out on equipment. |
| Needed Location | A section of a Corridor Segment, as defined for the NEVI formula program, where an EV charging station is needed to satisfy build-out of the Alternative Fuel Corridor. |
| NEPA | National Environmental Policy Act |
| Networked | A charger that can receive or send commands or messages remotely from or to a charging network provider or is otherwise connected to a central management system, such as by using OCPP 2.0.1, for the purposes of charger management and data reporting. |
| NEVI Formula Program | National Electric Vehicle Infrastructure Formula Program |
| NEVI Standards | Refers to the National Electric Vehicle Infrastructure Standards and Requirements, Final Rule, Code of Federal Regulations Section 23, Part 680 (23 CFR 680). See Section I.O. Reference Documents for the web link. |
| OCPI | Open Charge Point Interface. An open-source communication protocol that governs the communication among multiple charging networks, other communication networks, and software applications to provide information and services for EV drivers. |
| OCPP | Open Charge Point Protocol. An open-source communication protocol that governs the communication between chargers and the charging networks that remotely manage the chargers. |
| Operational | A charging port’s hardware and software are both online and available to use, or in use, and the charging port is capable of successfully dispensing electricity. |
| Preventative Maintenance | Maintenance that is performed on physical assets to reduce the chances of equipment failure and unplanned machine downtime. |
| Recipient | An applicant awarded a grant under a CEC solicitation. Please note that in FHWA documents, the definition of “recipient” may differ. |
| RSA | Registered Service Agency. An entity that repairs a commercial device that is registered with the California Department of Food and Agriculture Division of Measurement Standards. |
| SAE J3400 | A charging port standard for charging of EVs based on the North American Charging Standard (NACS) connector. |
| SFHA | Special Flood Hazard Area |
| Small Business | Please refer to California Government Code §14837 (d)(1)(A)-(B). “Small business” means an independently owned and operated business that is not dominant in its field of operation, the principal office of which is located in California, the officers of which are domiciled in California, and which, together with affiliates, has 100 or fewer employees, and average annual gross receipts of $15 million dollars or less over the previous three years, or is a manufacturer, as defined in subdivision (c), with 100 or fewer employees. For the purposes of public works contracts, as defined in Section 1101 of the Public Contract Code, and engineering contracts, as described in Section 4525, for public works projects, awarded through competitive bids or otherwise, “small business” means an independently owned and operated business that is not dominant in its field of operation, the principal office of which is located in California, the officers of which are domiciled in California, and which, together with affiliates, has 200 or fewer employees, and average annual gross receipts of $36 million dollars or less over the previous three years. |
| Software | A set of instructions, data, or programs used to operate computers and execute specific tasks. |
| Solicitation | Grant Funding Opportunity, which refers to this entire solicitation document and all its attachments and exhibits. |
| State | State of California |
| Subaward | For the Recipient, a subaward means all agreements it has with subrecipients and vendors. For a subrecipient, a subaward means all agreements it has with sub-subrecipients and vendors. For any lower-tiered level of sub-subrecipient, a subaward means all agreements it has with its own sub-subrecipients and vendors. |
| Subrecipient | A person or entity that receives grant funds directly from the Recipient and is entrusted by the Recipient to make decisions about how to conduct some of the grant’s activities. A Subrecipient’s role involves discretion over grant activities and is not merely just selling goods or services. |
| Uptime | The time that a charging port is online and available for use per the formula in the Scope of Work (Attachment 14). |
| Vendor | A person or entity that sells goods or services to the Recipient, subrecipient, or any lower-tiered level of sub-subrecipient, in exchange for some of the grant funds, and does not make decisions about how to perform the grant’s activities. The vendor’s role is ministerial and does not involve discretion over grant activities. |

## Cost of Developing Application

The Applicant is responsible for the cost of developing an application, and this cost cannot be charged to the State.

## Confidential Information

The Applicant shall not submit any confidential information as part of its application. All information submitted in an application will be considered and treated as non-confidential information that is subject to disclosure under the Public Records Act (Gov. Code § 7920.000 et seq.).

## Solicitation Cancellation and Amendments

It is CEC’s policy not to solicit applications unless there is a bona fide intention to award an agreement. However, if it is in the State’s best interest, CEC reserves the right, in addition to any other rights it has, to do any of the following:

- Cancel this solicitation;

- Revise the amount of funds available under this solicitation;

- Amend this solicitation as needed; and/or

- Reject any or all applications received in response to this solicitation.

If the solicitation is amended, CEC will post an addendum on CEC’s solicitation information website at www.energy.ca.gov/funding-opportunities/solicitations.

## Errors

If an Applicant discovers any ambiguity, conflict, discrepancy, omission, or other error in the solicitation at any time prior to 5:00 p.m. of the application deadline date, the Applicant should immediately notify CEC of the error in writing and request modification or clarification of the solicitation. The CEC will provide modifications or clarifications by written notice to all entities that requested the solicitation, without divulging the source of the request for clarification. The CEC shall not be responsible for failure to correct errors.

## Modifying or Recalling an Application

An Applicant may recall or modify a submitted application within ECAMS before the deadline to submit applications. Applications cannot be changed after that date and time. An application cannot be “timed” to expire on a specific date. For example, a statement such as the following is non-responsive to the solicitation: “This application and the cost estimate are valid for 60 days.”

## Immaterial Defect

The CEC may waive any immaterial defect or deviation contained in an Applicant’s application. CEC’s waiver shall in no way modify the application or excuse an Applicant proposed for funding from full compliance with solicitation requirements.

## Opportunity to Cure Administrative Errors

The CEC understands and appreciates the significant time and expense Applicants spend preparing applications. An administrative error that prevents an Applicant from submitting a complete application frustrates both the CEC and Applicants. The purpose of this process is to reduce the number of applications screened out or receiving a significantly reduced score for administrative errors while maintaining a fair competition. This process also ensures better competition and thus better projects to benefit California.

After the application deadline, an Applicant might identify, or the Evaluation Committee may find what reasonably appears to be, an administrative error. For purposes of this solicitation only, an administrative error is defined as an Applicant’s inadvertent mistake that prevents materials in existence as of the application deadline from appearing in its submitted application. Examples include, but are not limited to, accidentally:

- Scanning and submitting every other page in a document instead of every page.

- Submitting the wrong document.

- Leaving out a document.

If the Evaluation Committee find what reasonably appears to be an administrative error, they can communicate with the Applicant to confirm. If an Applicant finds an administrative error in its application, it should immediately contact the Commission Agreement Officer listed in the “Contact Information” section of this solicitation.

If an administrative error has been identified and communicated to the Commission Agreement Officer, the CEC may, but is not required to, allow the Applicant a period of time to provide the missing materials. Reasons why the CEC might NOT allow an Applicant to fix an administrative error include, but are not limited to:

- The funds have a deadline that does not allow time to fix the error.

- The application has been screened out or does not receive a passing score for reasons unrelated to the administrative error, making irrelevant any efforts to fix the error.

- The Applicant brings the error to the CEC’s attention too late in the solicitation process (e.g., after awards have been approved at a Business Meeting).

If the Evaluation Committee allows an Applicant the opportunity to fix an administrative error, the Commission Agreement Officer will communicate in writing to the Applicant’s project manager listed the deadline by which the Applicant must provide the missing materials. Reasonable efforts will be made to confirm receipt of the notice, but actual notice cannot be guaranteed, and the obligation is on the Applicant to ensure the proper contact(s) are listed and available to respond. The Evaluation Committee will not consider any materials submitted after the deadline.

This process only allows Applicants to submit materials in existence as of the application deadline. This process does NOT allow Applicants to submit material created or modified after the application deadline. The CEC has sole discretion to determine whether materials submitted are eligible for consideration by the Evaluation Committee under this opportunity to cure.

Applicants must include the following certification along with the materials it submits to fix an administrative error and must explain why the materials were not provided due to an inadvertent administrative error:

“I certify on behalf of the Applicant that the materials provided herein existed at the time of the application deadline, have not been modified since, and were not originally provided due to an inadvertent administrative error as described herein.”

The Evaluation Committee is not responsible for finding, or communicating with the Applicant about, any errors in an application. Applicants remain solely responsible for submitting applications, including any material submitted to fix an administrative error, that meet all solicitation requirements.

## Disposition of Applicant’s Documents

The entire evaluation process from receipt of applications up to the posting of the Notice of Proposed Award is confidential. On the Notice of Proposed Award posting date, or date of solicitation cancellation, all applications and related material submitted in response to this solicitation become a part of the property of the State and public record.

## Applicants’ Admonishment

This solicitation contains the instructions governing the requirements for a firm quotation to be submitted by interested Applicants, the format in which the technical information is to be submitted, the material to be included, the requirements which must be met to be eligible for consideration, and applicant responsibilities. Applicants are responsible for carefully reading the entire solicitation, asking appropriate questions in a timely manner, submitting all required responses in a complete manner by the required date and time, and making sure that all procedures and requirements of the solicitation are followed and appropriately addressed.

## Agreement Requirements

The content of this solicitation shall be incorporated by reference into the final agreement. See the sample agreement terms and conditions: the NEVI Standard terms and conditions, found at https://www.energy.ca.gov/sites/default/files/2025-09/NEVI_Standard_Terms_ADA.pdf, the NEVI Special Federal terms and conditions, found at https://www.energy.ca.gov/sites/default/files/2025-09/NEVI_Special_Federal_Terms_ADA.pdf. Final agreements with Recipients that are a California Tribal Organization serving a California Native American Tribe shall also have the Special Terms and Conditions for California Tribal Organizations with Sovereign Immunity serving California Native American Tribes with Sovereign Immunity, found at https://www.energy.ca.gov/media/12259.

CEC reserves the right to negotiate with Applicants to modify the project scope, the level of funding, or both. If CEC is unable to successfully negotiate and execute a funding agreement with an Applicant, CEC, at its sole discretion, reserves the right to cancel the pending award for an EV charging station and fund the next ranked EV charging station for that Needed Location according to the evaluation process discussed in Section I.D. How Award is Determined.

If proposed for an award, the CEC reserves the right to request information it deems appropriate to evaluate the financial condition of a proposed awardee, subrecipients, and vendors prior to approval of a grant award. If CEC, in its sole discretion, determines that a proposed awardee’s, a subrecipient’s, or a vendor’s financial condition may materially impact its ability to complete the proposed project, CEC reserves the right to cancel the proposed award.

CEC must formally approve all proposed grant awards. Grant agreements must be scheduled and considered at a CEC Business Meeting for approval by the CEC.

CEC will send the approved agreement, including the NEVI terms and conditions, Special Federal Award terms and conditions, and any additional terms and conditions to the grant recipient for review, approval, and signature. Once the grant recipient signs, CEC will fully execute the agreement. Recipients are approved to begin the project only after full execution of the agreement, including any authorizations needed from the FHWA.

## No Agreement Until Signed and Approved

No agreement between CEC and an Applicant is in effect until the agreement is approved at a CEC Business Meeting and signed by both the grant recipient and the CEC.

CEC reserves the right to modify the award documents prior to executing the agreement.

## Executive Order N-6-22 – Russia Sanctions

On March 4, 2022, Governor Gavin Newsom issued Executive Order N-6-22 (the EO) regarding Economic Sanctions against Russia and Russian entities and
individuals. “Economic Sanctions” refers to sanctions imposed by the U.S.
government in response to Russia’s actions in Ukraine, as well as any sanctions
imposed under state law. By submitting a bid or proposal, Applicant represents
that it is not a target of Economic Sanctions. Should the State determine
Applicant is a target of Economic Sanctions or is conducting prohibited
transactions with sanctioned individuals or entities, that shall be grounds for
rejection of the Applicant’s bid/proposal any time prior to agreement execution, or, if determined after agreement execution, shall be grounds for termination by the State.

National Electric Vehicle Infrastructure Standards and Requirements. https://www.federalregister.gov/documents/2023/02/28/2023-03500/national-electric-vehicle-infrastructure-standards-and-requirements.

Caltrans. California Manual on Uniform Traffic Control Devices. https://dot.ca.gov/programs/safety-programs/camutcd.

A directional sign displayed, usually with an arrow panel, off the freeway system to advise motorists where to turn en route to a destination.

“Commercial” in this context applies to “operations in which the amount dispensed affects customer charges or compensation” https://www.cdfa.ca.gov/dms/docs/publications/2024/2024_Combined_FRM.pdf.

The Past Performance Evaluation is available on the CEC website at: https://www.energy.ca.gov/media/6595