December 26, 2025

GFO-24-610

Medium- and Heavy-Duty Zero-Emission Vehicle Port Infrastructure

Addendum 7

The purpose of this addendum is to notify potential applicants of changes that have been made to GFO-24-610.

The addendum includes the following revisions to the Questions and Answers. Added language appears in bold underline, and deleted language appears in [strikethrough] and within square brackets.

## Questions and Answers

- Q65:	Our infrastructure project might take longer to complete than the time it takes for vehicles or off-road equipment to be delivered. If the solicitation requires us to place a purchase order within three months of executing the grant agreement, how can we prevent vehicles from arriving before the charging or hydrogen infrastructure is ready and sitting idle? Can we place purchase orders after the three months?

A65:	While the CEC reserves the right to cancel a grant agreement award if the Applicant cannot place a purchase order within three months, the application will be scored on the degree to which the proposed project is ready for implementation and capable of maximizing zero-emission vehicle deployment. This includes demonstrating how the project will expedite infrastructure installation, ensure timely vehicle utilization, and address potential timing challenges through coordination with utilities and planning agencies. If placing a purchase order within three months of agreement execution is not feasible, the Applicant should provide a clear, detailed timeline and plan for vehicle acquisition, including strategies to minimize delays and align delivery with infrastructure readiness. Applicants whose infrastructure will provide Public Access are not required to meet the three-month purchase order requirement.

Q66:	The solicitation requires that vehicles be delivered by the time the infrastructure becomes energized and operational. However, ports and their partners have limited control over vehicle and off-road equipment delivery timelines, as most acquisitions are through the EPA Clean Ports Program. Given that this program’s requirements are expected to strain supply and manufacturing capacity, how should Applicants address this requirement in their proposal?

A66:	Applicants must demonstrate that vehicles will be deployed and actively utilizing the funded infrastructure for at least 12 months before grant agreement end date. While the solicitation requires vehicles to be delivered by the time the infrastructure becomes energized and operational, the CEC recognizes that delivery timelines may be influenced by external factors such as the EPA Clean Ports Program and associated supply chain constraints. Project timelines should account for potential delays and include at least 12 months of data collection following commissioning to demonstrate successful utilization of the infrastructure. The application will be scored on the degree to which the estimated timeline for acquisition of new MDHD ZEVs and the purchase and installation of supporting infrastructure can be expedited. It will also be scored on the degree to which the tasks in the Scope of Work and the dates in the project schedule are complete, sequential, and will lead to successful and scheduled completion of the project.

Q67:	The solicitation manual states that Applicants may begin the project only after full execution of the agreement. Can these requirements be changed to allow projects to begin after the Notice of Proposed Awards (NOPA) is released to allow for earlier procurement of equipment and materials?

A67:	Under the Greenhouse Gas Reduction Fund (GGRF) which funds this grant solicitation, any work or procurement that occurs prior to full execution of the grant agreement is not eligible for reimbursement or match funding. This means that costs incurred before the agreement is executed cannot be counted toward the required match share or reimbursed by the CEC. However, this does not prohibit Applicants from beginning work at their own risk before the agreement is executed. To remain eligible, the project must meet the minimum deployment requirements for charging ports or hydrogen fueling positions during the term of the executed agreement. In other words, the construction and installation of the minimum required infrastructure must occur after the agreement is executed. The minimum match share required is 25%, and there is no cash match requirement.

Natalie Johnson

Commission Agreement Officer