GRANT FUNDING OPPORTUNITY

California’s National Electric Vehicle Infrastructure Formula Program - Solicitation 5

(South)

GFO-25-606

Solicitation Information

https://www.energy.ca.gov/funding-opportunities/solicitations

State of California

California Energy Commission

February 2026

##### Table of Contents

I.	Introduction	5

A.	Purpose of Solicitation	5

B.	Background	5

C.	Key Activities and Dates	5

D.	How Award Is Determined	6

E.	Availability of Funds	8

F.	Minimum and Maximum Award Amounts	8

G.	Maximum Number of Applications	9

H.	Single Applicant Cap	9

I.	Agreements Contingent on Funding Availability	9

J.	Pre-Application Workshop	10

K.	Participation Through Zoom	10

L.	Questions	11

M.	Contact Information	11

N.	Reference Documents	12

II.	Eligibility Requirements	13

A.	Applicant Requirements	13

B.	Project Requirements	16

C.	Match Funding Requirements	38

D.	Unallowable Costs (Reimbursable or Match Share)	40

III.	Application Format, Required Documents, and Delivery	43

A.	Required Format for an Application	43

B.	Method for Delivery	43

C.	Solicitation Informational Documents	44

D.	Application Content	44

IV.	Evaluation Process and Criteria	62

A.	Application Evaluation	62

B.	Notice of Proposed Awards	65

C.	Debriefings	65

D.	Scoring Scale	66

E.	Technical Evaluation Criteria	67

F.	Cost Evaluation	72

G.	Tie Breakers	73

V.	Administration	74

A.	Definition of Key Words	74

B.	Cost of Developing Application	80

C.	Confidential Information	80

D.	Solicitation Cancellation and Amendments	80

E.	Errors	80

F.	Modifying or Recalling an Application	80

G.	Immaterial Defect	81

H.	Opportunity to Cure Administrative Errors	81

I.	Disposition of Applicant’s Documents	82

J.	Applicants’ Admonishment	82

K.	Agreement Requirements	83

L.	No Agreement Until Signed and Approved	84

M.	Executive Order N-6-22 – Russia Sanctions	84

##### Attachments

1 – Project Narrative

2 – Schedule of Products and Due Dates

3 – Proposal Budget

4 – Letters of Commitment

5 – Preliminary Site Plan

6 – California Environmental Quality Act (CEQA) Worksheet

7 – National Environmental Policy Act (NEPA) Preliminary Environmental Study (PES) Form

8 – Utility Verification Form

9 – Resumes

10 – Contact List

11 – Past Performance Reference Form

12 – Applicant Declaration

13 – Letters of Support (optional)

14 – Restricted Access Letters or Agreements (if required)

15 – Scope of Work (informational only)

16 – Right of Way Certification Form 13B (NEVI) (informational only)

# I.	Introduction

## Purpose of Solicitation

This is a competitive grant solicitation. The California Energy Commission (CEC) announces the availability of up to $79,000,000 in grant funds for projects that will strategically deploy high-powered, direct current (DC) fast charging infrastructure to support medium- and heavy-duty (MDHD) electric vehicle (EV) travel along major corridors of the state highway system in southern parts of California. The purpose of this solicitation is to significantly expand the MDHD EV charging infrastructure along these corridors per National Electric Vehicle Infrastructure (NEVI) formula program requirements, contributing to the national charging network being built under this program.

Submitted projects should be for installation and operation of DC fast chargers, using commercially available technology, within a previously disturbed or developed area such that the projects will qualify for the National Environmental Policy Act (NEPA) categorical exclusion for electric vehicle charging stations codified in the Code of Federal Regulations, Title 10, Chapter X, Part 1021, Appendix B, Categorical Exclusion B5.23, as explained in the Federal Register notice of the U.S. Department of Transportation’s adoption of the electric vehicle charging stations categorical exclusion (see https://www.federalregister.gov/documents/2023/09/20/2023-20238/notice-of-adoption-of-electric-vehicle-charging-stations-categorical-exclusion-under-the-national).

## Background

The Infrastructure Investment and Jobs Act (IIJA) (Public Law 117-58) authorizes hundreds of billions of dollars in new investments in a wide array of infrastructure categories, including roads and bridges, water infrastructure, passenger rail, energy, and broadband internet. The IIJA includes $5 billion to accelerate EV infrastructure deployment nationally under the NEVI formula program. California’s share is expected to be $384 million allocated over 5 years.

NEVI is an initiative to create a coast-to-coast network of EV chargers focused on major highways that support the majority of long-distance trips. This national network will give drivers confidence that they can always find a place to charge, and jump start private investment in charging infrastructure.

The CEC is collaborating with the California Department of Transportation (Caltrans) on charging infrastructure deployment under an interagency agreement in which the CEC is charged with implementing and administering California’s NEVI formula program.

The CEC and Caltrans prepare NEVI deployment plans as required by the NEVI formula program. The most recent California NEVI Plan is found at https://dot.ca.gov/-/media/dot-media/programs/sustainability/documents/transportation-electrification/nevi/2025-ca-nevi-plan-update-a11y.pdf. Information about the state’s implementation of the NEVI program is found at https://www.energy.ca.gov/programs-and-topics/programs/federal-ev-infrastructure-programs.

## Key Activities and Dates

Key activities including dates and times for this solicitation are presented below.  An addendum will be released if the dates change for the asterisked (*) activities. Times listed are Pacific Standard Time or Pacific Daylight Time, whichever is being observed.

| ACTIVITY | ACTION DATE |
| --- | --- |
| Solicitation Release | February 5, 2026 |
| Pre-Application Workshop* | February 25, 2026 |
| Deadline for Written Questions* | March 5, 2026 |
| Anticipated Distribution of Questions/Answers | Week of March 30, 2026 |
| Support for Application Submission in the Energy Commission Agreement Management System (ECAMS) until 5:00 p.m. | Ongoing until May 7, 2026 |
| Deadline to Submit Applications by 11:59 p.m.* | May 7, 2026 |
| Anticipated Notice of Proposed Awards Posting | Week of July 20, 2026 |
| Anticipated CEC Business Meeting | October 2026 |

## How Award Is Determined

Awards will be determined in the following manner:

- Applications must pass screening.

Applications must first pass the administrative screening and technical screening discussed in Section IV.A.1-4. Applicants that pass these screenings will proceed to Technical Evaluation, discussed in Section IV.A.6.

- Applications must achieve at least the minimum scores required in Technical Evaluation.

Applications will be evaluated separately using the scoring scale shown in Section IV.D. and the Technical Evaluation Criteria listed in Section IV.E. A minimum score of 70 percent is required for the application to be eligible for funding. Also, each application must additionally receive a minimum score of 70 percent on both Technical Evaluation Criterion 2, Project Readiness, and Technical Evaluation Criterion 4, Project Budget and Finances, to be eligible for funding.

- Applications will be ranked based on Cost Evaluation in their respective Project Regions.

Applications that pass Administrative and Technical screening and score at least 70 percent in Technical Evaluation (as described in i. and ii. above), will advance to Cost Evaluation, discussed in Section IV.A.7. and Section IV.F., wherein the cost efficiency metrics of Cost-per-new-Combined Charging System (CCS)-Port and Cost-per-kW of New Capacity will be calculated for each application:

- Cost-per-new-CCS-Port

- Cost-per-kW of New Capacity

Each metric is scored out of 50 points, for a total of 100 points. The applications with the lowest Cost-per-new-CCS-Port and lowest Cost-per-kW of new capacity will receive the highest scores. Unless the CEC exercises any of its other rights regarding this solicitation (e.g., to cancel the solicitation or reduce funding), each application’s proposed charging station will be ranked according to the combined score of its Cost-per-new-CCS-Port and Cost-per-kW of new capacity against other proposed charging stations in each Project Region as described in Section IV.A.7. and Section IV.F. Applications will be recommended for funding in order of highest to lowest combined score per Project Region.

- Additional awards if funding is still available.

The CEC will recommend funding proposed projects in rank order based on their combined cost evaluation scores in each Project Region, as described in Section II.B.3.

If an application proposes an EV charging station location that is within 50 miles, measured in driving distance, of a higher-ranked application proposed for award under this solicitation, the CEC may, at its sole discretion,  select the next ranked application to ensure adequate geographic distribution of funded stations.

The CEC reserves the right to modify the funding allocated to each Project Region. For example, if all eligible projects within a given Project Region have been proposed for award, or the geographic distribution of proposed awards is not adequate as described in the paragraph above, the CEC may opt to shift the remaining funds dedicated to that Project Region into a different Project Region(s).

If the funds available under this solicitation (or within a given Project Region) are insufficient to fully fund a grant proposal, CEC reserves the right to recommend partially funding that proposal. In this event, the proposed Applicant/Awardee and Commission Agreement Manager (CAM) shall meet and attempt to reach agreement on a reduced scope of work commensurate with the level of available funding.

## Availability of Funds

A total of $79,000,000 is available for awards under this solicitation. The CEC, at its sole discretion, reserves the right to increase or decrease the amount of funds available under this solicitation.

## Maximum Award Amounts

Projects are eligible for 80 percent of the total allowable project cost, or $8 million, whichever is less. “Total allowable project cost” is the sum of the CEC’s reimbursable share and Applicant’s match share of the project costs.

There is no maximum award amount per charging port. The Cost-per-New-CCS-Port includes all CEC reimbursable costs associated with the capital expenditure required for the EV charging port. This includes, but is not limited to, administrative, installation, operations and maintenance, and equipment costs.

Projects will be evaluated on the degree to which the proposed infrastructure demonstrates a highly cost-effective use of CEC funds, with a low Cost-per-New-CCS-Port relative to the power level. Projects will be evaluated on both the Cost-per-new-CCS-Port and the Cost-per-kW of new capacity.

On-site renewable distributed energy resources and stationary battery energy storage systems related to the charging of EVs are eligible for CEC reimbursement; however, such costs may not exceed 50 percent of CEC grant funds per port. Additionally, these costs will be included in the calculation of Cost-per-new-CCS-Port for evaluation purposes.

## Maximum Number of Applications

Applicants may submit up to five (5) applications per Project Region as defined in Section II.B.3. Each application must be for a different charging station , be separate and distinct, and adhere to all requirements contained in this solicitation. Each application must propose one project that must consist of one EV charging station (in other words, one site) and install a minimum combined EV charging nameplate capacity of three (3) megawatts (MW) and eight (8) EV charging ports. Other project requirements are defined in Section II.B. of this manual.

If an Applicant is proposed for multiple awards, the CEC reserves the right to, in its sole discretion, combine those awards into a single grant agreement for ease of administration.

## Applicant Award Cap

Applicants submitting multiple applications are eligible for no more than 20 percent of the total funding available under this solicitation. If an Applicant requests and is proposed to be awarded more than 20 percent of the funds available, the CEC intends to propose awards to the Applicant using the Cost Evaluation score for each application. If some of the Applicant’s applications received the same score, the tie breaker criteria listed in Section IV.G. will be used to determine which applications are proposed for award.

If the highest-scoring application within a Project Region is not eligible because the Applicant has exceeded the applicant award cap, the CEC may award the next-highest-scoring application for that Project Region.

The CEC reserves the right, at its sole discretion, to modify or eliminate the applicant award cap.

## Agreements Contingent on Funding Availability

Without limitation to any other of the CEC’s rights and remedies, if any of the Clean Transportation Program funds used for agreements resulting from this solicitation, or any of the federal funds for the NEVI program, become unavailable; are reduced; or are deleted, for any reason including but not limited to FHWA’s failure to obligate funds, de-obligation of previously obligated funds, or failure to provide sufficient funds to reimburse the state of California for the work identified in agreements’ scopes of work, or for CEC administrative costs to oversee and implement resulting agreements, as the CEC may in its sole discretion determine, without limitation to all other rights and remedies available to it, the CEC shall have the option to either: (1) cancel agreements resulting from this solicitation with no liability occurring to the CEC; or (2) offer agreement amendments to Recipients to reflect a reduced amount of funds. Should the CEC choose to cancel any resulting agreements, the CEC shall have no liability to pay any funds whatsoever to Recipients, any subrecipients, and any vendors; nor to furnish any other consideration under the agreements; and the Recipients shall not be obligated to perform any provisions of the agreements.

## Pre-Application Workshop

There will be one Pre-Application Workshop; participation in this meeting is optional but encouraged. The Pre-Application Workshop will be held remotely through Zoom at the date, time and location listed below. Please call the Commission Agreement Officer (CAO) listed below or refer to CEC's solicitation information website at https://www.energy.ca.gov/funding-opportunities/solicitations to confirm the date and time.

February 25, 2026

9:30 a.m. to 12:00 p.m.

Via Zoom

## Participation Through Zoom

Zoom is the CEC's online meeting service. When attending remotely, presentations will appear on your computer/laptop/mobile device screen, and audio may be heard via the device or telephone. Please be aware that the Zoom meeting will be recorded.

Zoom Instructions:

To join this workshop, go to Zoom at: https://energy.zoom.us/j/82808001205?pwd=4di0jaQsPtG8Aczsn3iuRPuBwJUvVJ.1

You may also access the workshop by going to the Zoom webpage at https://join.zoom.us and enter the unique meeting ID and password below:

Meeting ID: 828 0800 1205

Meeting Password: 835540

Topic: Pre-Application Workshop for GFO-25-606 California’s NEVI Solicitation 5

Telephone Access Only:

Call (888) 853-5257 or (888) 475-4499 (toll-free). When prompted, enter the unique meeting ID number above. To comment over the telephone, dial *9 to “raise your hand” and *6 to mute/unmute your phone line.

Access by Mobile Device:

Download the application from the Zoom Download Center at https://energy.zoom.us/download.

Technical Support:

For assistance with problems or questions about joining or attending the meeting, please call Zoom technical support at (888) 799-9666 ext. 2, or you may contact the CEC’s Public Advisor’s Office at publicadvisor@energy.ca.gov, or (916) 957-7910.

To determine whether your computer is compatible with Zoom, visit:

this website: https://support.zoom.us/hc/en-us/articles/201362023-System-requirements-for-Windows-macOS-and-Linux.

## Questions

During the solicitation process, for questions only related to submission of applications in ECAMS, please contact ECAMS.SalesforceSupport@energy.ca.gov. By contacting this email address, Applicants will be able to access a team of technical assistants who can answer questions about application submission. Please also see Section III for additional information about ECAMS.

Applicants may ask questions at the Pre-Application Workshop and may submit written questions via e-mail to the CAO listed in the following section. However, all technical questions must be received by the deadline listed in the “Key Activities and Dates” table above. Questions received after the deadline may be answered at the CEC's discretion. Non-technical questions (e.g., questions concerning application format requirements or attachment instructions) may be submitted to the CAO at any time prior to 5:00 p.m. of the application deadline date. Similarly, questions related to submission of applications in ECAMS may be submitted to ECAMS.SalesforceSupport@energy.ca.gov at any time prior to 5:00 p.m. of the application deadline date.

The question-and-answer set will be posted on the CEC’s solicitation information website at www.energy.ca.gov/funding-opportunities/solicitations.

Any verbal communication with a CEC employee concerning this solicitation is not binding on the State and shall in no way alter a specification, term, or condition of the solicitation. All communication must be directed in writing to the CAO assigned to the solicitation.

## Contact Information

Eunice Lemos-Adair, Commission Agreement Officer

California Energy Commission

715 P Street, MS-18

Sacramento, California 95814

Telephone:1 (279) 226-1065

E-mail: Eunice.Lemos-Adair@Energy.ca.gov

## Reference Documents

Applicants responding to this solicitation may want to familiarize themselves with the following documents:

- California Energy Commission. Energy Commission Agreement Management System (ECAMS). https://www.energy.ca.gov/funding-opportunities/funding-resources/ecams-resources.

- California Energy Commission. National Electric Vehicle Infrastructure (NEVI) Formula Program. https://www.energy.ca.gov/programs-and-topics/programs/national-electric-vehicle-infrastructure-nevi-formula-program.

- California Energy Commission. California’s National Electric Vehicle Infrastructure Funding Program Map. https://experience.arcgis.com/experience/135c0da4b70f4717b4664ad2e427d2bc.

- Caltrans. Local Assistance Procedures Manual. https://dot.ca.gov/programs/local-assistance/guidelines-and-procedures/local-assistance-procedures-manual-lapm.

- Caltrans. Local Assistance Guidelines and Procedures. https://dot.ca.gov/programs/local-assistance/guidelines-and-procedures.

- Caltrans. Right of Way Manual. https://dot.ca.gov/programs/right-of-way/right-of-way-manual.

- National Electric Vehicle Infrastructure Standards and Requirements. https://www.federalregister.gov/documents/2023/02/28/2023-03500/national-electric-vehicle-infrastructure-standards-and-requirements.

- U.S. Department of Transportation, Federal Highway Administration. National Electric Vehicle Infrastructure (NEVI) Program. https://www.fhwa.dot.gov/environment/nevi/.

- California Energy Commission and Caltrans. California's Deployment Plan for the National Electric Vehicle Infrastructure Program – 2025 Annual Update. https://dot.ca.gov/-/media/dot-media/programs/sustainability/documents/transportation-electrification/nevi/2025-ca-nevi-plan-update-a11y.pdf .

- Joint Office of Energy and Transportation. Technical Assistance. https://driveelectric.gov/technical-assistance/.

- National Archives – Federal Register. Waiver of Buy America Requirements for Electric Vehicle Chargers. https://www.federalregister.gov/documents/2023/02/21/2023-03498/waiver-of-buy-america-requirements-for-electric-vehicle-chargers.

- California Energy Commission. National Electric Vehicle Infrastructure (NEVI) Funding Program, Docket Log 22-EVI-05. https://efiling.energy.ca.gov/Lists/DocketLog.aspx?docketnumber=22-EVI-05.

- Electric Vehicle Infrastructure Training Program. https://evitp.org/.

- California Energy Commission. Electric Vehicle Infrastructure Deployment Assessment – SB 1000. https://www.energy.ca.gov/programs-and-topics/programs/clean-transportation-program/electric-vehicle-infrastructure.

- California Energy Commission. Electric Vehicles Charging Infrastructure Assessment – AB 2127. https://www.energy.ca.gov/programs-and-topics/programs/electric-vehicle-charging-infrastructure-assessment-ab-2127.

- California Air Resources Board. Electric Vehicle Supply Equipment (EVSE) Standards. https://ww2.arb.ca.gov/our-work/programs/electric-vehicle-supply-equipment-evse-standards.

- California Department of Food and Agriculture, Division of Measurement Standards. Zero-Emission Vehicle Projects. https://www.cdfa.ca.gov/dms/programs/zevfuels/.

# II.	Eligibility Requirements

## Applicant Requirements

- Eligibility

This solicitation is open to all private entities, excluding investor-owned utilities, and is also open to California Tribal Organizations serving California Native American Tribes.

Eligible Applicants must have less than or equal to fifty (50) active projects across all CEC-funded zero-emission vehicle infrastructure grant agreements, including block grants, at the time of agreement execution. A project is considered “active” if it has been awarded under one of CEC’s grants or block grant programs and construction has not finished on the project; a request for final reimbursement has not been submitted; final reimbursement is pending; or the agreement term has not expired. The CEC reserves the right to modify this requirement.

- Terms and Conditions

Each grant agreement resulting from this solicitation will include terms and conditions that set forth the grant recipient’s rights and responsibilities. By providing the authorizations and certifications required under this solicitation, each Applicant agrees to enter into an agreement, if awarded, with the CEC to conduct the proposed project according to the terms and conditions for this solicitation, the NEVI Standard Terms and Conditions, found at https://www.energy.ca.gov/media/11964, the NEVI Special Terms and Conditions, found at https://www.energy.ca.gov/media/11963, and, if applicable, the Special Terms and Conditions for California Tribal Organizations serving California Native American Tribes with Sovereign Immunity, found at https://www.energy.ca.gov/media/12259, without negotiation.

Failure to agree to the terms and conditions by taking actions such as failing to provide the required authorizations and certifications or indicating that acceptance is based on modification of the terms may result in rejection of the application. Applicants must read the terms and conditions carefully. The CEC reserves the right to modify the terms and conditions prior to executing grant agreements.

If a California Tribal Organization (Tribal Organization) with sovereign immunity serving a California Native American Tribe (Tribe) with sovereign immunity is listed as a proposed awardee in the Notice of Proposed Awards (NOPA), before bringing the proposed award to a Business Meeting, CEC staff must receive (a) resolution(s) or other authorizing document(s) by the governing body of the Tribe and/or Tribal Organization (as applicable) which:

i.	Authorizes the Tribal Organization to enter into the proposed agreement, including accepting the Special Terms and Conditions for California Tribal Organizations with Sovereign Immunity Serving California Native American Tribes with Sovereign Immunity, including the Limited Waiver of Sovereign Immunity and Consent to Jurisdiction; and

ii.	Approves a limited waiver of the Tribal Organization’s sovereign immunity, to the extent that any such sovereign immunity exists, for any and all claims by the CEC that may arise relating to this Agreement and any remedies therefore under the laws of the state of California and the laws of the United States of America; and

iii.	Consents to personal jurisdiction over the Tribal Organization, and consents to venue in any court of the State of California and any federal court sitting in the State of California; and waives any and all claim that the Tribal Organization may have, including without limitation that such court is an inconvenient forum, for the purposes of any proceeding related to this Agreement; and, with respect to a proceeding in a court of the State of California or a federal court sitting in the State of California, any requirement that tribal remedies must be exhausted; and

iv.	Delegates authority to execute the proposed agreement to an appropriate individual.

The above requirements may be provided in one or more documents. The document(s) will be included as an exhibit to the resulting grant agreement.

Delay in award. Any delay in the Tribe or Tribal Organization’s ability to provide the documentation specified in sections (i)-(iv) above may result in a delayed award of the grant agreement.

Reservation of right to cancel proposed award. Funds available under this solicitation have encumbrance deadlines that the CEC must meet in order to avoid expiration of the funds. In addition to any other rights reserved to it under this solicitation or that it otherwise has, the CEC reserves the right to cancel a proposed award for an EV charging station at any time if it determines, in its sole and absolute discretion, that the documentation described in sections (i)-(iv) above would likely not be provided prior to an encumbrance deadline, and that the CEC’s ability to meet its encumbrance deadline may thereby be jeopardized. In this instance, the CEC may cancel the proposed award and award funds to the next highest ranked application for that Project Region according to the evaluation process discussed in Section I.D. How Award is Determined.

- California Secretary of State Registration

All corporations, limited liability companies (LLCs), limited partnerships (LPs) and limited liability partnerships (LLPs) that conduct intrastate business in California are required to be registered and in good standing with the California Secretary of State prior to its project being recommended for approval at a CEC Business Meeting. If not currently registered with the California Secretary of State, Applicants and project team members (e.g. subrecipients and even match fund partners) are encouraged to contact the Secretary of State’s Office as soon as possible to avoid potential delays in beginning the proposed project(s) (should the application be proposed for funding).

For more information, contact the Secretary of State’s Office via the Secretary of State Office’s website at www.sos.ca.gov. Sole proprietors using a fictitious business name must be registered with the appropriate county and provide evidence of registration to the CEC prior to their project being recommended for approval at a CEC Business Meeting.

## Project Requirements

Each application is considered one project and must propose to install one EV charging station that will support MDHD EVs at an eligible location, as described in Section II.B.2, adjacent to one of the state’s Alternative Fuel Corridors. The charging station may also support light-duty (LD) EVs, but the purpose and configuration of the station must prioritize MDHD EVs. Any costs associated foremost with LD EV charging will not be eligible for reimbursement by the CEC, nor counted toward match funding requirements. The project must develop, install, and operate the proposed EV charging station for at least five years as specified in the Scope of Work (Attachment 15).

The proposed EV charging station must install a minimum combined EV charging nameplate capacity of 3 MW and install a minimum of 8 new EV charging ports. See Section II.B.4. Megawatts Per EV Charging Station, Number of EV Charging Ports, and Connector Types for additional requirements.

For purposes of this solicitation, an EV charging station refers to the area in the immediate vicinity of a group of chargers and includes the chargers, supporting equipment, parking areas adjacent to the chargers, and lanes for vehicle ingress and egress. An EV charging station could comprise only part of the property on which it is located. Multiple chargers may be associated with one EV charging station.

MDHD EVs are defined as EVs with a gross vehicle weight rating (GVWR) greater than 10,000 pounds and include vans, buses, and trucks. LD EVs are those with GVWR of 10,000 pounds or less.

The state’s Alternative Fuel Corridors are shown in California’s National Electric Vehicle Infrastructure Funding Program Map at https://www.energy.ca.gov/programs-and-topics/programs/national-electric-vehicle-infrastructure-nevi-formula-program-0.

- Compliance with Requirements Applicable to NEVI Projects

Project selection and grant administration shall be consistent with the Bipartisan Infrastructure Law, enacted as the Infrastructure Investment and Jobs Act (IIJA), (Pub. L. 117-58). The NEVI formula program is authorized under Paragraph (2) under the Highway Infrastructure Program heading in title VIII of division J of the Bipartisan Infrastructure Law.

Applicants should take note that there are special requirements associated with the federal NEVI formula program that will apply to projects awarded under this grant. Those requirements are described in detail in the terms and conditions that will be required for grants awarded under this solicitation, which are referenced in Section II.A.2.

Without limitation to those terms or any other provision of this solicitation or resultant grant agreements, Applicants should in particular note that all work must comply with the Build America Buy America Act enacted as part of the IIJA, Davis Bacon Act, National Environmental Policy Act, Americans with Disabilities Act of 1990 (ADA), Title VI of the Civil Rights Act of 1964, all applicable requirements of Title VIII of the Civil Rights Act of 1968, the Uniform Relocation Assistance and Real Property Acquisition Act [49 Code of Federal Regulations (CFR) 24 et seq.], and the requirements of the federal NEVI Program, including the requirements of United States Code (USC) Title 23, Chapter 1; and 2 CFR part 200; and 23 CFR parts 35 and 36; any promulgated regulations for the federal NEVI Program; and California’s NEVI Deployment Plan, as amended from time to time.

The Federal Uniform Act must be followed on all federal-aid, local assistance projects, which is how all projects resulting from this solicitation will be categorized. This Act applies if federal funds are used in any phase of a project.

- Project Location

- The proposed EV charging station must be located within California, along any corridor group or corridor segment of one (1) of the state’s Alternative Fuel Corridors, which are shown in California’s National Electric Vehicle Infrastructure Funding Program Map at https://www.energy.ca.gov/programs-and-topics/programs/national-electric-vehicle-infrastructure-nevi-formula-program-0.

- The proposed EV charging station must be sited within one (1) mile, as a vehicle drives by the shortest route, of the Alternative Fuel Corridor’s nearest off-ramp or intersection where a vehicle can leave the corridor. Applicants must show their calculation of the driving distance between the nearest exit of the Alternative Fuel Corridor to the proposed station in their Project Narrative (Attachment 1). The EV charging station must be easily accessible via a route that can safely and conveniently accommodate theexpected MDHD EVs traveling to the facility, entering and leaving the facility, returning to the highway, and continuing in the original direction of travel.

- Proposed EV charging stations must be sited on previously disturbed or developed areas. “Previously disturbed or developed” refers to land that has been changed such that its functioning ecological processes have been and remain altered by human activity. The phrase encompasses areas that have been transformed from natural cover to non-native species or a managed state, including, but not limited to, utility and electric power transmission corridors and rights-of-way, and other areas where active utilities and currently used roads are readily available (10 CFR 1021.102(g)(1), found at https://www.ecfr.gov/current/title-10/chapter-X/part-1021/section-1021.102#p-1021.102(g)(1)).

- Access and parking must be in accordance with applicable requirements (such as local land use and zoning requirements) in the proposed project area and incorporate appropriate control technologies and best management practices as further described in the Federal Register notice of the Department of Transportation’s adoption of the EV charging stations categorical exclusion under NEPA (see https://www.federalregister.gov/documents/2023/09/20/2023-20238/notice-of-adoption-of-electric-vehicle-charging-stations-categorical-exclusion-under-the-national).

- The proposed EV charging station must not be sited on property owned by Caltrans.

- Project Regions

This solicitation identifies two project regions covering counties in southern California as listed below in Table 1 with funding allocated to each Project Region. The CEC reserves the right to modify the funding allocated to each Project Region.

Projects will be scored and ranked by Project Region designated by the county in which the project’s proposed EV charging station is located. Projects will be ranked and awarded based on their Cost Evaluation within their respective Project Regions, as discussed in Section I.D., until the funding allocation has been reached for that Project Region, or until all passing projects in that Project Region are proposed for award, whichever is first.

If an application proposes an EV charging station location that is within 50 miles, measured in driving distance, of a higher-ranked application proposed for award under this solicitation, the CEC may, at its sole discretion,  select the next ranked application to ensure adequate geographic distribution of funded stations.

The CEC reserves the right to modify the funding allocated to each Project Region. For example, if all eligible projects within a given Project Region have been proposed for award, or have been skipped over due to geographic proximity to a higher-ranked project as described in the paragraph above, the CEC may opt to shift the remaining funds dedicated to that Project Region into a different Project Region(s).

Table 1: Project Regions and Funding Allocations

| Project Region | Counties | Funding Allocation |
| --- | --- | --- |
| 4 | Los Angeles, Orange | $48,720,000 |
| 5 | Imperial, Riverside, San Bernardino, San Diego | $30,280,000 |
|  | TOTAL | $79,000,000 |

- Megawatts Per EV Charging Station, Number of EV Charging Ports, and Connector Types

- Each proposed EV charging station must install a minimum of 3 MW nameplate of new charging capacity. If the proposed project is an expansion of an existing EV charging station, the project must add at least 3 MW of additional nameplate capacity to the site.

- Each project must include the installation of at least 8 new EV charging ports.

- Each project must also make the proposed EV charging station “MW Ready,” meaning it must install the conduit, switchgear, and pad to enable the future installation of at least one 1-MW charger (the charger itself is not required).

- Each DC fast charging port must meet applicable industry standards and must be capable of charging any CCS-compliant vehicle. Each DC fast charging port must have at least one permanently attached CCS Type 1 connector.

- Each port may optionally include any other non-proprietary connector type, except for CHAdeMO, but must still include at least one permanently attached CCS Type 1 connector.

- A proposed EV charging port can have multiple connectors, but because only one connector is usable at a time, no extra capacity is granted if there is more than one connector on a single port.

- Each proposed DC fast charging port, and each connector attached to the port, must have a nameplate capacity to supply at least 150 kilowatts (kW) and be able to supply that power as described in Section II.B.8. Charging Equipment and Networking Requirements.

- Compliance with Applicable Laws, Ordinances, Regulations, and Standards

All Applicants proposed for award must comply with all applicable laws, ordinances, regulations, and standards; federal, state, and local electrical and building codes for construction.

- EV Charging Station Accessibility and Availability

EV charging stations funded under this solicitation must be accessible 24 hours per day, 7 days per week, year-round, to the applicable customers as described in a), b), or c) of this section. This does not prohibit isolated or temporary interruptions in service or access because of maintenance or repairs.

EV charging stations must be one of the following:

- Public Access, defined as an EV charging station that is open to the general public, meaning all EV charging equipment is available to any customer without restriction. A station that restricts access to certain customers, tenants, or employees is not publicly accessible.

- Restricted Access, defined as an EV charging station that is open to authorized commercial motor vehicle operators from more than one company (the station cannot be limited to one company’s sole use). Commercial motor vehicle operators are any entity that operates a motor vehicle designed or regularly used to carry freight, merchandise, or more than ten passengers, whether loaded or empty, including buses, but not including vehicles used for vanpools, or recreational vehicles operating under their own power.

- Hybrid Access, defined as an EV charging station that is part Public Access and part Restricted Access. In other words, some EV charging infrastructure is open to the general public, and some EV charging infrastructure is limited to authorized commercial motor vehicle operators from more than one company (not limited to one company’s sole use).

For Public Access stations, as well as the Public Access portions of Hybrid Access stations, signage that limits who can use the chargers is strictly prohibited. For such stations (or portions of stations), signs and other actions cannot be used to limit access to guests, patrons, or otherwise that would cause a driver to believe they would be prohibited from, towed, or fined for using the charger.

For Restricted Access stations, as well as the Restricted Access portions of Hybrid Access stations, the Application must include signed agreements or letters of intent from more than one commercial motor vehicle operator, attesting to their intended use of the station (Attachment 14).

EV charging stations must have paved parking spaces available to render EV charging services. EV charging stations and parking areas must be well lit. The charger user must be able to easily read any instructions on the charger and the area around the vehicle must have adequate lighting to allow the driver to safely walk from the charger to the charging port on the vehicle.

Proposed EV charging stations may utilize a reservation system, allowing customers the option to reserve chargers in advance of charging. If utilizing a reservation system, the reservation system must be available to all intended customers (either the general public or restricted-access users, depending on if the proposed station will be Public Access, Restricted Access, or Hybrid Access, as defined earlier in this section).

For EV charging stations that will be open to the general public, accessibility to all EV drivers is required. Applicants should familiarize themselves with the Division of the State Architect’s requirements on complying with ADA, coordinate with their local permitting agency, and comply with the customer service requirements in Section II.B.14 to ensure accessibility for all drivers.

- Project Team

The Applicant, or the Subrecipient installing chargers, must be an Experienced Contractor, which is defined as a company or organization with a proven record of accomplishment in overseeing the procurement, permitting, and installation of at least twenty (20) DC fast chargers. The company or organization must have completed installations at three (3) or more different property locations for three (3) or more different customers since January 1, 2018.

Not every subrecipient or vendor must meet this definition to participate in the project. At minimum, the project team must include one (1) Experienced Contractor to serve as a subject matter expert to all other contractors, if necessary.

The project team must include a charging network provider that has demonstrated experience or has the capability to provide networking services for the charging stations for at least the entire 5-year in-service requirement (see section II.B.12).

- Charging Equipment and Networking Requirements

All the following requirements must be met:

- Power Requirements

  - Each charging port must support output voltages between 250 volts DC and 920 volts DC.

  - Each port on an installed charger must have a continuous power delivery rating of at least 150 kW and supply power according to an EV’s power delivery request of at least 150 kW, simultaneously from each charging port at a charging station. These DC fast charging stations may conduct power sharing so long as each charging port continues to meet an EV's request for power up to 150 kW.

- Interoperability: Charger-to-EV Communication

  - The chargers must conform to ISO 15118-3, and hardware must be capable of implementing both ISO 15118-2 and ISO 15118-20.

  - The chargers must include all necessary software and hardware to perform Plug-and-Charge using ISO 15118-2.

  - Conformance testing for charger software and hardware should follow ISO 15118-4 and 15118-5, respectively.

- Interoperability: Charger-to-Charger Network Communication

  - The chargers must conform to Open Charge Point Protocol (OCPP) 2.0.1 or later. Manufacturers must attest that the charger conforms to OCPP 2.0.1 or later by detailing it on a publicly available charger specification sheet.

- Interoperability: Charging-Network-to-Charging Network Communication

  - The charger’s networking software must connect to a central management system using OCPP 2.0.1 for the purposes of charger management and data reporting.

  - The charging network must be capable of communicating with other charging networks in accordance with the Open Charge Point Interface (OCPI) 2.2.1.

- Interoperability: Network Switching Capability

- The chargers must be designed to securely switch network providers without any changes in hardware.

- Cybersecurity

  - The chargers and charging software must meet all the NEVI cybersecurity requirements listed in the federal NEVI standards. Funding recipients will be required to develop a cybersecurity plan as required in Section II.B.18 after agreement execution and prior to the time of station commissioning.

- Charger Network Connectivity Requirements

- The chargers must be networked and must include the following three abilities:

      - Have network connectivity with one of the following:

        - IEEE 802.11n for high-bandwidth wireless networking, or

        - IEEE 802.3 for Ethernet for local- or wide-area network applications.

      - Be able to receive remote software updates, real-time protocol translation, encryption, and decryption, including:

        - Internet Protocol (IP)-based processor which must support multiple protocols, and

        - Compliance with Transmission Control Protocol (TCP)/IP and IPv6.

      - Be able to connect to a network’s back-end software.

  - Each charging port must be covered by and included in a networking agreement for at least five (5) years.

- Safety and Weather Resistance

- The charging equipment must be certified by an Occupational Safety and Health Administration Nationally Recognized Testing Laboratory.

- The charging equipment must be able to withstand extreme weather conditions, including temperature extremes, flooding, heavy rains, and high winds.

- Display screens must be protected from malfunctions due to condensation and any local area weather conditions.

- Compliance with State Requirements

- All chargers must meet applicable requirements, including those of Senate Bill 454 (Corbett, Chapter 418, Statutes of 2013), the California Air Resources Board Electric Vehicle Supply Equipment (EVSE) Standards, and the California Department of Food and Agriculture Division of Measurement Standards, for public chargers.

- Electric Utility Capacity

- Applicants must complete the Utility Verification Form (Attachment 8) to determine potential capacity availability.

- Operational needs for the EV charging station electrical demand can be met in several ways, as shown in Table 2.

Table 2: Utility Capacity Options

| Utility Capacity Option | Description |
| --- | --- |
| Full Charging Capacity Upon Opening | The site is equipped to supply the full nameplate capacity of all chargers if each charger is delivering 100 percent of its rated nameplate capacity concurrently at time of station commissioning. This may include distributed energy resources (DERs) and battery energy storage systems (BESS). Applicants shall work with their electric utility during the site design and deployment of the chargers in determining the site level power needed to support the chargers at that level. |
| Ramped Charging Capacity | At station commissioning, each charger must be capable of delivering a minimum of 50 percent of its rated nameplate capacity with all chargers in use concurrently. Within five (5) years of agreement execution with the CEC, each charger must be capable of delivering a minimum of 80 percent of its rated nameplate capacity under the same conditions. Compliance may be supported by DERs and BESS. Applicants shall work with their electric utility during the site design and deployment of the chargers in determining the site level power needed to support the chargers at that level. |
| Flexible Service Agreement | If offered by the serving electric utility, the station operator may secure a flexible service agreement to receive a predefined capacity for specific times. The applicant must describe the station's expected peak operational times and associated electrical demand, and how the site will meet these needs. At the time of station commissioning, the site shall be able to meet the following minimums: be able to power each charger at a minimum of 25 percent of the rated nameplate capacity if all chargers operating concurrently at all hours of the day; be able to power each charger at a minimum of 50 percent of the rated nameplate capacity during the station's peak operational times. Power may also be supplemented by DERs or BESS. Within five (5) years of agreement execution with the CEC, each charger must be capable of delivering a minimum of 80 percent of its rated nameplate capacity under the same conditions. Compliance may be supported by DERs and BESS. Applicants shall work with their electric utility during the site design and deployment of the chargers in determining the site level power needed to support the chargers at that level. |

- Participation in demand response programs is permitted but will not be counted toward meeting operational needs.

- If DERs such as wind or solar and/or BESS are to be used, they must meet the following requirements:

  - The proposed system must be directly related to charging a vehicle and only transfer power to and from the chargers.

  - If DERs are proposed, they must be renewable, non-fossil fuel generation.

  - The proposed system must meet operational needs.

  - The proposed system must not increase the project timeline.

  - The proposed system must enhance fueling reliability and reduce costs for consumers.

- Build America, Buy America

Without limitation to all other requirements in the terms and conditions that will be required for grants awarded under this solicitation, which are referenced in Section II.A.2 above, or any other provision of this solicitation or resultant grant agreements, Applicants should in particular note that Recipients must comply with federal Buy America requirements consistent with the final Federal NEVI standards (23 U.S.C. 313 at https://www.govinfo.gov/content/pkg/USCODE-2021-title23/pdf/USCODE-2021-title23-chap3-sec313.pdf) and Build America, Buy America Act (Pub. L. No 117-58, div. G sections 70901-70927). This includes, but is not limited to, requirements that all iron and steel; all manufactured products; and all construction materials that are used in the project are produced in the United States. Applicants are encouraged to review the Federal requirements and to verify with their equipment supplier(s) that their equipment meets and can document compliance with this requirement.

- Data Submittals

Applications that result in proposed awards and executed agreements will be required to perform recordkeeping and reporting on charger operations and reliability as specified in the solicitation Scope of Work (Attachment 15). These requirements include quarterly, annual, and one-time data submittals, as well as real-time reporting of charger status and charging session information through application programming interface (API). Applicants should familiarize themselves with the National Electric Vehicle Infrastructure Standards and Requirements found at https://www.federalregister.gov/documents/2023/02/28/2023-03500/national-electric-vehicle-infrastructure-standards-and-requirements and the solicitation Scope of Work (Attachment 15) requirements and ensure they have systems in place to comply.

- Operation, Maintenance, and Uptime

Each charging port, charger, and EV charging station funded through the solicitation must operate for at least five (5) years after its commissioning date.

Each charging port must have an average annual uptime of greater than 97 percent per the requirements of the NEVI program specified in 23 CFR 680.116(b). A charging port is considered to be “up” when its hardware and software are both online and available for use, or in use, and the charging port successfully dispenses electricity in accordance with requirements for the minimum power level (see 23 CFR 680.106(d)). Charging port uptime must be calculated on a monthly basis for the previous twelve (12) months. Charging port uptime percentage must be calculated using the following equation:

µ = ((525,600−(T_outage−T_excluded))/525,600) × 100

where:

µ = port uptime percentage,

T_outage = total minutes of outage in previous year, and

T_excluded = total minutes of outage in previous year caused by the following reasons outside the charging station operator's control, provided that the charging station operator can demonstrate that the charging port would otherwise be operational: electric utility service interruptions, failure to charge or meet the EV charging customer's expectation for power delivery due to the fault of the vehicle, scheduled maintenance, vandalism, or natural disasters. Also excluded are hours outside of the identified hours of operation of the charging station.

It will be the Recipient’s responsibility to demonstrate that this uptime requirement is met.

Each charger and charging port funded through this solicitation shall meet the specific recordkeeping, maintenance, and reporting requirements related to uptime and other metrics that are detailed in the Scope of Work (Attachment 15).

- Payment Options

All of the following requirements must be met:

- All EV charging stations funded under this solicitation must provide secure payment methods, be accessible to persons with disabilities, and must at minimum include:

  - Near Field Communication (NFC) and Radio Frequency Identification (RFID) contactless payment methods that accept major debit and credit cards.

  - Either an automated toll-free phone number or short message/messaging system (SMS) that provides the EV charging customer with the option to initiate a charging session and submit payment.

- Additional payment mechanisms may be offered, such as Plug-and-Charge or payment through mobile apps.

- Public Access EV charging stations and the public components of Hybrid Access EV charging stations must not require a membership for use.

- Charging stations must not delay, limit, or curtail power flow to vehicles on the basis of payment method or memberships.

- Charging stations must provide access for users that are limited English proficient and accessibility for people with disabilities. Automated toll-free phone numbers and SMS payment options must clearly identify payment access for these populations.

- The point-of-sale and supporting network must use an open protocol to allow subscribers of other EV charging system networks to access the charging station.

- The point-of-sale and supporting network must be secure and meet the final NEVI cybersecurity requirements.

- Customer Service

The project must provide customer support service and ensure that EV charging customers have mechanisms to report outages, malfunctions, and other issues with the charging infrastructure. Mechanisms may include, but are not limited to, a toll-free telephone number, an email, instant messaging chat, or an online portal. The customer support service must be capable of providing or dispatching services to address customer concerns at the charging station. Customer support must be available in at least English and Spanish. Projects must comply with the Americans with Disabilities Act of 1990 (ADA) requirements and multilingual access when creating reporting mechanisms.

- Highway and On-Site Signage

The project must coordinate with appropriate local agencies and Caltrans for directional signage on and along the highway and local roads, if it is not already installed. The signs must meet the California Manual on Uniform Traffic Control Devices (CA MUTCD) standards, and all other applicable laws, ordinances, regulations, and standards. The Recipient shall coordinate with cities and counties on trailblazer signage on local roads leading to the charging location. This award may cover funding for trailblazer and on-site signage as required to comply with the federal NEVI standards.

Recipients may contact Caltrans sign coordinators and ask for sign installation on the State Highway System at https://dot.ca.gov/programs/safety-programs/sign-specs/district-sign-coordinators.

- Eligible Project Costs

Costs incurred for the following are eligible for CEC reimbursement or as the Applicant’s match share, after the corresponding project phase has been authorized by the FHWA and the grant agreement has been formally executed:

  - DC fast charging electric vehicle supply equipment (EVSE, or chargers) with at least 8 CCS ports per station

  - Transformers

  - Electric panels

  - Conduit

  - Wiring

  - Meters

  - On-site, renewable DER equipment such as solar arrays, or stationary BESS that is directly related to the charging of EVs. These costs should only be considered if they will lead to lower costs to consumers, greater EV charging station reliability, and if they do not substantially increase the timeline for completing an EV charging station project. Any of these systems must be interconnected to the charging system and must be separately metered from the site host's regular business meter. Eligible reimbursable costs may not exceed 50 percent of CEC grant funds per port.

  - Installation costs

  - Planning and engineering design costs.

  - Stub-outs

  - Lighting, canopies, and other amenities designed to serve EV charging station customers

  - Demand management equipment

  - Networking licenses for up to five (5) years of operations and which are purchased during the agreement term

  - Equipment warranties for up to five (5) years of operations and which are purchased during the agreement term

  - Maintenance provided during the agreement term for up to five (5) years of operations, or a maintenance agreement or a service level agreement for up to five (5) years of operations and which is purchased during the agreement term

  - Local engagement and outreach related to EV charging not to exceed three percent of the total reimbursable project cost

  - Signage

The following project costs and/or types ARE NOT eligible as CEC reimbursement or match share. This includes but is not limited to:

  - Vehicle purchases

  - Manufacturing costs

  - Cost of electricity to operate the charging station and its EVSE

  - Marketing and promotional activities

  - A standard outlet (110/120 volt or 220/240 volt)

  - Costs related to light-duty charging equipment or other costs such as Level 1 and/or Level 2 chargers

  - Mobile charging equipment

  - Land acquisition or lease costs

  - Costs to obtain match funding commitments

  - Lighting, canopies, and other amenities on the charging station site that are not designed to serve EV charging station customers

  - Nonrenewable distributed energy resources

  - Distribution grid or other equipment costs that are otherwise covered by programs or tariff rules of the electric utilities are excluded

  - Projects that are mandated by any local, regional, state, or federal law, rule, or regulation

  - Projects that help the Applicant meet a performance requirement mandated by local, regional, state, or federal law, rule, or regulation

  - Paper studies or research projects (e.g., a study which assess the cost and feasibility of EV charging station installations along certain regions/corridors)

  - Projects that are primarily surveys to determine interest in the installation of EV charging stations in a particular region/corridor

  - Proposals for vehicle demonstrations or demonstrations of existing technologies

  - Software development

A project that receives incentive funding from another CEC grant funding opportunity (GFO) or block grant incentive project is not eligible for this GFO.

- Electric Vehicle Infrastructure Training Program (EVITP)

EV charging infrastructure and equipment located on the customer side of the electrical meter shall be installed by a contractor with the appropriate license classification, as determined by the Contractors’ State License Board, and at least one (1) electrician on each crew, at any given time, who holds an EVITP certification. Projects that include installation of a charging port supplying 25 kilowatts or more to a vehicle must have at least 25 percent of the total electricians working on the crew for the project, at any given time, hold EVITP certification. One member of each crew may be both the contractor and an EVITP certified electrician. The requirements stated in this paragraph do not apply to any of the following:

(1)	EV charging infrastructure installed by employees of an electrical corporation or local publicly owned electric utility.

(2)	EV charging infrastructure funded by moneys derived from credits generated from the Low Carbon Fuel Standard Program (Subarticle 7 (commencing with Section 95480) of Article 4 of Subchapter 10 of Chapter 1 of Division 3 of Title 17 of the California Code of Regulations).

(3)	Single-family home residential EV chargers that can use an existing 208/240-volt outlet.

Compliance with California EVSE Commercial Device Requirements: All EVSE installed for commercial use shall have a type approval certificate issued through the California Type Evaluation Program (CTEP) administered by the California Department of Food and Agriculture (CDFA) Division of Measurement Standards (DMS) or Certificate of Conformance issued by the National Type Evaluation Program (NTEP) administered through the National Conference on Weights and Measures (NCWM). California accepts NTEP certificates so long as the device also meets CCR Title 4, Section 4002.11.

Unless otherwise updated by the CDFA DMS, any installation, repair, or maintenance on commercial EVSE must be performed by a Registered Service Agency (RSA) and after the device is placed in service, the RSA must report this information to the county within 24 hours. Device owners are responsible for registering their device with the county.

- Data Privacy and Cybersecurity

Recipients shall be responsible for cybersecurity as it relates to owning, operating, maintaining, and data sharing for the EVSE. The Recipient must develop and submit to the CEC a Data Management and Cybersecurity Plan after agreement execution and prior to the time of station commissioning. The Data Management and Cybersecurity Plan, as required in the Scope of Work (Attachment 15), must include the Recipient’s data security policies, procedures, and remediation plan. The plan should include, at minimum, the following:

- Strong authentication and access control

- Network segmentation to isolate critical components to limit attack

- Intrusion detection and monitoring

- Integrating cybersecurity measures at the hardware level

- Firmware integrity of chargers

- User data privacy and protection

- Secure data transfer and protection at rest

- Secure communications protocols

- Payment systems

- Cloud protections

- System and data access management to ensure only authorized individuals have access

- Employee cybersecurity training

- Patching and updates

- Incident response reporting and recovery, including a communications plan

- Audits and assessments

- Continuity of operations

- Risk acceptance and mitigation

- Disaster recovery

The CEC strongly encourages Recipients use the U.S. DOT’s guidance on developing a data management plan for assistance with their drafting their plans found at https://ntl.bts.gov/ntl/public-access/creating-data-management-plans. The US Joint Office of Energy and Transportation also has available Sample Cybersecurity Clauses for EV Charging Infrastructure Procurements, which can be found at https://driveelectric.gov/cybersecurity-clauses. Recipients are strongly encouraged to reference the Joint Office’s Sample Cybersecurity Clauses for EV Charging Infrastructure Procurements when developing their Application and agreements with subcontractors.

- Project Revenue and Pricing for EV Charging

Recipients must comply with the restrictions on use of program income specified in 23 CFR Part 680.106(m). Recipients may use revenue generated from the operation of charging stations for debt service, a reasonable return on investment, and/or costs for operation, maintenance, and site improvement. Recipients must include sufficient information in their Project Narrative (Attachment 1) for the CEC to evaluate how revenue from the proposed charging stations will be used in accordance with 23 CFR 680.106(m).

Communication of price. The price for charging must be displayed prior to initiating a charging transaction and be based on the price for electricity to charge in $/kWh. The price for charging displayed and communicated via the charging network must be the real-time price (i.e., price at that moment in time). The price at the start of the session cannot change during the session. Price structure including any other fees in addition to the price for electricity to charge must be clearly displayed and explained.

- Right of Way

Recipients must prepare to have their projects follow the procedures of federally-funded local transportation projects as explained in the Caltrans Local Assistance Procedures Manual (LAPM), found at https://dot.ca.gov/programs/local-assistance/guidelines-and-procedures/local-assistance-procedures-manual-lapm. In particular, Recipients should prepare for the Right of Way project phase by reviewing Attachment 16, the Right of Way Certification Form 13B (NEVI). This attachment is included as an informational item because, if awarded, Applicants will be responsible for completing the Right of Way Certification Form 13B as part of the Scope of Work (Attachment 15). All Applicants are encouraged to familiarize themselves with this attachment in the application phase.

The Right of Way Certification is to document that real property interests have been or are being secured, and physical obstructions, including buildings, utilities, and railroads, have been or will be removed, relocated, or protected as required for the construction, operation, and maintenance of the proposed federally funded project. The Right of Way Certification also documents that right of way activities were conducted in accordance with applicable policies and procedures outlined in the LAPM.

## Match Funding Requirements

- Total Match Share Requirement

For this solicitation, applications must include exactly 20 percent total match share of total allowable project cost. Example: A project for with a total allowable project cost of $5 million must have a budget with exactly $4 million in reimbursable share and $1 million in match share.)

“Match funding” or “match share” means cash or in-kind (non-cash) contributions provided by the Applicant/Recipient, subrecipients, or other parties that will be used in performance of the proposed project. Match share percentage is calculated by dividing the total match share contributions by the total allowable project cost. “Total allowable project cost” is the sum of the CEC’s reimbursable share and Recipient’s match share of the project costs. Match share expenditures have the following requirements:

- Total match share must conform to the “Cash Match Share Requirement” contained in this solicitation.

- All match share expenditures must conform to the terms and conditions of this solicitation and the resulting grant agreement.

- Applicants must disclose the source and provide verification and documentation for the match share funding committed to the project. For any match share committed by a third party (i.e., other than match share committed by the Applicant), Applicants must submit a letter of commitment from each match share partner identifying the source(s) and availability of match funding.

- During the term of the grant agreement, Recipients will be required to document and verify all match share expenditures through invoices submitted to the CEC.

- Match share funding may be in the form of cash or in-kind contributions such as donated labor hours and equipment.

- Equipment may count as match funds as long as the value of the contribution is based on documented market values or book values, prorated for its use in the project, and depreciated or amortized over the term of the project using generally accepted accounting principles (GAAP).

- Match share expenditures (cash and/or in-kind) must be documented, reasonable, allowable, and allocable to the project as determined by the CEC. Applicants proposed for award and that included in-kind match share in their budget will need to prepare a written description of in-kind match as explained in Section 3.9 Flexible Match in the Local Assistance Procedures Manual (found at https://dot.ca.gov/programs/local-assistance/guidelines-and-procedures/local-assistance-procedures-manual-lapm) for FHWA approval of the in-kind match share sources.

- Match share expenditures are allowable under an agreement only if they are incurred after an agreement is fully executed with the CEC and after E-76 approval (FHWA authorization) for the relevant project phase. Match expenditures incurred prior to the execution of an agreement and before E-76 approval (FHWA authorization) will not be eligible costs. The CEC is not liable for Applicant’s match share costs if the grant is not executed, if execution is delayed, or if the match share expenditure is not allowable by FHWA or under the terms and conditions of the grant. Please note that non-match expenditures incurred prior to agreement execution and E-76 approval (FHWA authorization) are not reimbursable.

- Cash Match Share Requirement

Applications must include a minimum 50 percent cash match share. (Example: If a project proposes $1 million in match share, $500,000 or more must be cash match and the remaining $500,000 can be in-kind match.)

Cash match means the net of any funds actually expended by the Applicant for the project. Net means after any sort of discount or rebate is applied. Expenditures for Applicant’s compensated labor hours, including allowable fringe benefit and overhead rates, travel, materials, supplies, equipment, subrecipient costs, and other miscellaneous expenditures may be claimed as cash match if the expenditures are included in the approved agreement budget, paid in full with funding sources other than CEC funds, including block grants funded by the CEC, and supported with appropriate documentation, including proof of payment. For indirect overhead, backup documentation, such as a cost allocation plan based on actual expenditures incurred and paid, is required. Cost allocations must be reasonable and allocable to the proposed project.

- In-Kind Match Share

The balance of the total match share requirement beyond the cash match share requirement (if any) may be met through in-kind match share contributions.

Applications that move to an executed agreement will require FHWA approval (separate from E-76 approval) for any in-kind match funding sources. Applicants may propose in-kind match funding in their proposal’s budget. If FHWA does not approve the in-kind match source(s), then the Applicant must replace the ineligible match sources and will still be liable for the total match funding in the grant agreement. Please reference Section 3.9 Flexible Match in the Local Assistance Procedures Manual at https://dot.ca.gov/programs/local-assistance/guidelines-and-procedures/local-assistance-procedures-manual-lapm for more information.

In-kind match share contributions are: 1) non-cash contributions provided by the Applicant; 2) cash or non-cash contributions provided by subrecipients; and 3) cash or non-cash contributions provided by other third parties. Applicant in-kind match share can be in the form of volunteer labor, existing equipment, existing supplies, and services provided by a third-party or subcontract. The value of in-kind match is based on the fair market value of the goods and services provided at the time it is claimed as match. In-kind match share must be included in the agreement budget and supported with appropriate documentation. Cost allocations must be reasonable and allocable to the proposed project.

- Match Share Restrictions

- Other Sources of CEC Funding – Other sources of CEC funding may not be claimed as match share. This includes block grants funded by the CEC.

- Other Sources of Federal Funding - Other sources of Federal funding may not be claimed as match share, unless specifically allowed by law to be used as non-Federal match.

- Funds Already Expended or Otherwise Encumbered – Applicants cannot claim funds that have already been expended or otherwise encumbered as match share. Match share expenditures are only allowable if they are incurred after an agreement is fully executed with the CEC and after E-76 approval (FHWA’s authorization of the project).

- Investor-Owned Utility Program Funding – Funding provided through utility tariff programs may not be used as match share.

- Documentation – If selected for an award, all claimed match share expenditures must be adequately documented to the CEC during the agreement invoicing process.

## D.	Unallowable Costs (Reimbursable or Match Share)

For an item of cost to be allowable for reimbursement with CEC funds or as match share expenditure, it must be included in the executed agreement budget and allowable per the terms and conditions of the resulting agreement. The following are examples of unallowable costs under an agreement resulting from this solicitation. This list is not comprehensive and additional items of cost may be unallowable in accordance with the agreement terms and conditions.

- Forgone Profit – For example, if a company usually charges 10% profit but only charges 4% to the CEC the unclaimed difference is not an allowable item of cost.

- Forgone Rent – For example, rent that is not paid is not an allowable item of cost.

- Discounted or Refunded Equipment Costs – For example, a claim that equipment costs $10,000 but the grant recipient only pays $6,000 due to some “special” discount. The difference of $4,000 is not an allowable match share expense. Another example is if the grant recipient actually pays $10,000 but the vendor refunds $4,000 – only the net $6,000 is an allowable item of cost.

- Forgone Salary, Fringe, Indirect or Other Types of Cost – For example, a person normally charges or is paid $100 per hour but will only charge $50 per hour towards the CEC award. Only actual costs incurred and paid to the employee are allowable. Therefore, if an employee is actually paid $100 per hour and the CEC only reimburses at $40 per hour, then the unreimbursed $60 per hour is an allowable match share cost because this is an actual payment as opposed to a forgone salary amount. Volunteer labor (i.e., labor from a person who does not receive any compensation for their labor) may be an allowable in-kind match share expense if the value of the labor is reasonable and justified.

- Utility Provided Electrical Upgrades and Funding-– For example, expenses that are already paid or to be paid for through a utility program, tariff, or other ratepayer funding is not an allowable item of cost. This includes ratepayer-funded enrollment incentives.

- Compliance with Local, Regional, State, or Federal Law, Rule or Regulation - For example, expenses associated with ensuring compliance with state or federal building codes, including provisions of the California Green Building Standards Code requiring the installation of a minimum amount of electric vehicle supply equipment, Electric Vehicle Capable, or Electric Vehicle Ready parking spaces, is not an allowable item of cost.

- LD EV Charging – For example, the cost of planning, procuring, installing, maintaining, or operating EV charging that is intended primarily for the purpose of recharging LD EVs.

# III.	Application Format, Required Documents, and Delivery

## Required Format for an Application

This section contains the format requirements and instructions on how to submit an application. The format is prescribed to assist the Applicant in meeting State requirements and to enable the CEC to evaluate each application uniformly and fairly. Applicants must follow all application format instructions, answer all questions, and supply all requested information.

All applications submitted under this solicitation must be typed or printed using a standard 11-point font, single-spaced and a blank line between paragraphs.  Pages must be numbered, and sections titled.

## Method for Delivery

The method of delivery for this solicitation is the Energy Commission Agreement Management System (ECAMS), available at https://ecams.energy.ca.gov/.

Information about ECAMS will be provided at the Pre-Application Workshop. Information about how to register for an ECAMS account and guidance on how to apply through the system is available at https://www.energy.ca.gov/funding-opportunities/funding-resources under General Funding Information.

The CEC is providing a team of technical assistants to support Applicants with this process. Please email ECAMS.SalesforceSupport@energy.ca.gov for support.

ECAMS allows Applicants to complete and submit their application to the CEC prior to the date and time specified in this solicitation. Files uploaded to the system must be in Microsoft Word (.doc format) and Excel Office Suite formats unless originally provided in the solicitation in another format. PDF format is acceptable. The completed Proposal Budget Template, Attachment 3, must be in Excel format.

The deadline to submit grant applications through ECAMS is 11:59 p.m. ECAMS automatically closes at 11:59 p.m. If the full submittal process has not been completed before 11:59 p.m., your application will not be considered. NO EXCEPTIONS will be entertained.

The CEC strongly encourages Applicants to upload and submit all applications by 5:00 p.m. because CEC staff will not be available after 5:00 p.m. or on weekends to assist with the upload process. And please note that while we endeavor to assist all would-be Applicants, we cannot guarantee staff will be available for consultation on the due date, so please plan accordingly.

Please give yourself ample time to complete all steps of the submission process: do not wait until right before the deadline to begin the process. Due to factors outside the CEC’s control and unrelated to ECAMS, upload times may be much longer than expected. For example, some past Applicants experienced unexpected issues on their end, causing long delays that prevented timely submission. They spent significant time and resources on applications the CEC will not consider.

Please plan accordingly. First time users must register as a new user to access the system. There will be two types of user accounts to establish: 1) An organizational account, for the entity applying to the solicitation; and 2) user accounts for individuals who will be submitting the application on behalf of the organization.

Applicants will be required to upload all attachments marked “required” in the Fsystem in order for the application to be submitted.

## Solicitation Informational Documents

In addition to this solicitation manual, the following attachments are available on the solicitation webpage as informational documents to consider in preparing applications:

  - Scope of Work (Attachment 15)

If awarded, this document will be included as part of the recipient agreement. The Scope of Work outlines tasks to be completed under this solicitation as well as project and recipient-specific information to be filled in during agreement development

  - Right of Way Certification Form 13B (NEVI) (Attachment 16)

If awarded, recipients will complete this form to document the Right of Way (R/W) or rights in real property that may be required for each EV charging station. It has been customized for the NEVI formula program.

## Application Content

Items listed below are required as part of the application package. Failure to provide any items may result in disqualification of the application. Attachment requirements are expanded and explained below in this section and in the attachments themselves. Note that Letters of Support (Attachment 13) are optional.

| Item | Attachment Number |
| --- | --- |
| Project Narrative | Attachment 1 |
| Schedule of Products and Due Dates | Attachment 2 |
| Proposal Budget | Attachment 3 |
| Letters of Commitment | Attachment 4 |
| Preliminary Site Plan | Attachment 5 |
| CEQA Worksheet | Attachment 6 |
| National Environmental Policy Act (NEPA) Preliminary Environmental Study (PES) Form | Attachment 7 |
| Utility Verification Form | Attachment 8 |
| Resumes | Attachment 9 |
| Contact List | Attachment 10 |
| Past Performance Reference Form(s) | Attachment 11 |
| Applicant Declaration | Attachment 12 |
| Letters of Support (Optional) | Attachment 13 |
| Restricted Access Letters or Agreements (If Required) | Attachment 14 |

- Applicant Certifications

ECAMS will require Applicants to provide the required authorizations and certifications listed below prior to final submission of their application:

All Applicants must certify under penalty of perjury under the laws of the State of California that:

- I am authorized to submit this application on behalf of the Applicant.

- I authorize the CEC to make any inquiries necessary to verify the information presented in this application.

- I authorize the CEC to obtain business credit reports and make any inquiries necessary to verify and evaluate the financial condition of the Applicant.

- I have read and understand the terms and conditions contained in this solicitation. I accept the terms and conditions contained in this solicitation on behalf of the Applicant and the Applicant is willing to enter into an agreement with the CEC to conduct the proposed project according to the terms and conditions without negotiation.

- I certify that (1) this application does not contain any confidential or proprietary information, or (2) if confidential information is allowed under the solicitation, it has been properly identified.

- I certify under penalty of perjury under the laws of the State of California that, to the best of my knowledge, the information contained in this application is correct and complete.

- I am authorized to agree to the above certifications on behalf of the Applicant.

- Project Narrative (Attachment 1) (Limit: 25 pages)

Applicants must address each of the sections described in Project Narrative (Attachment 1) by providing sufficient, unambiguous detail so that the Evaluation Committee will be able to evaluate the application against each scoring criterion (see Section IV.A. Application Evaluation).

- Schedule of Products and Due Dates (Attachment 2)

Applicants must include a completed Schedule of Products and Due Dates. All EV charging stations, chargers, and supporting equipment should be operational within three (3) years from the agreement execution date. Instructions for the Schedule of Products and Due Dates are included in Attachment 2. The Schedule of Products and Due Dates must be in MS Excel.

- Proposal Budget (Attachment 3)

Applicants must include a completed Proposal Budget for the project, as well as Major Subrecipient Proposal Budgets where a subaward will be $100,000 or more (explained in more detail below). Applicants must upload all budgets (Prime and Major Subrecipients) as MS Excel attachments and leave the ECAMS budget sections blank in ECAMS.

The Applicant must submit information on all tabs of the budget forms. The salaries, rates, and other costs entered must reflect the salaries, rates, and other costs the Applicant would include if selected as a grant recipient. A separate set of complete budget forms is required for the Applicant and for each subaward containing $100,000 or more of CEC funds.

    - Detailed instructions for completing these forms are included at the beginning of Attachment 3.

      - Rates and job descriptions shown must reflect rates and job descriptions charged under an agreement resulting from this solicitation. The salaries, rates, and other costs entered on these forms become a part of the final agreement. The entire term of the agreement and projected rate increases must be considered when preparing the budget. Unless a federally approved indirect rate is used, indirect rates proposed are considered capped and shall not change during the term of the agreement. The grant recipient shall only be reimbursed for their actual rates up to the indirect rate cap. A description of available indirect rate options is available on the ECAMS Resources webpage under Budget Category Guidance for indirect rates. Unlike indirect rates, the rates for Direct Labor and Fringe Benefits are treated as estimates; a grant recipient can invoice at higher rates as long as it is only invoicing for actual expenditures it has made. The hourly or monthly rates provided shall be unloaded (before fringe benefits or indirect costs).

      - The information provided in these forms will not be kept confidential.

      - All reimbursable expenditures must be expended within the approved term of the grant agreement. Expenditures may be counted as reimbursable or match share only after an agreement is executed and the FHWA authorizes the relevant project phase (E-76 approval).

      - Applicants must budget for the expenses of a Kick-off Meeting, at least one (1) Critical Project Review meeting, and a Final meeting. Meetings may be conducted at the CEC or remotely, as determined by the CAM.

      - Applicants must budget for the preparation and submission of quarterly progress reports during the term of the agreement.

      - The purchase of equipment (defined as items with a unit cost greater than $5,000 and a useful life of greater than one year) with CEC funds will require disposition of purchased equipment at the end of the project. Typically, grant recipients may continue to utilize equipment purchased with CEC funds as long as the use is consistent with the intent of the original agreement. There are no disposition requirements for equipment purchased with match share funding.

    - The Budget must reflect estimates for actual costs to be incurred during the approved term of the agreement. The CEC can only approve and reimburse for actual costs that are properly documented in accordance with the grant agreement terms and conditions.

    - Current policy dictates that Applicants shall NOT budget for, and CANNOT be reimbursed for, more than their actual allowable expenses (i.e., the budget cannot include profit, fees, or markups) under the agreement. Subrecipients (all tiers) are allowed to include up to a maximum total of 10% profit, fees or mark-ups on their own actual allowable expenses less any expenses budgeted to sub-subrecipients (i.e., profit, fees and markups are not allowed on lower tier subrecipient expenses). For example, if a subrecipient has $100,000 in actual allowable costs but has budgeted $20,000 to a sub-subrecipient, then the subrecipient can only include up to 10% profit on $80,000 ($100,000 minus $20,000). See terms and conditions for additional restrictions and requirements.

IMPORTANT – Payment of Prevailing Wage: Applicants must read and pay particular attention to the terms and conditions section related to Public Works and payment of Prevailing Wages. Prevailing wage rates can be significantly higher than non-prevailing wage rates. Failure to pay legally required prevailing wage rates can result in substantial damages and financial penalties, termination of the grant agreement, disruption of projects, and other complications.

- Letters of Commitment (Attachment 4)

Applicants must submit the following letters of commitment. A commitment letter commits an entity or individual to providing the service or funding described in the letter. Site control documentation must be submitted for the proposed charging station in the application.

  - Key Project Partners: Key project partners identified in the application must provide letters demonstrating their ability to fulfill their identified roles. Letters are limited to two (2) pages each.

  - Match Share Contributors Letters of Commitment: Any match share contributors (including the Applicant and/or a third-party) must identify the intended amount of match that will be committed to the project, the funding source(s), and state that the match share contributor will provide the identified match funding. Letters of commitment from match share contributors must contain a telephone number and email address to allow the CEC to contact the match share partner or representative to confirm their authority to commit matching funds to the proposed project. Letters are limited to two (2) pages each.

  - Site Control Documentation: Documentation explaining lease arrangements, ownership or access rights for the proposed site. Documentation may include but not be limited to: a lease, site host agreement, memorandum of understanding, letter of intent, or property deed. No page limit per document.

- Preliminary Site Plan (Attachment 5)

Applicants must submit a preliminary site plan for the proposed EV charging station in the application.

The preliminary site plan must include the following at a minimum:

- Address of the EV charging station

- Map of the charging station showing the following:

  - Location of all existing charging ports at the charging station (if applicable). Specify the power delivery rate for each existing port (if applicable).

  - Location of all ports proposed to be installed. Specify the power delivery rating planned for each charging port.

  - Location of ADA accessible ports.

  - Location of lighting and shelter (if applicable).

  - Travel path (ingress/egress) from the charging station.

- CEQA Worksheet (Attachment 6)

Applicants must include a completed CEQA Worksheet. The CEC requires this information to assist it in making its own determination under the California Environmental Quality Act (Public Resources Code Section §§ 21000 et seq).

The CEQA worksheet(s) will help Applicants and the CEC to determine CEQA compliance obligations by identifying which projects may require more extensive CEQA review, and it will be used to help evaluate the Project Readiness evaluation criterion in this solicitation (see Section IV.E.2). Failure to complete the worksheet(s) may lead to disqualification of the application.

Applicants are encouraged to provide documentation of communication with the local lead agency, if one exists (e.g., a county or city). Documentation may include a completed notice of exemption, a letter from the local agency acknowledging its role in the CEQA process, or a permit application to the lead agency that is stamped as received. If no CEQA review would be required by the local lead agency, provide documentation (e.g. a letter or e-mail) from the local agency explaining why CEQA review is not required.

  - Additional Requirements

- Time is of the essence. Prior to approval of the agreement at a CEC business meeting, the CEC must comply with CEQA. To comply with CEQA, the CEC must have CEQA-related information from Applicants and sometimes other entities, such as local governments, in a timely manner. For example, if a project requires an Environmental Impact Report, the process to complete it can take many months. It is critical that Applicants organize project proposals in a manner that minimizes the time required for the CEC to comply with CEQA and provide all CEQA-related information to the CEC in a timely manner. Projects recommended for funding must complete the CEQA process within 6 months of the release date of the NOPA. The CEC reserves the right to cancel proposed awards that do not meet this CEQA deadline and recommend funding for the next highest scoring passing proposal for that Project Region according to the evaluation process discussed in Section I.D. How Award is Determined.

- Reservation of right to cancel proposed award. In addition to any other right reserved to it under this solicitation or that it otherwise has, if the CEC determines, in its sole and absolute discretion, that the CEQA review associated with a proposed project would not likely be completed in a timely manner, or that the CEC’s ability to meet its encumbrance deadline may be jeopardized, the CEC may cancel a proposed award and award funds to the next highest scoring passing proposal for that Project Region according to the evaluation process discussed in Section I.D. How Award is Determined, regardless of the originally proposed Applicant’s diligence in submitting information and materials for CEQA review. Examples of situations that may arise related to CEQA review include but are not limited to:

    - Example 1: If another state agency or local jurisdiction, such as a city or county, must take the role of lead agency under CEQA, the CEC’s review may be delayed while waiting for a determination from the lead agency.

    - Example 2: If the proposed work is part of a larger project for which a detailed environmental analysis has been or will be prepared by another state agency or local jurisdiction, the CEC’s review may be delayed as a result of waiting for a supplemental or initial analysis, respectively, from the other agency.

    - Example 3: If the nature of the proposed work is such that a project is not categorically or otherwise exempt from the requirements of CEQA, and an initial study or other detailed environmental analysis appears to be necessary, the CEC’s review, or the lead agency’s review, may take longer than the time available to encumber the funds. If an initial study or environmental impact report has already been completed by another state agency or a local jurisdiction, serving as the lead agency, the Applicant must ensure that such an analysis covers the work in the proposed project, or must obtain a revised analysis and determination from the lead agency reviewing the proposed project.

    - Example 4: If the proposed project clearly falls under a statutory or categorical exemption or is a project for which another state agency or local jurisdiction has already adopted a CEQA finding that the project will cause no significant effect on the environment, the project will likely have greater success in attaining rapid completion of CEQA requirements.

- The above examples are not exhaustive of instances in which the CEC may or may not be able to comply with CEQA in a timely manner and are only provided as further clarification for potential applicants. Please plan project proposals accordingly.

- National Environmental Policy Act (NEPA) Preliminary Environmental Study (PES) Form (Attachment 7)

Applicants must fully complete the Pilot NEPA PES form. This form will help Applicants, the CEC, and Caltrans determine NEPA compliance obligations by identifying which projects may require additional environmental study (e.g., biological or cultural) to finalize NEPA compliance.

If awarded under this solicitation, Applicants will have the opportunity to review and update this form before official submission to Caltrans for NEPA review.

Applicants should review Exhibit 6-B: Instructions for Completing the Preliminary Environmental Study (PES) Form found at https://dot.ca.gov/-/media/dot-media/programs/local-assistance/documents/env/pes-instructions.pdf to complete the form. Applicants may also review the Example Pilot PES Form found at https://dot.ca.gov/-/media/dot-media/programs/local-assistance/documents/env/lapm6a-example.pdf for an example of a fully completed form.

Applicants must complete all fields in a yellow box to advance to subsequent sections of the form. Input “N/A” into Section 1.3 “Federal Project Number” and Section 1.6 “District Local Assistance Engineer.” Input your own organization and contact information into Section 1.7. The answer to Section 1.8 should be “No.” Select “Yes” for Section 1.10.

Applicants should prepare the required attachments listed in Section 5 of the pilot NEPA PES form. In particular, two attachments will be used to help evaluate the Project Readiness evaluation criteria in this solicitation (see Section IV.E.2):

- GeoTracker Printout for Hazardous Materials. For this attachment, use the State Water Resources Control Board Geo Tracker found at https://geotracker.waterboards.ca.gov/ to determine if any of the proposed EV charging station addresses are located within a 1,000-foot radius of any of the following:

  - Leaking Underground Storage Tank (LUST) Cleanup Site

  - Cleanup Program Site

  - Military Cleanup Site

  - Military Privatized Site

  - Military Underground Storage Tank (UST) site

Include two screenshots of the map search results with the NEPA PES Form (Attachment 7) for each proposed EV charging station:

- The first screenshot showing the address of the site with the 1,000-foot radius. After searching for the site address, the site will load with a box showing the address of the site and an option to create a radius. Enter 1,000 feet to create a radius around the address. Take a screenshot showing the address box with the number of feet and the radius around the site.

- For the second screenshot click the ‘X’ to close the address box to only show the radius around the site. Take a screenshot showing the full radius with any potential hazardous waste sites within.

- FEMA map. For this attachment, use the FEMA Flood Map Service Center at https://msc.fema.gov/portal/search to determine if any of the proposed EV charging station addresses are located in a Special Flood Hazard Area (SFHA). SFHAs are labeled as:

Zone A, Zone AO, Zone AH, Zones A1-A30, Zone AE, Zone A99, Zone AR, Zone AR/AE, Zone AR/AO, Zone AR/A1-A30, Zone AR/A, Zone V, Zone VE, and Zones V1-V30.

Include the address of the site and a screenshot of the map search results with the NEPA PES Form (Attachment 7) for each proposed EV charging station.

No signatures are needed on this form at the time of application.

Reservation of right to cancel proposed award. In addition to any other right reserved to it under this solicitation or that it otherwise has, if the CEC determines, in its sole and absolute discretion, that the NEPA review associated with a proposed project would not likely be completed in a timely manner, or that the CEC’s ability to meet its encumbrance deadline or any other NEVI-related deadline may thereby be jeopardized, the CEC may cancel a proposed award and award funds to the next highest scoring passing proposal for that Project Region according to the evaluation process discussed in Section I.D. How Award is Determined, regardless of the originally proposed Applicant’s diligence in submitting information and materials for NEPA review.

- Utility Verification Form (Attachment 8)

Applicants must complete a Utility Verification Form. The form will be used to evaluate the level of readiness of the proposed charging station. Instructions for completing the Utility Verification Form are included in Attachment 8. Applicants may need assistance from the utility company serving the area where the proposed charging station is located to complete the form. If this is required, Applicants should contact the utility company as soon as possible to understand their timelines to complete the verification form.

- Resumes (Attachment 9)

Applicants must include resumes for key personnel identified in the proposal. “Key personnel” are individuals that are critical to the project due to their experience, knowledge, and/or capabilities. Resumes are limited to a maximum of 2 pages each, consolidated into one attachment.

- Contact List (Attachment 10)

Applicants must include a completed Contact List by including the appropriate points of contact for the Applicant. The CEC will complete the CEC points of contact during agreement development.

- Past Performance Reference Form(s) (Attachment 11)

Applicants must complete and submit a separate Past Performance Reference Form for each CEC agreement (e.g., contract, grant, or loan) received by the Applicant in the last 10 years, including ongoing agreements, and the 5 most recent agreements with other public agencies within the past 10 years.

- Applicant Declaration (Attachment 12)

This form requests the Applicant declare that they are not delinquent on taxes nor suspended by the California Franchise Tax Board; are not being sued by any public agency or entity; are in compliance with the terms of all settlement agreements, if any, entered into with the CEC or another public agency or entity; are in compliance with all judgments, if any, issued against the Applicant in any matter to which the CEC or another public agency or entity is a party; are complying with any demand letter made on the Applicant by the CEC or another public agency or entity; and are not in active litigation with the CEC regarding the Applicant’s actions under a current or past contract, grant, or loan with the CEC. The declaration must be signed under penalty of perjury by an authorized representative of the Applicant’s organization.

- Letters of Support (Attachment 13 - optional)

Applicants are encouraged to submit letter(s) of support that substantiate the estimated demand and/or the potential benefits of the proposed project. Third-party letters of support can be provided by, but are not limited to: air districts, state or federal agencies, local safety officials, potential users of the proposed project, community-based organizations, and any other relevant organizations. Letters are limited to two-pages each, consolidated into one attachment.

- Restricted Access Letters or Agreements (Attachment 14 – if required)

For Applications for Restricted Access stations, or Hybrid Access stations that include charging ports with restricted access, the Application must include signed agreements or letters of intent from more than one commercial motor vehicle operator, attesting to their intended use of the charging station. The agreements or letters must describe the commercial motor vehicle operator’s vehicles that will be utilizing the restricted access equipment, including the vehicles’ quantity and type.

# IV.	Evaluation Process and Criteria

## Application Evaluation

Applications will be evaluated and scored based on the responses to the information requested in this solicitation and on any other information available such as past performance of CEC agreements. The entire evaluation process from receipt of applications to posting of the Notice of Proposed Award is confidential.

To evaluate applications, the CEC will organize an Evaluation Committee. The Evaluation Committee may consist of CEC staff or staff of other California state entities.

  - Screening Criteria

The CEC’s Contracts, Grants, and Loans Office will screen applications for compliance with the Administrative Screening Criteria. The Evaluation Committee will screen applications for compliance with the Technical Screening criteria. Applications that fail any of the Administrative or Technical Screening Criteria shall be disqualified and eliminated from further evaluation.

  - Administrative Screening Criteria

| ADMINISTRATIVE Screening Criteria | Pass/Fail |
| --- | --- |
| - The application is received by the CEC by the due date and time specified in the “Key Activities Schedule” in Section I of this solicitation. | Pass Fail |
| - The Applicant has not included a statement that is contrary to the required authorizations and certifications when submitting in ECAMS. | Pass Fail |

  - Technical Screening Criteria

| Technical Screening Criteria | Pass/Fail |
| --- | --- |
| - The Applicant is an eligible Applicant. | Pass Fail |
| - The project meets the requirements described in Section II.B.4, Megawatts Per EV Charging Station, Number of EV Charging Ports, and Connector Types requirements. | Pass Fail |
| - The project team requirements described in Section II.B.7 are met. | Pass Fail |
| - The project meets the minimum match share requirement specified in Section II.C. | Pass Fail |
| - The Applicant passes the past performance screening criterion. | Pass Fail |

  - Applicant’s Past Performance Screening Criteria (Pass/Fail)

An Applicant may be disqualified under this solicitation due to severe performance issues under one or more prior or active CEC agreement(s) within the last 10 years. For the purposes of this screening criterion an Applicant is defined as either (a) an entity, principal investigator, or lead individual acting on behalf of themselves, that received funds from the CEC (e.g. a contract, grant, or loan) and entered into an agreement(s) with the CEC; or (b) an entity, principal investigator, or lead individual that received a CEC-funded incentive. Any Applicant that does not have an active or prior agreement and has not received a CEC-funded incentive equates to no severe performance issues and therefore would pass this screening criterion.

Severe performance issues are characterized by significant negative outcomes under an agreement and may include:

  - Agreement was terminated with cause.

  - The CEC filed litigation against the Applicant.

  - Severe audit findings are not resolved to the CEC’s satisfaction. Severe audit findings may include but are not limited to: incomplete or unsatisfactory deliverables; grant funds used inappropriately (i.e., other than as represented); or questioned costs.

  - Project objectives were not met.

  - Significant delays in project completion resulting in delayed benefits for California. Project completion delays of one year or more from the originally proposed project schedule and caused by factors within the Applicant’s control may be considered significant.

  - Deliverables were not submitted to the CEC or were of poor quality. For example, Applicant delivered poorly written reports that required significant rework by staff prior to acceptance or publication.

  - Demonstrated poor or delayed communication when significant issues or setbacks were experienced that materially and negatively impacted the project. For example, delays in informing the CEC when the Applicant experiences loss of a key project partner or site control may be considered significant.

  - Grounds to Reject an Application or Cancel an Award

In addition to the Screening Criteria identified within this solicitation, the CEC reserves the right to reject an application and/or cancel an award for reasons including, but not limited to the following:

- The application contains false or intentionally misleading statements or references which do not support an attribute or condition contended by the Applicant.

- The application is intended to erroneously and fallaciously mislead the State in its evaluation of the application and the attribute, condition, or capability is a requirement of this solicitation.

- The application does not comply or contains caveats that conflict with the solicitation and the variation or deviation is material or it is otherwise non-responsive.

- The CEC, in its sole discretion, determines the Applicant’s, a subrecipient’s, or a vendor’s financial condition may materially impact its ability to complete the proposed project.

  - Technical Evaluation

Applications passing all screening criteria will be submitted to the Evaluation Committee to review and score based on the Evaluation Criteria using the Scoring Scale described below.

The Evaluation Committee reserves the right to schedule a clarification interview with an Applicant to clarify and/or verify information submitted in the application. However, these interviews may not be used to change or add to the contents of the original application. Applicants will not be reimbursed for time spent answering clarifying questions.

The total score for each application will be the average of the combined scores of all Evaluation Committee members. A minimum score of 70 percent is required for the application to be eligible to advance to Cost Evaluation. In addition, a minimum score of 70 percent is required on both Technical Evaluation Criterion 2, Project Readiness, and Technical Evaluation Criterion 4, Project Budget and Finances, to advance to Cost Evaluation.

  - Cost Evaluation

All applications that receive a minimum passing score of 70 percent or higher in the Technical Evaluation portion of scoring (both overall and for Technical Evaluation Criterion 2 and 4 individually) as described in previous sections will advance to Cost Evaluation. Advancement to Cost Evaluation signifies that the project meets the minimum threshold for funding eligibility. The Evaluation Committee will then apply a cost-efficiency ranking system to prioritize projects based on their proposed use of CEC funds.

Projects will be ranked within their Project Region and scored based on two cost metrics for up to 100 points:

- Cost-per-new-CCS-Port (up to 50 points)

  - Cost-per-new-CCS is calculated by dividing the total CEC dollars requested by the number of new CCS ports

- Cost-per-kW of New Capacity (up to 50 points)

  - Cost-per-kW of New Capacity is calculated by dividing the total CEC dollars requested by the total new capacity

For each metric:

- Projects will be ranked from lowest to highest cost.

- The project with the lowest Cost-per-new-CCS-Port and the lowest Cost-per-kW of new capacity will receive the maximum score of 50 points each.

- Subsequent projects will receive decreasing scores in 5-point increments (e.g., 45, 40, 35, etc.), based on their relative cost position in the ranking.

- If multiple projects share the same cost value, they will receive the same score, and the next score will be skipped accordingly.

- The final score for each project will be calculated by summing the scores from both cost metrics.

## Notice of Proposed Awards

The results of the evaluation will be posted in a Notice of Proposed Awards (NOPA) and will include (1) the total proposed funding amount; (2) the rank order of Applicants; and (3) the amount of each proposed award. CEC will publish the NOPA on the CEC’s website.

## Debriefings

Applicants that are not proposed for funding may request a debriefing after the release of the NOPA by e-mailing the CAO listed in Part I. A request for debriefing should be received no later than 15 calendar days after the NOPA is released.

## Scoring Scale

Using this Scoring Scale, the Evaluation Committee will give a score for each criterion described in the Evaluation Criteria.

| % of Possible Points | Interpretation | Explanation for Percentage Points |
| --- | --- | --- |
| 0% | Not Responsive | Response does not include or fails to address the requirements being scored. The omission(s), flaw(s), or defect(s) are significant and unacceptable. |
| 10-30% | Minimally Responsive | Response minimally addresses the requirements being scored. The omission(s), flaw(s), or defect(s) are significant and unacceptable. |
| 40-60% | Inadequate | Response addresses the requirements being scored, but there are one or more omissions, flaws, or defects or the requirements are addressed in such a limited way that it results in a low degree of confidence in the proposed solution. |
| 70% | Adequate | Response adequately addresses the requirements being scored. Any omission(s), flaw(s), or defect(s) are inconsequential and acceptable. |
| 75% | Between Adequate and Good | Response better than adequately addresses the requirements being scored. Any omission(s), flaw(s), or defect(s) are inconsequential and acceptable. |
| 80% | Good | Response fully addresses the requirements being scored with a good degree of confidence in the Applicant’s response or proposed solution. No identified omission(s), flaw(s), or defect(s). Any identified weaknesses are minimal, inconsequential, and acceptable. |
| 85% | Between Good and Excellent | Response fully addresses the requirements being scored with a better than good degree of confidence in the Applicant’s response or proposed solution. No identified omission(s), flaw(s), or defect(s). Any identified weaknesses are minimal, inconsequential, and acceptable. |
| 90% | Excellent | Response fully addresses the requirements being scored with a high degree of confidence in the Applicant’s response or proposed solution. Applicant offers one or more enhancing features, methods or approaches exceeding basic expectations. |
| 95% | Between Excellent and Exceptional | Response fully addresses the requirements being scored with a better than excellent degree of confidence in the Applicant’s response or proposed solution. Applicant offers one or more enhancing features, methods or approaches exceeding basic expectations. |
| 100% | Exceptional | All requirements are addressed with the highest degree of confidence in the Applicant’s response or proposed solution. The response exceeds the requirements in providing multiple enhancing features, a creative approach, or an exceptional solution. |

## Technical Evaluation Criteria

| Criterion | Possible Points |
| --- | --- |
| - EV Charging Station Location and Equipment Applications will be evaluated on the degree to which: - The justification for the proposed EV charging station location is compelling, effectively addressing the needs of a clearly identified customer base. - The proposed EV charging station location will be easily accessible from the Alternative Fuel Corridor and the distance within one mile or closer of an exit (either an offramp or highway intersection) is verified using a distance measuring tool. - The types of charging equipment, number of charging ports, and types of connectors chosen are justified with clear reasoning based on expected customer needs. - The proposed EV charging station is not located at or adjacent to an existing site where MDHD EV charging already occurs. - The EV charging station site design has the customer experience in mind, including appropriate lighting, shelter, and stall configurations to support a variety of customer needs. Stall configurations will allow for easy navigation and, if serving both, LD and MDHD customer stalls will be clearly differentiated and safely separated. - The proposed project’s EV charging station has convenient onsite or nearby amenities that enhance customer experience. - The grid connection and its capacity, and other renewable DER equipment, such as solar arrays and BESS, will provide reliable power supply at each EV charging station. Any renewable DER equipment will deliver benefits such as reduced costs to customers and improved reliability and will not substantially increase the project timeline. | 10 |
| - Project Readiness Applications will be evaluated on the degree to which: - Site control or access rights for the proposed EV charging station property is secured. If control or access rights are not secured at the time of application, there is a credible and time-efficient plan for securing control or access rights. - The owner and operator of the proposed EV charging station and its equipment are clearly identified and ready to assume those responsibilities. - Due diligence has been conducted for the proposed EV charging station site, including research into the site’s zoning and progress made in obtaining needed planning approvals and permits. - Progress has been made in obtaining a CEQA determination for the EV charging station, from outreach to the local authority having jurisdiction up to actual receipt of a notice of exemption or a determination that no CEQA review is required. - The proposed EV charging station site is not in Special Flood Hazard Areas (SFHA) and does not have open cleanup cases within a 1,000-foot radius. - There is available electrical capacity enabling timely station electrification for the proposed EV charging station. - The timeline for obtaining EV chargers and other proposed equipment is minimized and supported by verifiable documentation from the manufacturer(s). - There are backup sites already identified, or the Applicant has a process in place to expeditiously select a new EV charging station site in the event the charging station location must be changed. NOTE: Project Readiness must obtain a minimum passing score of 21 points (70 percent) within this evaluation criterion to be eligible for funding. | 30 |
| - Expected Project Benefits Applications will be evaluated on the degree to which: - The cost to charge for drivers will be reduced or minimized, with methods and assumptions explained. - There is demonstrated reason to expect high utilization of the station by MDHD EVs, including specific fleets. - The estimated return on investment is reasonable and supported by plans to build station utilization over time. - Community outreach has been conducted and the surrounding local community will benefit from the installation or expansion of MDHD charging infrastructure. - The proposed project incorporates workforce development and economic benefits to the local communities surrounding the proposed charging station site. - There is a credible plan to meet or exceed the solicitation’s goal of 25 percent small business participation. | 10 |
| - Project Budget and Finances Applications will be evaluated on the degree to which: - The proposed budget maximizes the quantity of proposed eligible charging ports per CEC dollar requested. - The proposed budget maximizes aggregate new charging capacity (kW) across all eligible charging ports per CEC dollar requested. - The rationale for the requested CEC funds, including Cost-per-new-CCS-Port and Cost-per-kW of New Capacity is clear and well-supported. - Administrative and overhead expenses are minimized. - Mach funding commitments are supported by verifiable documentation. - Public funds are necessary for the proposed project. - Income or revenue earned from the operation of the proposed EV charging station will be used in compliance with the federal NEVI standards under 23 CFR 680.106(m), (which require use for debt service, a reasonable return on investment, and/or costs for operation, maintenance, and site improvement) and there is a method in place for documenting compliance during at least the first five years of operations. - There are credible strategies to secure additional capital, as needed, to ensure project success and continued operations and maintenance of the station beyond the term of the funding agreement. NOTE: Project Budget and Finances must obtain a minimum passing score of 21 points (70 percent) within this evaluation criterion to be eligible for funding. | 30 |
| - Operations and Maintenance Plan Applications will be evaluated on the degree to which: - The operations and maintenance (O&M) plan demonstrates an overall ability to achieve an average annual uptime of greater than 97 percent per charging port. - The O&M plan demonstrates strategies to physically secure the site effectively and limit or prevent tampering with or damage to the chargers. - The O&M plan outlines strategies and timelines to provide prompt attention to chargers that are not operational and demonstrates an ability to carry out repairs to maximize uptime. - The O&M plan outlines the availability of site host training and describes the responsibilities of the site host in conducting O&M. - The O&M plan clearly outlines who is responsible for maintaining the charging stations, including all the charging equipment, auxiliary equipment, and applicable supporting elements, such as lighting and restrooms. - The Applicant commits to continuing the proposed project beyond the agreement term and minimum five-year data reporting period. | 10 |
| - Team Experience and Qualifications Applications will be evaluated on the degree to which: - The key personnel assigned to complete the project, including the project manager, and their areas of responsibility are clearly identified. - The project team has members with at least three (3) years of experience designing, planning, constructing, testing, operating, or maintaining EV charging stations, and the qualifications, skills, abilities, and relevant technical and business experience align with the needs and successful completion of the proposed project. - The Applicant or lead installation Subrecipient(s) from the proposed project team meet(s) or exceed(s) the Experienced Contractor definition. - The Applicant’s selected charging station network provider(s) has demonstrated experience keeping chargers in service for five or more years. - The Applicant demonstrates experience with federally funded projects and compliance with federal requirements like the Davis Bacon Act. - The Applicant demonstrates experience meeting deadlines and completing milestones associated with large, complex public projects, including previously successful EV charging projects and: - Adherence to schedules and due dates. - Effective and timely issue resolution. - Quality of deliverables. - Objectives of past projects have been attained. - Honest, timely, and professional communication with staff from the funding entity. - Effective coordination with project partners, subrecipients, vendors, and other stakeholders. - Timely and accurate invoicing. | 10 |
| Total Possible Points | 100 |
| Minimum Passing Score (70%) | 70 |

## Cost Evaluation

All applications scoring 70 percent or higher on the Technical Evaluation Criteria from Section IV.E. (both overall and for Technical Evaluation Criterion 2, Project Readiness, and Technical Evaluation Criterion 4, Project Budget and Finances) will move on to the Cost Evaluation phase. During the Cost Evaluation, applications will be evaluated solely on cost-efficiency metrics where they will be ranked within their Project Region based on:

- Cost-per-New-CCS-Port

- Cost-per-kW of New Capacity

Each metric is scored out of 50 points, for a total of 100 points. Applications with the highest combined Cost-per-New-CCS-Port and Cost-per-kW of New Capacity score of new capacity within their respective Project Region will be recommended for funding first, as described in in Section I.D. How Award is Determined. However, if an application proposes an EV charging station location that is within 50 miles, measured in driving distance, of a higher-ranked application proposed for award under this solicitation, the CEC may, at its sole discretion, select the next ranked application to ensure adequate geographic distribution of funded stations.

The Cost-per-New-CCS-Port is calculated by dividing the total CEC grant dollars requested by the number of ports with a CCS connector proposed to be installed at the station. For example, if the total grant funding request is $2,000,000, and the number of ports to be installed is 20, the Cost-per-New-CCS-Port would be $100,000. The total grant funding request includes all CEC reimbursable costs associated with the capital expenditure required for the EV charging port. This includes, but is not limited to, administrative, design, installation, operations and maintenance, and equipment costs.

Similarly, the Cost-per-kW of New Capacity is calculated by dividing the total CEC grant dollars requested by the total power proposed to be installed at the station. For example, if the total grant funding request is $2,000,000, and the power to be installed is 4MW, the Cost-per-kW of New Capacity would be $500. The total grant funding request includes all CEC reimbursable costs associated with the capital expenditure required for the charging port. This includes, but is not limited to, administrative, design, installation, operations and maintenance, and equipment costs.

## Tie Breakers

If the Cost Evaluation score is the same for two or more applications, the application with a higher score in the Technical Evaluation will be ranked higher. If still tied, the application with a higher score in the Project Readiness criterion will be ranked higher. If still tied, an objective tiebreaker (such as a random drawing) will be utilized. Similarly, if one Applicant has proposed awards exceeding the applicant award cap, this same process will be used to determine which applications are proposed for award.

# V.	Administration

## Definition of Key Words

Important definitions for this solicitation are presented below:

| Word/Term | Definition |
| --- | --- |
| ADA | Americans with Disabilities Act |
| Alternative Fuel Corridor | AFC. In accordance with 23 U.S.C. 151, FHWA has designated alternative fuel corridors to support installation of EV charging, hydrogen, propane, and natural gas fueling infrastructure at strategic locations along major national highways. For the purposes of this solicitation, AFCs refer to those designated for the installation of EV charging infrastructure. |
| API | Application Programming Interface. A type of software interface that offers service to other pieces of software. An API allows two or more computer programs to communicate with each other. |
| Applicant | Respondent to this solicitation |
| Application | Formal written response to this document from applicant |
| BESS | Battery Energy Storage System |
| California Native American Tribe | A Native American tribe located in California that is on the contact list maintained by the Native American Heritage Commission for the purposes of Chapter 905 of the Statutes of 2004. |
| California Tribal Organization serving a California Native American Tribe | A corporation, association, or group controlled, sanctioned, or chartered by a California Native American Tribe that is subject to its laws, the laws of the State of California, or the laws of the United States. |
| Caltrans | California Department of Transportation |
| CAM | Commission Agreement Manager |
| CAO | Commission Agreement Officer |
| CCS | Combined Charging System. A charging port standard for fast charging of EVs that can provide up to 350 kilowatts of power. |
| CEC | California Energy Commission |
| CEQA | California Environmental Quality Act |
| CHAdeMO | A charging port standard for fast charging of EVs. |
| Charger | A device with one or more charging ports and connectors for charging EVs. Also referred to as electric vehicle supply equipment (EVSE). |
| Charging Network | A collection of chargers located on one or more property(ies) that are connected via digital communications to manage the facilitation of payment, the facilitation of electrical charging, and any related data requests. |
| Charging Network Provider | The entity that operates the digital communication network that remotely manages the chargers. Charging network providers may also serve as charging station operators and/or manufacture chargers. |
| Charging Port | The system within a charger that charges one EV. A charging port may have multiple connectors, but it can provide power to charge only one EV through one connector at a time. May also be referred to as “port.” |
| Charging Session | The period after a charge attempt during which the EV is allowed to request energy. Charging sessions can be terminated by the customer, the EV, the charger, the charging station operator, or the charging network provider. |
| Charging Station Operator | The entity that owns the chargers and supporting equipment and facilities at one or more charging stations. Although this entity may delegate responsibility for certain aspects of charging station operation and maintenance to subrecipients or vendors, this entity retains responsibility for operation and maintenance of chargers and supporting equipment and facilities. In some cases, the charging station operator and the charging network provider are the same entity. |
| Commercial Motor Vehicle | A motor vehicle designed or regularly used to carry freight, merchandise, or more than ten passengers, whether loaded or empty, including buses, but not including vehicles used for vanpools, or recreational vehicles operating under their own power. Definition taken from 23 CFR 658.5. |
| Commercial Motor Vehicle Operator | An entity that operates a commercial motor vehicle as defined in this solicitation. |
| Connector | The device that attaches an EV to a charging port to transfer electricity. |
| Corridor Group | A group of one or more corridor segments. Under the NEVI formula program, 23 Corridor Groups are defined from the designated Alternative Fuel Corridors. |
| Corridor Segment | A portion of a highway corridor that is part of a Corridor Group. Under the NEVI formula program, defined by a letter, A through E. |
| DCFC | Direct Current Fast Charger. Equipment that provides charging through a direct-current plug, typically at a rate of 50 kilowatts or higher. |
| DER | Distributed Energy Resource. Small, modular, energy generation and storage technologies that provide electric capacity or energy where it is needed. |
| E-76 | E-76 is the federal-aid authorization to proceed process. A Project Authorization/Adjustment Request Form (DOT LAPM 3-A, found at https://forms.dot.ca.gov/v2Forms/servlet/FormRenderer?frmid=DOTLAPM3A) is used to request FHWA authorization to begin reimbursable work for a specific project phase, such as construction. FHWA authorization or “E-76 approval” means the request to begin work is approved and establishes the date from which reimbursable work may begin. |
| EV | Electric Vehicle. A motor vehicle that is either partially or fully powered on electric power received from an external power source. In the NEVI regulation, EVs do not include golf carts, electric bicycles, or other micromobility devices. |
| EV Charging Station | The area in the immediate vicinity of one or more chargers and includes the chargers, supporting equipment, parking areas adjacent to the chargers, and lanes for vehicle ingress and egress. An EV charging station could comprise only part of the property on which it is located. Multiple chargers may be associated with one EV charging station. EV charging station may also be referred to as “charging station” or “station.” |
| EVITP | The Electric Vehicle Infrastructure Training Program. EVITP provides training and certification for electricians installing EVSE. |
| EVSE | Electric Vehicle Supply Equipment. A “charger” as defined. |
| Experienced Contractor | A company or organization with a proven record of accomplishment in overseeing the procurement, permitting, and installation of at least 20 DCFCs. The company or organization must have completed installations at least three or more different property locations for three or more different customers since January 1, 2018. |
| FHWA | U.S. Department of Transportation, Federal Highway Administration |
| GAAP | Generally Accepted Accounting Principles |
| Hardware | The machines, wiring, and other physical components of an electronic system including onboard computers and controllers. |
| Installed | Attached or placed at a location and available for use for a charging session. The date a charger is installed is the date it is first available for use for a charging session. |
| kW | Kilowatt |
| LAPM | Caltrans Local Assistance Procedures Manual |
| Level 1 Charger | A charger that operates on a circuit from 110 volts to 120 volts and transfers AC electricity to a device in an EV that converts AC to direct current to charge an EV battery. |
| Level 2 Charger | A charger that operates on a circuit from 208 volts to 240 volts and transfers AC electricity to a device in an electric vehicle (EV) that converts AC to direct current to charge an EV battery. |
| LD | Light Duty vehicles are vehicles with a gross vehicle weight rating less than or equal to 10,000 pounds. |
| Maintenance | Any instance in which preventive or corrective maintenance is carried out on equipment. |
| MDHD | Medium-Duty and Heavy-Duty. MDHD vehicles are vehicles with a gross vehicle weight rating (GVWR) above 10,000 pounds and include vans, buses, and trucks. Medium-duty (MD) are vehicles greater than 10,000 pounds GVWR and less than or equal to 26,000 pounds. Heavy-duty (HD) vehicles have GVWR greater than 26,000 pounds. |
| NEPA | National Environmental Policy Act |
| Networked | A charger that can receive or send commands or messages remotely from or to a charging network provider or is otherwise connected to a central management system, such as by using OCPP 2.0.1, for the purposes of charger management and data reporting. |
| NEVI Formula Program | National Electric Vehicle Infrastructure Formula Program |
| NEVI Standards | Refers to the National Electric Vehicle Infrastructure Standards and Requirements, Final Rule, Code of Federal Regulations Section 23, Part 680 (23 CFR 680). See Section I.O. Reference Documents for the web link. |
| OCPI | Open Charge Point Interface. An open-source communication protocol that governs the communication among multiple charging networks, other communication networks, and software applications to provide information and services for EV drivers. |
| OCPP | Open Charge Point Protocol. An open-source communication protocol that governs the communication between chargers and the charging networks that remotely manage the chargers. |
| Operational | A charging port’s hardware and software are both online and available to use, or in use, and the charging port is capable of successfully dispensing electricity. |
| Preventative Maintenance | Maintenance that is performed on physical assets to reduce the chances of equipment failure and unplanned machine downtime. |
| Recipient | An applicant awarded a grant under a CEC solicitation. Please note that in FHWA documents, the definition of “recipient” may differ. |
| RSA | Registered Service Agency. An entity that repairs a commercial device that is registered with the California Department of Food and Agriculture Division of Measurement Standards. |
| SAE J3400 | A charging port standard for charging of EVs based on the North American Charging Standard (NACS) connector. |
| SFHA | Special Flood Hazard Area |
| Small Business | Please refer to California Government Code §14837 (d)(1)(A)-(B). “Small business” means an independently owned and operated business that is not dominant in its field of operation, the principal office of which is located in California, the officers of which are domiciled in California, and which, together with affiliates, has 100 or fewer employees, and average annual gross receipts of $15 million dollars or less over the previous three years, or is a manufacturer, as defined in subdivision (c), with 100 or fewer employees. For the purposes of public works contracts, as defined in Section 1101 of the Public Contract Code, and engineering contracts, as described in Section 4525, for public works projects, awarded through competitive bids or otherwise, “small business” means an independently owned and operated business that is not dominant in its field of operation, the principal office of which is located in California, the officers of which are domiciled in California, and which, together with affiliates, has 200 or fewer employees, and average annual gross receipts of $36 million dollars or less over the previous three years. |
| Software | A set of instructions, data, or programs used to operate computers and execute specific tasks. |
| Solicitation | Grant Funding Opportunity, which refers to this entire solicitation document and all its attachments and exhibits. |
| State | State of California |
| Subaward | For the Recipient, a subaward means all agreements it has with subrecipients and vendors. For a subrecipient, a subaward means all agreements it has with sub-subrecipients and vendors. For any lower-tiered level of sub-subrecipient, a subaward means all agreements it has with its own sub-subrecipients and vendors. |
| Subrecipient | A Subrecipient is defined as a person or entity that receives grant funds directly from the Recipient and is entrusted by the Recipient to make decisions about how to conduct some of the grant’s activities. A Subrecipient’s role involves discretion over grant activities and is not merely just selling goods or services. |
| Uptime | The time that a charging port is online and available for use per the formula in the Scope of Work (Attachment 15). |
| Vendor | A person or entity that sells goods or services to the Recipient, subrecipient, or any lower-tiered level of sub-subrecipient, in exchange for some of the grant funds and does not make decisions about how to perform the grant’s activities. The vendor’s role is ministerial and does not involve discretion over grant activities. |

## Cost of Developing Application

The Applicant is responsible for the cost of developing an application, and this cost cannot be charged to the State.

## Confidential Information

The Applicant shall not submit any confidential information as part of its application. All information submitted in an application will be considered and treated as non-confidential information that is subject to disclosure under the Public Records Act (Gov. Code § 7920.000 et seq.).

## Solicitation Cancellation and Amendments

It is CEC’s policy not to solicit applications unless there is a bona fide intention to award an agreement. However, if it is in the State’s best interest, the CEC reserves the right, in addition to any other rights it has, to do any of the following:

- Cancel this solicitation;

- Revise the amount of funds available under this solicitation;

- Amend this solicitation as needed; and/or

- Reject any or all applications received in response to this solicitation.

If the solicitation is amended, the CEC will post an addendum on CEC’s solicitation information website at www.energy.ca.gov/funding-opportunities/solicitations.

## Errors

If an Applicant discovers any ambiguity, conflict, discrepancy, omission, or other error in the solicitation at any time prior to 5:00 p.m. of the application deadline date, the Applicant should immediately notify the CEC of the error in writing and request modification or clarification of the solicitation. The CEC will provide modifications or clarifications by written notice to all entities that requested the solicitation, without divulging the source of the request for clarification. The CEC shall not be responsible for failure to correct errors.

## Modifying or Recalling an Application

An Applicant may recall or modify a submitted application within ECAMS before the deadline to submit applications. Applications cannot be changed after that date and time. An application cannot be “timed” to expire on a specific date. For example, a statement such as the following is non-responsive to the solicitation: “This application and the cost estimate are valid for 60 days.”

## Immaterial Defect

The CEC may waive any immaterial defect or deviation contained in an Applicant’s application. The CEC’s waiver shall in no way modify the application or excuse an Applicant proposed for funding from full compliance with solicitation requirements.

## Opportunity to Cure Administrative Errors

The CEC understands and appreciates the significant time and expense Applicants spend preparing applications. An administrative error that prevents an Applicant from submitting a complete application frustrates both the CEC and Applicants. The purpose of this process is to reduce the number of applications screened out or receiving a significantly reduced score for administrative errors while maintaining a fair competition. This process also ensures better competition and thus better projects to benefit California.

After the application deadline, an Applicant might identify, or the Evaluation Committee may find what reasonably appears to be, an administrative error. For purposes of this solicitation only, an administrative error is defined as an Applicant’s inadvertent mistake that prevents materials in existence as of the application deadline from appearing in its submitted application. Examples include, but are not limited to, accidentally:

- Scanning and submitting every other page in a document instead of every page.

- Submitting the wrong document.

- Leaving out a document.

If the Evaluation Committee find what reasonably appears to be an administrative error, they can communicate with the Applicant to confirm. If an Applicant finds an administrative error in its application, it should immediately contact the Commission Agreement Officer listed in the “Contact Information” section of this solicitation.

If an administrative error has been identified and communicated to the Commission Agreement Officer, the CEC may, but is not required to, allow the Applicant a period of time to provide the missing materials. Reasons why the CEC might NOT allow an Applicant to fix an administrative error include, but are not limited to:

- The funds have a deadline that does not allow time to fix the error.

- The application has been screened out or does not receive a passing score for reasons unrelated to the administrative error, making irrelevant any efforts to fix the error.

- The Applicant brings the error to the CEC’s attention too late in the solicitation process (e.g., after awards have been approved at a Business Meeting).

If the Evaluation Committee allows an Applicant the opportunity to fix an administrative error, the Commission Agreement Officer will communicate in writing to the Applicant’s project manager listed the deadline by which the Applicant must provide the missing materials. Reasonable efforts will be made to confirm receipt of the notice, but actual notice cannot be guaranteed and the obligation is on the Applicant to ensure the proper contact(s) are listed and available to respond. The Evaluation Committee will not consider any materials submitted after the deadline.

This process only allows Applicants to submit materials in existence as of the application deadline. This process does NOT allow Applicants to submit material created or modified after the application deadline. The CEC has sole discretion to determine whether materials submitted are eligible for consideration by the Evaluation Committee under this opportunity to cure.

Applicants must include the following certification along with the materials it submits to fix an administrative error and must explain why the materials were not provided due to an inadvertent administrative error:

“I certify on behalf of the Applicant that the materials provided herein existed at the time of the application deadline, have not been modified since, and were not originally provided due to an inadvertent administrative error as described herein.”

The Evaluation Committee is not responsible for finding, or communicating with the Applicant about, any errors in an application. Applicants remain solely responsible for submitting applications, including any material submitted to fix an administrative error, that meet all solicitation requirements.

## Disposition of Applicant’s Documents

The entire evaluation process from receipt of applications up to the posting of the Notice of Proposed Award is confidential. On the Notice of Proposed Award posting date, or date of solicitation cancellation, all applications and related material submitted in response to this solicitation become a part of the property of the State and public record.

## Applicants’ Admonishment

This solicitation contains the instructions governing the requirements for a firm quotation to be submitted by interested Applicants, the format in which the technical information is to be submitted, the material to be included, the requirements which must be met to be eligible for consideration, and applicant responsibilities. Applicants are responsible for carefully reading the entire solicitation, asking appropriate questions in a timely manner, submitting all required responses in a complete manner by the required date and time, and making sure that all procedures and requirements of the solicitation are followed and appropriately addressed.

## Agreement Requirements

The content of this solicitation shall be incorporated by reference into the final agreement. See the sample agreement terms and conditions referenced in Section II.A.2 of this solicitation. Final agreements with Recipients that are a California Tribal Organization serving a California Native American Tribe shall also have the Special Terms and Conditions for California Tribal Organizations serving California Native American Tribes with Sovereign Immunity, found at https://www.energy.ca.gov/media/12259.

The CEC reserves the right to negotiate with Applicants to modify the project scope, the level of funding, or both. If CEC is unable to successfully negotiate and execute a funding agreement with an Applicant, CEC, at its sole discretion, reserves the right to cancel the pending award and fund the next highest ranked eligible project according to the evaluation process discussed in Section I.D. How Award is Determined.

If proposed for an award, the CEC reserves the right to request information it deems appropriate to evaluate the financial condition of a proposed awardee, subrecipients, and vendors prior to approval of a grant award. If the CEC, in its sole discretion, determines that a proposed awardee’s, a subrecipient’s, or a vendor’s financial condition may materially impact its ability to complete the proposed project, the CEC reserves the right to cancel the proposed award.

The CEC must formally approve all proposed grant awards. Grant agreements must be scheduled and considered at a CEC Business Meeting for approval by the CEC.

The CEC will send the approved agreement, including the NEVI terms and conditions, Special Federal Award terms and conditions, and any additional terms and conditions to the grant recipient for review, approval, and signature. Once the grant recipient signs, the CEC will fully execute the agreement. Recipients are approved to begin the project only after full execution of the agreement, including any authorizations needed from the FHWA.

## No Agreement Until Signed and Approved

No agreement between the CEC and an Applicant is in effect until the agreement is approved at a CEC Business Meeting and signed by both the grant recipient and the CEC.

The CEC reserves the right to modify the award documents prior to executing the agreement.

## Executive Order N-6-22 – Russia Sanctions

On March 4, 2022, Governor Gavin Newsom issued Executive Order N-6-22 (the EO) regarding Economic Sanctions against Russia and Russian entities and
individuals. “Economic Sanctions” refers to sanctions imposed by the U.S.
government in response to Russia’s actions in Ukraine, as well as any sanctions
imposed under state law. By submitting a bid or proposal, Applicant represents
that it is not a target of Economic Sanctions. Should the State determine
Applicant is a target of Economic Sanctions or is conducting prohibited
transactions with sanctioned individuals or entities, that shall be grounds for
rejection of the Applicant’s bid/proposal any time prior to agreement execution, or, if determined after agreement execution, shall be grounds for termination by the State.

Federal NEVI Standards: https://www.federalregister.gov/documents/2023/02/28/2023-03500/national-electric-vehicle-infrastructure-standards-and-requirements

Caltrans. California Manual on Uniform Traffic Control Devices. https://dot.ca.gov/programs/safety-programs/camutcd.

A directional sign displayed, usually with an arrow panel, off the freeway system to advise motorists where to turn en route to a destination.

“Commercial” in this context applies to “operations in which the amount dispensed affects customer charges or compensation” https://www.cdfa.ca.gov/dms/docs/publications/2024/2024_Combined_FRM.pdf.

The Past Performance Evaluation is available on the CEC website at: https://www.energy.ca.gov/media/6595